| Programmes | Sub-programmes | Projects/activities | Location | Time Frame |  |  |  | Cost |  |  |  | Prog. Status |  | Implementing Dep'ts |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | 1 | 2 | 3 | 4 | GoG | IGF |  | Others | New | Ongoing | Lead | Coll. |
| Goal 1: Build a Prosperous Society |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ECONOMIC DEVELOPMENT | Local and economic development | - Support 1000 local businesses with training and funding | District Wide |  |  |  |  |  | 30,000 |  |  |  |  | BAC | DA |
|  |  | - Construction of 4No market and renovate 1No market. | Esiama, Akropong, Asomase, Nkroful, Aiyinase |  |  |  |  | 1,980,000.00 |  |  |  |  |  | Works Dep't | DA |
|  |  | - Create industrial village | Ampain |  |  |  |  | 450,000 |  |  | 150,000 |  |  | DA | BAC |
|  |  | - Establish a ceramics factory | Teleku Bokazo |  |  |  |  | 500,000 | 50,00 |  | 1,500.000 |  |  | DA | GFZB |
|  |  | - Support 40 SMEs to Register/formalize their businesses thru RGD | District Wide |  |  |  |  | 4,000 |  |  | 1,000 |  |  | BAC | RGD |
|  |  | - Organize annual Business Expo | District Wide |  |  |  |  | 70,000.00 | 30,000 |  |  |  |  | ENI/ BAC | Agri Dept/ENI |
|  |  | - Support youth and vulnerable with employable skills | District wide |  |  |  |  | 100,000.00 |  |  | 260,000.00 |  |  | BAC | MOFA, DA |
|  |  | - Support in follow-up and counselling of businesses | District wide |  |  |  |  |  | 1,000.00 |  |  |  |  | BAC | DA |
|  | Agricultural and Rural Development | - Prepare and implement 2024 Local Economic Development (LED) Plan | District wide |  |  |  |  | 3,000.00 |  |  |  |  |  | DA | BAC |
|  |  | - Support the Implementation of the EDGE Project | Menzezor |  |  |  |  |  |  |  | 1,900,000.00 |  |  | ENI | MOFA/DA |
|  |  | - Establish and update database on all farmers in the district | District Wide |  |  |  |  | 4,100 |  |  |  |  |  | Agri Dept | DA/Statistics |
|  |  | - Advanced E-Extension and sensitization activities (study tour, malaria, COVID 19, child labour, HIV, pest and infections) | Menzezor, District Wide |  |  |  |  | 4.800 |  |  |  |  |  | Agri Dept | Works Dep't, DA/ NCCE |
|  |  | - Train 500 and equip 200 youth in modern agriculture and agro-business | District Wide |  |  |  |  |  | 5,000 |  |  |  |  | Agri Dept | Agri Dept. |
|  |  | - Organize District Level Farmers Day Celebration | Selected Community |  |  |  |  | 50,000 |  |  |  |  |  | Agri Dept | DPO, DA |
|  |  | - Conduct yield studies on selected crops (rice, maize, cassava and plantain) | District Wide |  |  |  |  |  | 5,375 |  |  |  |  | Agri Dept. | MOFA |
|  |  | - Collaborate with forestry commission to plant and nature 5,000 trees under the Green Ghana Project. | District wide |  |  |  |  | 500.00 |  |  |  |  |  | Forestry | Agric Dept |
|  |  | - Early warning systems and emergency preparedness for livestock and crop production. (small ruminant, COVID,PPE and FAW) | District wide |  |  |  |  | 2,810.00 |  |  |  |  |  | Agric Dept | DA/NADMO |
|  |  | - Support the distribution of 10,000 (PERD) rubber seedling and 50,000 oil palm seedling by CSIR and MDF. | District wide |  |  |  |  | 21,500 |  |  |  |  |  | Agric Dept | DA |
|  |  | - Organise capacity building training for staffs ( AEAs, DDOs) |  |  |  |  |  | 364 |  |  | 3000 |  |  | Agric Dept | DA |
|  |  | - Train 20 women farmers and 5 AEAs on local food utilization |  |  |  |  |  | 950.00 |  |  |  |  |  | Agric Dept | DA |
|  |  | - Showcase to 20 women farmers the establishment of home gardens |  |  |  |  |  | 1,230 |  |  |  |  |  | Agric Dept | DA |
|  |  | - Train 10 farmers (5 males and 5 females) on safe use and handling of Agro-Chemicals by the end of October 2022. |  |  |  |  |  | 790 |  |  |  |  |  | Agric Dept | DA |
|  |  | - Support the District Chamber of Agriculture, Commerce and Technology (Training for DCAT officers) | District Assembly |  |  |  |  |  | 5,000 |  | 5,000 |  |  | Agri Dept | DA |
|  | Tourism and creative Arts development | - Support and promote Kundum Festival and other | District wide |  |  |  |  |  | 25,000 |  |  |  |  | Culture Unit | DA |
|  |  | - Form 10 tourism clubs in basic and Senior High Schools | Selected Schools |  |  |  |  |  | 2,500 |  |  |  |  | GES | Culture/ DA |
|  |  | - Rehabilitation of Kwame Nkrumah Motel | Nkroful |  |  |  |  |  | 110,000 |  |  |  |  | Works | DA |
| Sub-Total |  |  |  |  |  |  |  | 413,600 | 175,575 | 58,500 |  |  |  |  |  |

| Programmes | Sub-programmes | Projects/activities | Location | Time Frame |  |  |  | Cost |  |  | Prog. Status |  | Implementing Dep'ts |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | 1 | 2 | 3 | 4 | GoG | IGF | Others | New | Ongoing | Lead | Coll. |
| Goal 2: Create Opportunities for all |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| EDUCATION AND TRAINING | Pre-Tertiary Education | - Support STMIE programme | Nkroful |  |  |  |  | 3,625 | 3,000 |  |  |  | GES | DA |
|  |  | - Completion/Construction of 2No. 6-unit classroom block | Esiama SDA, KIMTECH. Anwia(N), Ngabawie(N) |  |  |  |  | 1,110,000.00 | 169,500 |  |  |  | DA | GES |
|  |  | - Completion of 5No. 3-unit classroom blocks and construction of 1No 3-unit classroom block | Nyamebekyere, Akropong, Awiebo, Asomase (N) |  |  |  |  | 616,223.9 |  | 465,196.79 |  |  | DA | GES |
|  |  | - Completion of 2No. KG and construction of 1No KG block | Anlobra, Teleku Bokazu, Kotokuom(N), Kikam |  |  |  |  | 800,000 | 315,368.34 |  |  |  | DA | GES |
|  |  | - Construction of 2 No. 4-unit teachers quarters | Adubrim, Kwasikrom, Matukwa |  |  |  |  | 240,000 | 220,000 | 300,000 |  |  | DA | Dev’t Partners, GES |
|  |  | - Completion and construction of Assembly Hall for Esiama Sec-Tec | Esiama, UBAISH |  |  |  |  | 412,000 | 47,500 |  |  |  | DA | GES |
|  |  | - Support to organize inter-school sports and gaming activities | District Wide |  |  |  |  |  | 10,000.00 |  |  |  | DA | GES |
|  |  | - Renovation of District Education Office | Nkroful |  |  |  |  |  | 50,000.00 |  |  |  | DA | GES |
|  |  | - Provide items for "my first day at school" celebrations and institute Best Teacher Award especially in deprived schools | Some Selected Schools |  |  |  |  | 20,000 | 18,500 | 15,000.00 |  |  | DA | GES/Private Schools |
|  |  | - procurement of school furniture and uniforms for schools at all levels | Some Selected Schools |  |  |  |  |  | 2,000,000.00 |  |  |  | Procurement | GES |
|  |  | - Support and award scholarship to needy but brilliant students | District wide |  |  |  |  | 50,000.00 |  | 1,500,000.00 |  |  | DA | Ghana Gas |
|  |  | - Formation and inauguration of 81 malaria clubs in basic Schools | Selected school |  |  |  |  | 2000.00 |  |  |  |  | GES | DA |
|  |  | - Organize reading competition in English and Local dialects in schools’ for basic schools | All Basic Schools |  |  |  |  | 10,000.00 |  |  |  |  | GES | DA |
|  |  | - Organize story telling competition and cultural festivals basic schools | All Basic Schools |  |  |  |  | 16,000.00 |  |  |  |  | GES | DA/Culture |
|  |  | - Train 20 to 48 existing teachers in covid-19 prevention guidelines | District wide |  |  |  |  | 2,000.00 |  |  |  |  | GES | GHS |
|  |  | - Organize capacity building on Job Services (ENI and USAID learning) | District wide |  |  |  |  |  |  | 20,000.00 |  |  | GES | ENI, USAID |
|  |  | - Conduct induction workshop for newly trained teachers | District wide |  |  |  |  | 15,000 |  |  |  |  | GES | DA/HRM |
|  |  | - Conduct SPAM in basic schools and Organize yearly mock exams for JHS students | District wide |  |  |  |  | 6,500 | 10,000.00 |  |  |  | GES | DA |
|  |  | - Support regular inspection and monitoring of schools.SMCs and PTAs | District wide |  |  |  |  |  | 4,500 |  |  |  | GES | DA |
|  | Primary Healthcare Delivery | - Construct a District Hospital at Nkroful | Nkroful |  |  |  |  | 120,000,000 |  |  |  |  | GHS | DA |
|  |  | - Provision of medical supplies to CHPS Compounds and Complete the upgrading and expansion works at St. Martin De Porres Hospital, Eikwe | Ngalekyi |  |  |  |  |  | 6,000 | 7,500 |  |  | DA | GNPC, GHS |
|  |  | - Construction of 2 No. CHPS Compounds | New Adiembra, Ebi, |  |  |  |  | 600,000.00 |  |  |  |  | DA | GHS |
|  |  | - Complete the construction of NHIS Office at Nkroful | Nkroful |  |  |  |  | 500,000 |  |  |  |  | DA | NHIS |
| HEALTH AND HEALTH SERVICE DELIVERY |  | - Conduct public health education and organize campaigns on mental health | District Wide |  |  |  |  |  | 8,000 |  |  |  |  |  |
|  |  | - Support to organize capacity building programmes for Health Staff for effective monitoring and evaluation | District Wide |  |  |  |  | 15,500 |  | 22,000 |  |  | GHS | NGO |
|  |  | - Promote ante/post natal services and organize district health wide health screening activities. | District Wide |  |  |  |  | 7,500 |  | 4,000 |  |  | GHS | DA |
|  |  | - Continue the administration of vaccines under the NID programme | District Wide |  |  |  |  |  | 6,000 | 2,000 |  |  | GHS | DA |
|  |  | - Embark on quarterly regenerative health and nutrition outreach programmes | District Wide |  |  |  |  | 12,125 |  |  |  |  | GHS | DA |
|  | HIV, AIDS/STIs and other infections | - Support HIV/AIDS and STIs, etc activities | District wide |  |  |  |  | 4,625 |  | 6,250 |  |  | GHS | NGOs |
|  |  | - Organize quarterly HIV/AIDS Committee Meetings and celebrate world AIDS day. | Nkroful |  |  |  |  | 11,000.00 |  |  |  |  | DAC | GHS |
|  |  | - Ensure registration of all birth and death in the district | District wide |  |  |  |  |  | 5,000 |  |  |  | Birth & death Dept. | DA |
|  |  | - Organize quarterly sensitization programmes on teenage pregnancy and child marriage | District wide |  |  |  |  |  | 19,100 |  |  |  | SWCD | DA/NCCE |
|  |  | - Provide support for family planning activities | District wide |  |  |  |  |  |  |  |  |  | GHS | DA |
|  | Food and Nutrition |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | - Monitor the school feeding programme to ensure quality and well balanced diet is served | District wide |  |  |  |  | 1,500 |  |  |  |  | Central Admin | DA |
| WATER AND ENVIRONMENTAL SANITATION | Water Supply, Waste Management and Environmental Sanitation | - Drilling of 10No. Mechanized boreholes | Nkroful, Adubrim, Akropong, Old an New Sanfo, Aiyinase |  |  |  |  | 250,000 |  | 10,000 |  |  | DA | DWST |
|  |  | - Construction/ Extension of water supply for selected communities | New and old Bakanta, Asanda, Nkroful, Kamgbuli,Asomase, Teleku Bokazo |  |  |  |  |  |  |  |  |  | DA | DWST |
|  |  | - Prepare, and implement the District Water and Sanitation Plan | District Assembly |  |  |  |  |  | 44,500 |  |  |  | DWST | DA |
|  |  | - Form and train 10No. WATSan Committees | Selected Communities |  |  |  |  | 25,000 |  |  |  |  | DWST | DA |
|  |  | - Construction of 9No. latrines for institution and public places | Basake, Asanta, Nvenlosolo, Salma, UBAISH, Esiama Market, Aiyinase Market, Nvuma, Edwakpole, Kikam, Boamokpole |  |  |  |  | 35,000 |  |  |  |  | Works Dept. | EHSU |
|  |  | - Monitor Day Care Centres and orphanages within the district | District Wide |  |  |  |  | 5,000 | 2,000 |  |  |  | SWCD | DA |
|  |  | - Facilitate the provision of resource persons such as sign language interpreters and braille transcribers at all levels | District wide |  |  |  |  |  | 4,000 |  |  |  | SWCD | PWD |
|  |  | - Promote the re-entry of dropouts and adolescent mothers back to school after childbirth | Predominant Communities |  |  |  |  |  | 5,000 |  |  |  | SWCD | GES |
|  |  | - Organize sensitization programmes on child labour and trafficking | District Wide |  |  |  |  |  | 13,000 |  |  |  | SWCD | DA, NCCE, LABOUR DEP'T, NCCE |
|  |  | - Institute Child Protection Committees in 10 Communities and enforce child rights and gender-related by-laws | District wide |  |  |  |  |  | 5,000 |  |  |  | SWCD | DA |
|  |  | - Settle child maintenance cases and Organize community engagements and behavioural change campaigns to promote positive parenting | District wide |  |  |  |  |  | 5,000 |  |  |  | SWCD | UNICEF |
|  |  | - Organise and support community mobilization activities in 10 communities | District wide |  |  |  |  |  | 1,500 | 6,625 |  |  | SWCD | Gender Desk |
|  | Women empowerment | - Organize sensitization Campaigns on gender-based violence and other harmful cultural practices in 10 Community | District Wide |  |  |  |  | 7,100 |  | 2,500 |  |  | SWCD/DPCU | DA |
|  |  | - Organize skill training for women on VSLA and other income generating activities | District Wide |  |  |  |  |  | 20,000 | 3,000 |  |  | SWCD | DA, BAC |
|  | Social Protection | - Mobilize indigenes and vulnerable people for NHIS registration | District Wide |  |  |  |  | 1,900 |  |  |  |  | SWCD | NHIS, DA |
|  |  | - Support People With Disabilities (PWDs) with training skills, items, cash, school fees medical bills and start-up capital. | District Wide |  |  |  |  | 200,000.00 |  |  |  |  | SWCD | BAC, DA |
|  |  | - Monitor and support the Livelihood Empowerment Against Poverty (LEAP) programme | District wide |  |  |  |  |  | 2,000.00 |  |  |  | SWCD | DA |
| Sub-Total |  |  |  |  |  |  |  | 17,251,500 | 641,900 | 10,311,289 |  |  |  |  |

| Programmes | Sub-programmes | Projects/activities | Location | Time Frame |  |  |  | Cost |  |  | Prog. Status |  | Implementing Dep'ts |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | 1 | 2 | 3 | 4 | GoG | IGF | Others | New | Ongoing | Lead | Coll. |
| Goal 3: Safeguard the Natural Environment and ensure a resilient Built Environment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | - Revive conservation committee groups and build women capacity in conservation | District Assembly |  |  |  |  | 4,200 |  | 3,000 |  |  | DA | WEWICON |
| Environment |  | - Protect natural reserves (mangroves and forest) and recreation areas from encroachment | District Wide |  |  |  |  | 26,500 | 15,000.00 |  |  |  | PPD | Works Dept. |
|  |  | - Organize food and nutrition campaign in 15schools and 5health centres | District wide |  |  |  |  |  | 13,000 |  |  |  | EHSU | DA |
|  |  | - conduct 200 domicilary and food premises inspection | Districtwide |  |  |  |  |  |  |  |  |  |  |  |
|  |  | - Implement the CLTS programme and intensify environmental health education campaigns in 30 schools | District wide |  |  |  |  | 10,000 |  |  |  |  | EHSU | DA |
|  |  | - Sensitize 10communities on improved sanitation | District Wide |  |  |  |  |  |  |  |  |  |  |  |
|  |  | - Construction of slaughter house | Aiyinasi, Esiama, Asasetre (market places) |  |  |  |  | 128,000 |  |  |  |  | DA | EHSU |
|  |  | - organize medical screening of 500 food vendors | District wide |  |  |  |  | 1 7,500 |  |  |  |  | EHSU | GHS, DA |
|  |  | - 0rganise clean exercises in 16 communities | Selected communities |  |  |  |  | 30,000.00 |  |  |  |  | EHSU | DA |
|  |  | - Ensure the control of noise pollution | District wide |  |  |  |  |  | 12,000.00 |  |  |  | EHSU | DA |
|  |  | - Educate and inspect galamsey site in the district to reclaim lands and plant trees | District wide |  |  |  |  | 120,000.00 |  |  |  |  | EHSU | DA |
|  |  | - Monitor waste collection by zoomlion and Evacuate refuse from communities | District wide |  |  |  |  |  | 2,000 |  |  |  | EHSU | Zoomlion |
|  |  | - Review and prepare DESSAP | District Assembly |  |  |  |  | 30,000.00 |  |  |  |  | EHSU | DA |
|  |  | - Arrest, educate and prosecute recalcitrant sand winners at the beach | District Wide |  |  |  |  |  |  | 15,000 |  |  | EHSU | DA |
| RESILIENT BUILT ENVIRONMENT |  | - Organize Capacity Building Training in Climate Change for DPCU/HODSMembers | District Assembly |  |  |  |  |  |  | 6,500 |  |  | Agri Dept. | DA |
|  |  | - Train farmers on climate smart agriculture technologies | District wide |  |  |  |  | 2,000 |  |  |  |  | Agric .Dept. | MOFA |
|  |  | - Reshaping of Feeder roads and Monitoring of rehabilitation of roads | Selected communities |  |  |  |  | 85,000.00 |  |  |  |  | Feeder Roads | DA |
|  |  | - Support road safety activities in the District | District Wide |  |  |  |  | 120,000.00 |  |  |  |  | Road Safty | DA |
|  | Human Settlements Development and Housing | - Organize technical and statutory planning committee meetings | District Assembly |  |  |  |  |  | 25,000 |  |  |  | PPD | HODs |
|  |  | - Support the preparation of local plans | Bomoakpole |  |  |  |  |  | 20,000 |  |  |  | PPD | DA |
|  |  | - Sensitization of the public on permitting and development control | District Wide |  |  |  |  |  | 5,000 |  |  |  | PPD | Works Dep't, DA |
|  |  | - Organize joint inspections to check unauthorised developemts | District Wide |  |  |  |  |  | 40,000.00 |  |  |  | PPD | Works Dep't, DA |
|  |  | - Prepare operation and maintenance (O&M) Plan | District Assembly |  |  |  |  | 3,000 |  |  |  |  | Works Dep't | Dev't Planning Unit |
|  |  | - Undertake building inspections and ensure that all public buildings are disability friendly | District wide |  |  |  |  |  | 8,250 |  |  |  | Works Dep't | DA |
| Sub-Total |  |  |  |  |  |  |  | 23,685,650 | 229,620 | 13,000 |  |  |  |  |

| Programmes | Sub-programmes |  | Projects/activities |  |  | Location |  | Time Frame |  |  |  |  |  |  |  | Cost |  |  |  |  |  | Prog. Status |  |  |  | Implementing Dep'ts |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  | 1 |  | 2 |  | 3 |  | 4 |  | GoG |  | IGF |  | Others |  | New |  | Ongoing |  | Lead |  | Coll. |  |
| Goal 4: Maintain a Stable, United and Safe Society |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Resource Mobilization and Expenditure Management |  | - Update economic/ Tourism data to improve revenue |  |  | District wide |  |  |  |  |  |  |  |  |  | 100,000.00 |  |  |  |  |  |  |  |  |  | Statistical Dept. |  | Revenue Unit |  |
|  |  |  | - Provide revenue collection and management logistics |  |  | District Assembly |  |  |  |  |  |  |  |  |  | 12,000 |  |  |  |  |  |  |  |  |  | Revenue Unit |  | GIZ, DA |  |
|  |  |  | - Organize public sensitization on revenue mobilization in market places and lorry stations |  |  | Aiyinase, Asasetre, Esiama, Teleku Bokazo |  |  |  |  |  |  |  |  |  |  |  | 7,500 |  |  |  |  |  |  |  | Revenue Unit |  | Budget/Finance, Works, PPA |  |
|  |  |  | - Mount and update revenue performance and Accountability Bill Boards at the Various Area Councils |  |  | Esiama, Asasetre, Awiebo Basake, Aiyinase, Kikam, Nkroful, Atoabo |  |  |  |  |  |  |  |  |  | 22,000 |  |  |  |  |  |  |  |  |  | Fin. Dep't |  | DA |  |
|  |  |  | - Prepare and Implement a Revenue Improvement Action Plan |  |  | District Assembly |  |  |  |  |  |  |  |  |  |  |  | 7,000 |  |  |  |  |  |  |  | DBU/Fin Dept |  | DA |  |
| DEMOCRACY, GOVERNANCE AND PUBLIC ACCOUNTABILITY | Local Government and Decentralization |  | - Construction of 2No. Area Council Offices and 2 Community Centers |  |  | Esiama, Aiyinase Adubrim, Aiyinase North, New Bakanta |  |  |  |  |  |  |  |  |  | 500,000.00 |  | 100,000 .00 |  |  |  |  |  |  |  | DA |  | WORKS/DPO |  |
|  |  |  | - Procurement of double cabin Pickup vehicle |  |  | DA |  |  |  |  |  |  |  |  |  |  |  | 550,000.00 |  |  |  |  |  |  |  | Procurement |  | Works/PPD |  |
|  |  |  | - Procurement of Streetlights |  |  | District wide |  |  |  |  |  |  |  |  |  |  |  | 500,000.00 |  |  |  |  |  |  |  | Procurement |  | DA |  |
|  |  |  | - Procurement of Construction materials for self -help projects |  |  | District wide |  |  |  |  |  |  |  |  |  |  |  | 500,000.00 |  |  |  |  |  |  |  | DA |  | DA |  |
|  |  |  | - Organize all statutory meetings |  |  | District Assembly |  |  |  |  |  |  |  |  |  | 100,000.00 |  | 50,000.00 |  |  |  |  |  |  |  | Central Admin |  | DA |  |
|  |  |  | - Maintenance of Assembly vehicles and other bungalows |  |  | District Assembly |  |  |  |  |  |  |  |  |  | 300,000.00 |  | 50,000.00 |  |  |  |  |  |  |  | Central Admin |  | DA |  |
|  |  |  | - Coordinate the preparation of Community Action Plans |  |  | District Assembly |  |  |  |  |  |  |  |  |  | 10,000.00 |  |  |  |  |  |  |  |  |  | Dev't Planning |  | DPCU |  |
|  |  |  | - Review and prepare Annual Action Plans and Composite Budgets |  |  | District Assembly |  |  |  |  |  |  |  |  |  | 50,000.00 |  |  |  |  |  |  |  |  |  | Dev't Planning, Budget Unit |  | HODs |  |
|  |  |  | - Undertake Town Hall Meetings on AAPs, fee-fixing and composite annual budget |  |  | Alll Area Council Offices |  |  |  |  |  |  |  |  |  | 50,000 |  | 10,000.00 |  | 5,000 |  |  |  |  |  | Dev't Planning |  | Budget/HODs |  |
|  |  |  | - Oganize Public Hearings of the MTDP (2022-2025). |  |  | District Assembly |  |  |  |  |  |  |  |  |  | 30,000.00 |  | 40,000 |  |  |  |  |  |  |  | Dev’t Planning |  | HODs, other stakeholders |  |
|  |  |  | - Organize capacity building training for staffs, Assemblymembers, revenue collectors |  |  | Administration |  |  |  |  |  |  |  |  |  | 60,000.00 |  | 20,000.00 |  |  |  |  |  |  |  | HR |  | DA |  |
|  |  |  | - Administer comprehensive HRMIS and submit monthly returns to RCC |  |  | Administration |  |  |  |  |  |  |  |  |  | 30,000.00 |  |  |  |  |  |  |  |  |  | HR |  | DA |  |
|  |  |  | - Processing of personnel input forms for promotion/salary restoration/ New Entrant |  |  | Administration |  |  |  |  |  |  |  |  |  |  |  | 20,000.00 |  |  |  |  |  |  |  | HR |  | DA |  |
|  |  |  | - Procure office stationery logistics and others |  |  | District Assembly |  |  |  |  |  |  |  |  |  | 100,000.00 |  | 50,000.00 |  |  |  |  |  |  |  | Procurement |  | DA |  |
|  |  |  | - Maintenance of office equipment and logistics |  |  | District Assembly |  |  |  |  |  |  |  |  |  | 50,000.00 |  |  |  |  |  |  |  |  |  | Procurement |  | DA |  |
|  | Human Security and Public Safety |  | - Construction of Police Station |  |  | Asomase |  |  |  |  |  |  |  |  |  |  |  | 400,000 |  |  |  |  |  |  |  | DA |  | GPS |  |
|  |  |  | - Conduct fire safety inspections at all public places and other others of Fire service |  |  | Selected Communities |  |  |  |  |  |  |  |  |  | 8,300 |  |  |  |  |  |  |  |  |  | GNFS |  | DA, NADMO |  |
|  | Corruption and Economic Crimes |  | - Support all activities of the Audit unit |  |  | District Assembly |  |  |  |  |  |  |  |  |  | 40,000 |  |  |  |  |  |  |  |  |  | Internal Audit |  | External Audit |  |
|  | Law and Order |  | - Lobby for the posting of more Police Personnel into the district |  |  | District Assembly |  |  |  |  |  |  |  |  |  |  |  | 7,500 |  |  |  |  |  |  |  | DISEC |  | GPS |  |
|  |  |  | - Support the Police Service and other Security Agencies with Logistics |  |  | District Assembly |  |  |  |  |  |  |  |  |  | 60,500 |  |  |  | 50,000 |  |  |  |  |  | DISEC |  | GPS |  |
|  |  |  | - Organize DISEC Meetings |  |  | District Wide |  |  |  |  |  |  |  |  |  |  |  | 40,000.00 |  |  |  |  |  |  |  | Central Admin |  | DA |  |
|  | Civil Society and Civic Engagement |  | - Collaborate with NGO to implement the Youth inclusive development programme |  |  | District Assembly |  |  |  |  |  |  |  |  |  |  |  | 10,000 |  | 50,500 |  |  |  |  |  | Dev’t Planning |  | FON/GIZ |  |
|  |  |  | - Support Religious activities |  |  | District Wide |  |  |  |  |  |  |  |  |  | 30,800 |  |  |  |  |  |  |  |  |  | DA |  |  |  |
| TOTAL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 104,700 |  | 170,350 |  | 18,500 |  |  |  |  |  |  |  |  |  |
| Programmes |  | Sub-programmes |  | Projects/activities | Location |  | Time Frame |  |  |  |  |  |  |  | Cost |  |  |  |  |  | Prog. Status |  |  |  | Implementing Dep'ts |  |  |  |
|  |  |  |  |  |  |  | 1 |  | 2 |  | 3 |  | 4 |  | GoG |  | IGF |  | Others |  | New |  | Ongoing |  | Lead |  | Coll. |  |
| Goal 5: Mainstream emergency planning and preparedness into Ghana’s development planning agenda at all levels to respond to potential internal and external threats (including COVID-19) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| EMERGENCY PLANNING AND RESPONSE (INCLUDING COVID-19 RECOVERY PLAN) |  | Hydrometeological Threats |  | - Organize community sensitizations on disaster prevention | District Wide |  |  |  |  |  |  |  |  |  | 9,500 |  |  |  |  |  |  |  |  |  | NADMO |  | DA, NCCE |  |
|  |  |  |  | - Organize pests and insect infection sensitization campaign in communities | District Wide |  |  |  |  |  |  |  |  |  |  |  | 6,000 |  | 4,500 |  |  |  |  |  | NADMO |  | MOFA, NCCE |  |
|  |  |  |  | - Formation of Disaster Risk Reduction clubs in schools and communities | Selected Schools |  |  |  |  |  |  |  |  |  |  |  | 8,000 |  |  |  |  |  |  |  | NADMO |  | GES, DA |  |
|  |  |  |  | - Organize Disaster Risk Reduction training programmes at zonal levels | District Wide |  |  |  |  |  |  |  |  |  |  |  |  |  | 3,000 |  |  |  |  |  | NADMO |  | GNFS, DA |  |
|  |  |  |  | - Support NADMO activities | District Assembly |  |  |  |  |  |  |  |  |  | 8,000 |  |  |  |  |  |  |  |  |  | DA |  | NADMO, Private Sector |  |
|  |  |  |  | - Train Area Council Members and Traditional Authorities on impact of sand winning and galamsey on the environment | District Wide |  |  |  |  |  |  |  |  |  |  |  | 6,000 |  |  |  |  |  |  |  | NADMO |  | DA |  |
|  |  | Biological Threats |  | - Undertake surveillance, monitoring and evaluation of Health threats and epidemics and pandemics | District Wide |  |  |  |  |  |  |  |  |  |  |  | 6,000 |  |  |  |  |  |  |  | DHD |  | NCCE |  |
|  |  |  |  | - Intensify monitoring at Filling Stations to ensure adherence to Standard Operating Procedures. | District Wide |  |  |  |  |  |  |  |  |  |  |  | 6,000 |  |  |  |  |  |  |  | GNFS |  | Security agencies |  |
|  |  |  |  | - Support the establishment of a well-resourced Emergency Centre | District Wide |  |  |  |  |  |  |  |  |  |  |  | 60,000 |  |  |  |  |  |  |  | DA |  | Private Sector |  |
|  |  |  |  | - Create awareness on the consequences of ethnic and chieftaincy conflicts | District Wide |  |  |  |  |  |  |  |  |  |  |  |  |  | 4,500 |  |  |  |  |  | NCCE |  | DA |  |
|  |  | Covid-19 Response |  | - Conduct sensitization on covid-19 Prepare and implement a covid-19 recovery Plan | District Wide |  |  |  |  |  |  |  |  |  |  |  | 6,000 |  |  |  |  |  |  |  | NCCE |  | DA |  |
|  |  |  |  | - Support Public Health Emergency Management Committee | District Wide |  |  |  |  |  |  |  |  |  |  |  | 40,800 |  |  |  |  |  |  |  | DA |  | DHD |  |
|  |  |  |  | - Vaccinate 50,000 people against covid-19 | District Wide |  |  |  |  |  |  |  |  |  |  |  | 35,000 |  |  |  |  |  |  |  | DHD |  | DA |  |
|  |  |  |  | - Prepare and implement drainage plans for flood prone areas | District Assembly |  |  |  |  |  |  |  |  |  |  |  | 3,000 |  |  |  |  |  |  |  | PPD |  | Works Dep't, DA |  |
|  |  |  |  | - Frequently desilt choked drains | Major Communities |  |  |  |  |  |  |  |  |  | 6,000 |  | 12,000.00 |  |  |  |  |  |  |  | EHSU |  | PPD,WORKS,NADMO |  |
| Sub-Total |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 17,500 |  | 118,300 |  | 12,000 |  |  |  |  |  |  |  |  |  |

| Programmes | Sub-programmes | Projects/activities |  | Location | Time Frame |  |  |  | Cost |  |  | Prog. Status |  | Implementing Dep'ts |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | 1 | 2 | 3 | 4 | GoG | IGF | Others | New | Ongoing | Lead | Coll. |
| Goal: Improve delivery of development outcomes at all levels |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| IMPLEMENTATION, COORDINATION, MONITORING AND EVALUATION | Implementation and Coordination | - Organize quarterly DPCU Meetings |  | District Assembly |  |  |  |  | 50,000 |  |  |  |  | Dev't Planning | DA/FON |
|  |  | - Prepare quarterly and Annual Progress Reports |  | District Assembly |  |  |  |  | 6,000 |  |  |  |  | Dev't Planning | DPCU/HODS |
|  |  | - Organize Capacity Building programme for DPCU members |  | District Assembly |  |  |  |  | 6,000 | 2,500 |  |  |  | FON/GIZ | HODs |
|  | Monitoring and Evaluation | - Organize quarterly Participatory Project Monitoring and review meetings |  | District Assembly |  |  |  |  | 2,000 |  |  |  |  | Dev't Planning | FON/GIZ /DPCU |
|  |  | - Conduct mid-term review of 2022-2025 DMTDP |  | District Assembly |  |  |  |  | 10,000 |  | 10,000.00 |  |  | Dev't Planning | FON/GIZ |
|  |  | - Establish and update Central Database for Planning and Budgeting |  | District Assembly |  |  |  |  | 10,000 |  |  |  |  | Statistical Dept. | HODs |
|  |  | - Conduct Monthly Market Survey |  | District Assembly |  |  |  |  | 5,000 | 2,500 |  |  |  | Statistical Dept. | HODs |
|  |  | - Disseminate statistical Data and projections with Relevant Units, Departments and Agencies in the District. |  | District Assembly |  |  |  |  | 10,000 |  |  |  |  | Statistical Dept. | HODs |
| Sub-Total |  |  |  |  |  |  |  |  | 69,000 | 10,000 | 5,500 |  |  |  |  |
| GRAND TOTAL |  |  |  |  |  |  |  |  | 41,541,950 | 1,345,745 | 10,418,789 |  |  |  |  |