DISTRICT MEDIUM-TERM DEVELOPMENT PLAN 
(2022-2025)

Prepared By: DISTRICT PLANNING COORDINATING unit

ELLEMBELLE DISTRICT ASSEMBLY

P.O BOX 34, NKROFUL

JULY, 2021

# FOREWORD

Sequel to the creation of the Ellembelle District Assembly (EDA) by Legislative Instrument (LI 1918) in December, 2007 as the highest political Authority, pursuant to section 12 of the Local Governance Act, 2016 (Act 936), it became one of the twenty-two (22) administrative Districts in the Western Region, pursuing the development of its jurisdiction.

Subsequently, the leadership of the Assembly took full charge of the development agenda of the district. As a requirement for local-level development, the Assembly through its District Planning and Coordinating Unit (DPCU), coupled with the support of all its stakeholders, has prepared and implemented its new District Medium Term Development Plans (DMTDP, 2022-2025) guided by the National Development Policy Framework and Guidelines produced and certified by the National Development Planning Commission.

The district has experienced a high rate of economic growth, improved domestic revenue mobilisation leading to increased Internal Generated Revenue (IGF), substantial reduction in poverty, crime and vulnerability levels and enhanced access to basic social services such as education, health, potable water and improved sanitation across the length and breadth of the district.  These enviable gains need to be sustained and greater efforts made to enhance the socio-economic conditions of the people in particular and the business community in general. To vigorously pursue the development policy - Agenda for Jobs: Creating Prosperity and Equal Opportunities for All, the Ellembelle District Assembly must position itself to provide not only critical public services delivery but also, facilitate the creation of jobs and wealth to support Ghana’s transformation to achieve a Ghana Beyond Aid.

The DMTDP offers a great opportunity for the Assembly and citizens to work together to ensure that the socio-economic development of the district is consistently advanced. Through this plan, the Assembly will pursue resilience planning, strengthen Public Private Partnership in delivering critical public goods and services and work towards achieving our vision of becoming an attractive investment destination with highly skilled manpower where the natural resources are harnessed on sustainable basis to the benefit of the district and the nation at large.

The emergence of the COVID-19 Pandemic presented a unique and challenging development dimension and thus called for a strategic preparedness and response that is robust enough to address the new challenges, mitigate the risks related to the new variants and secure a safer environment for all who live or do business in our district. The strategies also aim at building on achievements while guiding the coordinated action required at the local level, complimenting the national and global efforts to overcome the ongoing challenges in the response to the COVID-19 pandemic.

This plan has taken into consideration the harmonization of physical planning in space, investment attraction, revenue generation, gender and social protection, and regulatory compliance. It was prepared based on effective participation from all key and relevant stakeholders such as CSOs/NGOs, DPs, Private Sector, FBOs, among others. The DMTDP 2018 to 2021 was equally reviewed to ascertain and validate the existing situation and to provide the desired future and direction in the planning process as result of the changes that have occurred in the last couple of years and to ensure strategic, systematic and well-thought-out development for towns and communities as envisioned in the National Development Agenda.

The Assembly is convinced that the DMTDP (2022-2025) is of the highest quality and will meet all minimum requirements as expected by the authorities and benefits the people. The Assembly thus, makes a clarion call to all stakeholders to effectively support the implementation of the plan so that together we can deliver quality, holistic and sustainable development to our people.

…………………………………………….

HON KWASI BONZOH

DISTRICT CHIEF EXECUTIVE

Table of Contents

FOREWORD	i

LIST OF TABLES	i

EXECUTIVE SUMMARY	i

1.0	Introduction	i

1.1.1	Vision	i

1.1.2	Mission	i

1.1.3	Core Values	i

1.1.4	Functions	i

1.4.1	Conclusion	i

CHAPTER ONE	1

1.0	PERFORMANCE REVIEW AND PROFILE/CURRENT SITUATION/BASELINE	1

1.1	Introduction	1

1.2	Performance Review of District Medium Term Development Plan 2018-2021	1

1.2.1	Analysis of Performance Review	1

1.2.2	Key Challenges Encountered in Implementing the DMTDP 2018-2021	1

1.2.3	Lessons Learnt Which Have Implications for DMTDP (2022-2025)	1

1.2.4	Way Forward for DMTDP 2022-2025	1

1.2.5	Review of Assembly Finance	1

1.3	Analysis of Existing Situation/Compilation of the District Profile	1

1.3.1	Location and Size	1

1.3.1 Physical and Natural Environment	1

1.3.2	Soil, Vegetation and Agriculture	1

1.3.3	Climate and Disaster	1

1.3.4 Relief and Drainage	1

1.3.5	Spatial Analysis / Settlement	1

1.3.6	Culture	1

1.3.7	Governance	1

1.3.8	Security	1

1.3.9	Health Facilities	1

1.3.10	Educational Facilities	1

1.3.11	Information Communication Technology	1

1.3.12	Water and Sanitation	1

1.3.13	Local Economic Development	1

1.3.14	Tourism	1

1.3.15	Food and Nutrition Security	1

1.3.16	Trade and Commerce	1

1.3.17	Roads and Transport	1

1.3.18	Financial Institution	1

1.3.19	Child and Vulnerability Issues	1

CHAPTER TWO	1

2.0	PRIORITIZATION OF DEVELOPMENT ISSUES	1

2.1	Introduction	1

2.2	Harmonization of Community Needs and Aspirations with Identified Key Development Issues	1

2.3	Impact Analysis	1

CHAPTER THREE	1

3.0	DEVELOPMENT PROJECTIONS, GOALS, OBJECTIVES AND STRATEGIES	1

3.1	Introduction	1

3.2	Desired Future Conditions	1

3.3	Development Projections for 2022– 2025	1

3.3.1	Education	1

3.3.2	Water Facilities	1

3.3.3	Health Facilities	1

3.3.4	Population Projections	1

3.3.5	Population Size and Distribution	1

3.4	District Development Goal	1

3.4 Desired Future Maps	1

CHAPTER FOUR	1

4.0	DEVELOPMENT PROGRAMMES AND SUB-PROGRAMMES	1

4.1	Introduction	1

4.2	Composite Programmes of Action Linked to the Programme Based Budgeting	1

4.3	Programme Financing	1

4.4	Maintenance Plan of the DMTDP 2022 – 2025	1

CHAPTER FIVE	1

5.0 ANNUAL ACTION PLANS	1

5.1 Introduction	1

CHAPTER SIX	1

6.0	MONITORING AND EVALUATION PLAN	1

6.1	Introduction	1

6.2	Purpose of the M&E Plan	1

6.3	Monitoring	1

6.4	Stakeholders Analysis	1

6.5	Evaluation Arrangement	1

6.6	Participatory Monitoring and Evaluation	1

CHAPTER SEVEN	1

7.0	COMMUNICATION STRATEGY	1

7.1	Introduction	1

7.2	Communication Objectives	1

7.3	Dissemination of the Medium-Term Development Plan	1

7.4	Approaches/Channels for Communication	1

CONCLUSION	1

BIBLIOGRAPHY	Error! Bookmark not defined.

# LIST OF TABLES

Table 1. 1: Performance Review of MTDP 2018-2021	1

Table 1. 2: Revenue Performance from 2018-2020	1

Table 1. 3: Financial Performance (2018-2021)	1

Table 2. 1: Scoring Scales	1

Table 2. 2: Linking of Community needs/aspirations with Key Development Issues/gaps from performance review and profile	Error! Bookmark not defined.

Table 2. 3: List of Prioritized Development Issues	1

Table 3. 1: Basic School Classroom Projections, 2022– 2025	1

Table 3. 2 Projections for Potable Water Facilities– 2022– 2025	1

Table 3. 3: Health Facilities Projections – 2022 – 2025	1

Table 3. 4: Yearly projected total population of the District: 2022–2025	1

Table 3. 5: Age Distribution and Projected Population in the District, 2022-2025	1

Table 3. 6: Population Projection of 20 Largest Communities in the District	1

Table 3. 7: Adopted Thematic Goals, Focus Areas, Issues, Policy Objectives and Strategies from NMTDPF 2022-2025	1

Table 4. 1: Composite Programme of Action	1

Table 4. 2: Programme Financing	1

Table 4. 3: Maintenance Plan for Projects and Programmes (2022-2025)	1

Table 5. 1: 2022 Annual Action Plan	1

Table 5. 2: 2023 Annual Action Plan	Error! Bookmark not defined.

Table 5. 3: 2024 Annual Action Plan	1

Table 5. 4: 2025 Annual Action Plan	1

Table 6. 1: monitoring and evaluation indicator	1

Table 6. 2: Stakeholder Analysis for the Conduct of Monitoring and Evaluation	1

Table 6. 3: Monitoring and Evaluation Work Plan	1

Table 6. 4 Participatory Monitoring and Evaluation Template	1

Table 7. 1: Matrix Showing Target Stakeholders and Purpose of Communication	1

Table 7. 2: Communication Strategies	1

LIST OF FIGURES

Figure 1. 1: Ellembelle District assembly in National Context	1

Figure 1. 2: Showing the Religious Composition of the District	1

Figure 1. 3: Tourism Map of Ellembelle District	1

LIST OF ABBREVIATIONS AND ACRONYMS

ADB		-	African Development Bank

ANC		-	Ante Natal Care

BECE		-	Basic Education Certificate Exams

BNI		-	Bureau of National Investigation

CEPS		-	Customs Exercise and Preventive Service

CHPS		-	Community-based Health Planning and Services

CIDA		-	Canadian International Development Agency

CBO		-	Community Based Organisation

CSLP		-	Coastal Sustainable Landscapes Project

CWSA		-	Community Water and Sanitation Agency

DACF		-	District Assembly Common Fund

DDF		-	District Development Fund

DMTDP	-	District Medium Term Development Plan

DWST		-	District Water and Sanitation Team

DHD		-	District Health Directorate

CBRDP	-	Community Based Rural Development Project

GES		-	Ghana Education Service

GETFUND	-	Ghana Education Trust Fund

FCUBE	-	Free Compulsory Universal Basic Education

FoN		-	Friends of the Nation

GoG		-	Government of Ghana

GPRS		-	Ghana Poverty Reduction Strategy

GWCL		-	Ghana Water Company Limited

HASCO	-	Half-Assini Senior High School

HIPC		-	Highly Indebted Poor Countries

ICFG		-	Integrated Coastal and Fisheries Governance Initiative

ICM		-	Integrated Coastal Management

IDA		-	International Development Agency

IFAD		-	International Fund for Agricultural Development

IGF		-	Internally Generated Funds

ISD		-	Information Service Department

KG		-	Kindergarten

MSHAP	-	Multi-Sectorial HIV/AIDS Programme

NDPC		-	National Development Planning Commission

NEPAD	-	New Economic Pact for African Development

NGO		-	Non-Governmental Organization

PSP		-	Private Sector Participation

PPAG		-	Planned Parenthood Association of Ghana

POCC		-	Potentials Opportunities Challenges and Constraints

SHEP		-	Self Help Electrification Programme

SIF		-	Social Investment Fund

S&T		-	Science and Technology

SMC		-	School Management Committee

SSNIT		-	Social Security and National Insurance Trust

USAID	-	United States Agency for International Development

VIP		-	Village Infrastructure Project

VRA		-	Volta River Authority

VSLA		-	Village Savings and Loans Associations

# ACKNOWLEDGEMENT

Firstly, we thank the Almighty God for seeing us through the preparation of the whole plan.  The second thanks go to the Chief Executive of the Ellembelle District Assembly, Hon, Kwasi Bonzoh and the District Coordinating Director, Emil Atsu Tawiah for their massive support throughout the entire preparation of the plan.

Again, another thank you to all Honorable Assembly Members, Zonal Council Members, Unit Committees, the Traditional Authorities, Civil Society representatives and all the agencies and corporate institutions as well as all other stakeholders who gave us the needed data to execute this assignment

Lastly, a very big thank you to the entire plan preparation team (District Planning Coordinating Unit) for their selfless dedication/commitment throughout the entire plan preparation period.

The planning team comprises of;

| S/N | NAME | DESIGNATION |
| --- | --- | --- |
|  | HON. KWASI BONZOH | DISTRICT CHIEF EXECUTIVE |
|  | MR. EMIL TAWIAH ATSU | DCD (CHAIRMAN) |
|  | MR. MICHAEL APPIAH-ACHEAMPONG | DPO (SECRETARY) |
|  | MR. BRIGHT OHENE APPIAH | DISTRICT BUDGET ANALYST |
|  | MR. EMMANUEL AMFO | DISTRICT FINANCE OFFICER |
|  | DR. AUGUSTINE KWASI AMOAKO | DISTRICT DIRECTOR OF HEALTH |
|  | MR P. ACKAH BLAY QUAYSON | EDUCATION DIRECTOR |
|  | MR. BENARD DONKOR | AGRIC DIRECTOR |
|  | MR. WISDOM BAKUYEYA | SOCIAL WELFARE AND COM DEVT OFFICER |
|  | NANA NYANZU AMIHERE IV | CHIEF OF AKOTO (T. A REP) |
|  | MR. EDWARD ARTHUR | BAC HEAD |
|  | MR. EDEM RAPHAEL | PHYSICAL PLANNING OFFICER |
|  | MR. ALHASSAN SAAKA | DISTRICT WORKS ENGINEER |
|  | MR. BRIGHT ERZAH SANZAH | DISTRICT DIRECTOR, NADMO |
|  | MR. DOUGLAS ASUAKO-FERKAH ARHINKORAL | DISTRICT DIRECTOR, EPA |
|  | HON. ASMAH JOHN | CHAIRMAN, DEVT PLAN. SUB COM |
|  | JOSEPHINE ACKAH | UCSOND (CIVIL SOCIETY REP.) |
|  | MR. ALEX K. DAMPTEY | DISTRICT ENVIRONMENTAL HEALTH OFFICER |
|  | COMFORT QUARMINE | DISTRICT COMMANDER, GNFS |
|  | EMMANUEL ACKAH | DISTRICT MANAGER, ECG |
|  | MR. FRANCIS OBENG BOAMPONG | DISTRICT DIRECTOR, NCCE |
|  | SUPT. THOMAS BAYOR | DISTRICT COMMANDER, GHANA POLICE SERVICE |

# EXECUTIVE SUMMARY

- Introduction

District assemblies are mandated to exercise deliberative, legislative and executive functions, as stated in the Section 12 sub-section 2 and 3 of the Local Governance Act 2016, Act 936 and 940 as amended (Republic of Ghana, 2016). In addition, the act also states that, a District Assembly shall formulate and Execute plans, programmes and strategies for the effective mobilization of resources necessary for the overall development of the District, as well as being responsible for the overall development of the area within their jurisdiction. These Development Plans are to be prepared and submitted to the National Development Planning Commission (NDPC) through the Regional Coordinating Councils (RCCs) for approval after the General Assembly has adopted it. The District Medium Term Development Plan (DMTDP) under the National Medium Term Development Policy Framework (NMTDPF) 2022 – 2025 has the following 6 main Goals which spans throughout the 4-Year Medium-Term Development Plan (MTDP):

- Build a Prosperous Society

- Create Opportunities for All

- Safeguard the Natural Environment and Ensure A Resilient Built Environment

- Maintain a Stable, United and Safe Society

- Mainstream emergency planning and preparedness into Ghana’s development planning agenda at all levels to respond to potential internal and external threats (including COVID-19)

- Improve delivery of development outcomes at all levels

1.1 Vision, Mission, Core Values and Functions of Ellembelle District Assembly

### Vision

An attractive investment destination with highly skilled manpower where the natural resources are harnessed on sustainable basis to the benefit of the district and the nation at large.

### Mission

The Ellembelle District Assembly exists to formulate and execute plans, programmes and strategies for the effective mobilization of resources necessary for the overall development of the district

### Core Values

In order to achieve the goals and objectives of the Ellembelle District Assembly, the six service delivery standards of the Local Government Service have been adopted as the core values of the Assembly to serve as guiding principles in the performance of its functions. These service delivery standards are;

- Participation: the involvement of relevant stakeholders including Civil Society Groups, Media, NGOs, Private Sector and Community Members in the planning, implementation, monitoring and evaluation of service delivery at the District Assembly.

- Professionalism: the demonstration of requisite skills and competencies, and the ability to adopt best practices in the delivery of services to the satisfaction of the client whilst adhering to ethical standards.

- Client focus: using client requirements to prioritize and consistently develop affordable and accessible Services in a timely manner.

- Transparency: providing all stakeholders with the understanding of how the District Assembly operates, and furnishing them with easy access to adequate and timely information regarding decisions and actions taken by the Assembly.

- Efficient and Effective use of Resources: the optimal use of resources (including time, human resources, natural resources, financial resources, etc.) to provide services and products that satisfy the requirements of users in a timely manner.

- Accountability: taking responsibility for one’s actions and/or in-actions in rendering services and informing citizens on the use of public resources.

### Functions

In accordance with the Local Governance Act, 2016 (Act 936), the functions of the Ellembelle District Assembly include:

  - Exercise political and administrative authority in the district

  - Promote local economic development

  - Provide guidance, give direction to and supervise other administrative authorities in the district as may be prescribed by law.

  - Formulate and execute plans, programmes and strategies for the effective mobilization of the resources necessary for the overall development of the district;

  - Promote and support productive activity and social development in the district and remove any obstacles to initiative and development;

  - sponsor the education of students from the district to fill particular manpower needs of the district especially in the social sectors of education and health, making sure that the sponsorship is fairly and equitably balanced between male and female students;

  - Initiate programmes for the development of basic infrastructure and provide municipal works and services in the district;

  - Be responsible for the development, improvement and management of human settlements and the environment in the district;

  - In co-operation with the appropriate national and local security agencies, be responsible for the maintenance of security and public safety in the district;

  - Ensure ready access to courts in the district for the promotion of justice;

  - Act to preserve and promote the cultural heritage within the district;

  - Initiate, sponsor or carry out studies that may be necessary for the discharge of any of the duties conferred by the Act or any other enactment; and

  - Perform any other functions that may be provided under another enactment.

  - Objective

The main objective of the plan is to put in place a road map, which in the medium term would guide the district to pursue a course of sustainable development by reducing the generally high level of poverty and improve the living conditions of the people in the district with considerable emphasis on growing the informal sector for accelerated local economic development.

The National Development Planning Regulation, 2016 (LI 2232) District Assemblies to initiate and prepare district development plans and settlement structure plans in a manner prescribed by the commission and ensure that the plans are prepared with full participation of the local economy.

In fulfilling the above functions, a Preparation Team was formed out of the DPCU and tasked to prepare the plan.

  - Methodology

In preparing this Plan the following methods were employed in gathering the required data and information.

- Performance Review of the existing 2018-2021 MTDP

- Preliminary studies and investigation into developing emerging issues

- Area Council meetings were held with key stakeholders, Traditional Authorities and community members

- Socio-economic data which constitutes primary data and secondary data

- Final Public Hearing was organized with Area Council members, Traditional Authority, Civil Society and other key stakeholders on the draft plan

- General Assembly meeting was held for the adoption of the 2022-2025 DMTDP

  - Organization of the Plan.

The plan is organized into seven Chapters.

Chapter One examines the performance of the DA in the implementation of the DMTDP 2018 – 2021.  The reasons for non-achievement of the planned development objectives, problems encountered and lessons learnt were documented to inform the new plan.  The district profile is outlined.  This chapter ends with a summary of key development issues/gaps identified from the performance review and profile.

In chapter two, the district development issues are harmonized with the community needs and aspiration gathered from the community needs assessments. The key development issues under the Agenda for Jobs (2018 – 2021) with implications for 2022-2025 were identified and harmonized with the NMTDPF 2022-2025. The key issues from the NMTDPF 2022-2025 were then adopted and prioritized based on their multiplier, widespread and linkage effects.

Chapter Three outlines the district development focus and goal for the medium term. Projections for development requirements within the medium term have also been made in this chapter. The chapter ends with adopted development issues, thematic goals, objectives and strategies from the NMTDPF 2022-2025

Chapter Four contains the Composite Programme of Action of the DA for the 2022-2025. It is undoubtedly linked to the programme-based budgeting. The Chapter ends with the Indicative Financial strategies of the District Assembly to mobilize resources to finance the MTDP in conjunction with Development partners, NGO’s, Civil Society Organisations, etc.

The implementation arrangements for the plan are outlined in this chapter.  Key stakeholders who would be involved in the plan implementation have been identified.  The plan has been phased into annual action plans commencing 2022.  In each annual action plan, the location of the project, time, cost of project, lead and collaborating agencies and source of funding are outlined for monitoring and evaluation.

Chapter six outlines how the programmes, projects or activities outlined for implementation during the planned period will be monitored and evaluated as prescribed by the NDPC guidelines for M&E. The purpose of the M&E Plan has clearly been stated in this chapter. The monitoring as well as evaluation matrices are prepared and strategy for data collection and use outlined.

The chapter also contains the dissemination and communication strategy of the plan and approaches or channels to be used to achieve these objectives.

Chapter seven deals with the communication strategy to be used in informing stakeholders about the plan.

### Conclusion

Harmonized key development issues in the district have been identified.  Again, development priorities to address the key development issues have been outlined.  It is therefore anticipated that the DA as the lead facilitator of the development process would enjoy the collaboration and support of all key stakeholders to effectively implement the plan to achieve the stated objectives for the period 2022 – 2025

# CHAPTER ONE

# PERFORMANCE REVIEW AND PROFILE/CURRENT SITUATION/BASELINE

## Introduction

The Ellembelle District Assembly was carved out of the then Nzema East District, now Nzema East Municipal in December 2007 by Legislative Instrument (LI) 1918 and officially inaugurated in February, 2008. The Ellembelle District is richly endowed with human and natural resources stretching from great pool of mineral deposits (gold, kaolin, silica, Oil & Gas), labour, rich soil, rivers and streams, good climate, tropical rainforest with variety of timber species, cash crops to livestock and all that is desirable or necessary for generating a high quality of life.

POPULATION DISTRIBUTION  MAP

However, the Ellembelle District is deprived as compared to other developing and developed areas in the country.  According to the 2010 Population & Housing Census, about 79.4% of its population lives in rural and 20.6% in urban areas thus making the district very rural in terms of economy and demography.

Most of the communities in the district lack basic services like potable water, health facilities, decent housing, clean environment and quality education facilities.  The district has very poor road conditions especially the northern part and this situation impacts negatively on its marketing and service delivery. However, the people enjoy television signals from satellite disks (such as MultiTV, DStv and Strong) network and Telephone facilities through private mobile phone operators (MTN, Airtel Tigo and Vodafone. Nevertheless, the Ellembelle District Assembly in partnership with its development partners is determined to put in place a formidable accelerated development programmes facilitated by a development plan.

## Performance Review of District Medium Term Development Plan 2018-2021

The Ellembelle District Assembly has implemented considerable number of planned programmes and projects proposed in the DMTDP (2018-2021). The DMTDP (2018-2021) was prepared in line with Medium-Term National Development Framework Policy, An Agenda for Jobs: Creating Prosperity and Equal Opportunities for all (2018-2021) under 4 of the 5 thematic goals. These include;

- Build a Prosperous Society

- Create Opportunities for All

- Safeguard the natural environment and ensure a resilient built environment

- Maintain a stable, united and safe society

In accordance with the thematic goals above, the Assembly formulated and outlined development programmes, projects and activities to achieve the intended targets of the MTNDPF (2018-2021).

However, certain factors impeded the successful implementation of some of the programmes, projects and activities outlined in the DMTDP (2018-2021). Paramount among these factors include; low internally generated funds, irregular/delay flow of statutory funds, weak sub-structures, projects not completed on time among others

In spite of these challenges, remarkable progress has been made with regard to the implementation of projects and programmes geared towards meeting the socio – economic needs of the people

| S.N | DEVELOPMENT DIMENSION | OUTCOME INDICATOR | BASELINE (2017) | 2018-2021 MTDP TARGET | DEV'T OUTCOMES |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | YEAR | DATA |
|  | ECONOMIC DEVELOPMENT | Increase IGF performance of the Assembly | 968,290.70 | 100% | 2020 | 270% |
|  |  | Percentage of arable land under cultivation | 55% | 100% | 2021 | 72% |
|  |  | Total output in agricultural production crops (mt) | 85,433.48 | 160,000.00 | 2021 | 181,148.31 |
|  |  | Number of new industries established | 20 | 120 | 2021 | 91 |
|  |  | Number of new jobs created | 150 | 1,500 | 2021 | 560 |
|  |  | Transformation of Subsistence Farming into Commercial farming | 2000 | 70% | 2020 | 80% |
|  |  | Increase yield of selected crops and livestock | 85,561.43 | 100% | 2020 | 14.25% |
|  |  | Increase in number of tourist arrivals | 593 | 100% | 2020 | 21% |
|  | SOCIAL DEVELOPMENT | Increase in B.E.C.E performance |  | 100% | 2020 | 68% |
|  |  | Increase in W.A.S.S.C.E |  | 100% | 2020 | 73% |
|  |  | Enhance teacher pupil ratio |  | 01:35 | 2020 | 1:56 |
|  |  | Reduction in maternal mortality | 6 | 0/100,000 live birth | 2020 | 60.6/100,000 |
|  |  | Number of operational health facilities | 41 | 50 | 2021 | 43 |
|  |  | Proportion of population with valid NHIS card | 21,869 | 50,000 | 2021 | 53,352 |
|  |  | Number of births and deaths registered | 4,563 | 5,000 | 2021 | 2,993 |
|  |  | Reduction in malaria case fatality | 1.7 | 0 | 2020 | 0 |
|  |  | Increase in number of family planning accepters | 984 | 1,200 | 2020 | 1,042 |
|  |  | Percentage of population with sustainable access to safe drinking water | 67.50% | 90% | 2020 | 73.93% |
|  |  | Percentage of population with access to improved sanitation service | 60% | 90% | 2020 | 74.56% |
|  |  | Reduction in reported cases of child non-maintenance | 43 | 50% | 2020 | 11% |
|  |  | Number of recorded cases of child trafficking and abuse | NRD | 0 | 2021 | 16 |
|  |  | Net Enrolment ratio | 80.67% | 100% | 2020 | 76% |
|  |  | Gender Parity Index | 1 | 1 | 2020 | 1 |
|  |  | Completion Ratio |  | 100% | 2020 | 97% |

Table 1. 1: Performance Review of MTDP 2018-2021

| S.N | DEVELOPMENT DIMENSION | OUTCOME INDICATOR | BASELINE (2017) | 2018-2021 MTDP TARGET | DEV'T OUTCOMES |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | YEAR | DATA |
|  | ENVIRONMENT, INFRASTRUCTURE & HUMAN SETTLEMENT | Percentage of Road Network in good condition | 57.40% | 80% | 2020 | 66.54% |
|  |  | percentage decrease in disaster incidents | 13 | 50% | 2020 | 61.5% |
|  |  | Percentage increase in building permit application | 72% | 100% | 2020 | 118% |
|  |  | Percentage of communities covered by electricity | 72% | 90% | 2020 | 76% |
|  | GOVERNANCE, CORRUPTION AND PUBLIC ACCOUNTABILITY | Percentage of Annual Action Plan implemented | 54% | 100% | 2020 | 95.87% |
|  |  | District Assembly performance in DPAT & other assessment |  | 100% | 2020 | 99% |
|  |  | Proportion of Assembly Members who are women | 14% | 30% | 2020 | 7.60% |
|  |  | Percentage decrease in reported cases of crime | 1,036 | 50% | 2020 | 22% |

Source: DPCU, 2021

### Analysis of Performance Review

Despite the daunting challenges faced by the Ellembelle District Assembly in the implementation of its planned programmes and projects which was further worsened by the impact of the novel corona virus, the Assembly was able to achieve some successes as depicted in the table 1.

For instance, the Assembly was able to exceed its revenue target by over 200%. This was mainly as a result of revaluation activities carried out on landed properties of some major companies in the district which led to the levying and collection of property rates. The Assembly did not perform as much in the area of gender equality where the proportion of Women Assembly Members dropped from 14% in the previous Assembly to 7% in the new Assembly.

Over all, the Assembly has made some progress in alleviating poverty and promoting inclusive development. A lot of progress has also been made in the area of infrastructure as major roads within the district have been awarded on contract and are at various stages of completion. The Assembly will continue to pursue projects and programmes to consolidate the gains made under the previous plan and bring accelerated development to the people of Ellembelle.

### Key Challenges Encountered in Implementing the DMTDP 2018-2021

The Ellembelle District set to implement many projects at the southern part of the district instead of the Northern area of Aiyinase Area Council which is cut off from the district due to its difficult terrain (road accessibility). Co-incidentally, this Northern part is also the food basket of the district where large plantations can be found. In light of this, the Assembly pursued and lobbied hardly to get the major road linking these communities awarded on contract. The contractors are currently on site and expected to complete the works within this plan period. This will not only make it possible for the Assembly to take development projects to this part of the district but will also open up this part of the district for vibrant economic activities to thrive.

The district abounds in many resources which could have been harnessed for the benefit of the citizens. Kaolin is mined and taken out of the district, large quantities of cocoa is produced in Aiyinase North area and its environs, cassava is also produced in large quantities. All these produces including many others can be processed within the district to generate the needed employment as well as revenue. The One-District-One factory policy is therefore a wake-up call for all investors to come and invest in the district.

The district did not put in place any programme to deal with the challenges associated with the Oil and Gas sector. With the oil discovery, influx of people into the district has increased tremendously thereby raising the cost of living ranging from food stuffs to accommodations (rents).

Lastly, poor coordination among development actors thus increasing waste of limited resources was also a challenge. Implementing projects without due consultation with the Assembly by development partners was also identified.

### Lessons Learnt Which Have Implications for DMTDP (2022-2025)

The Assembly must liaise with development partners to ensure the early completion of roads under construction to link the Northern part of the district to the south. Administratively, the Aiyinase North can be made an Area Council to speed up pace of development.

Secondly, priority should be given to the Northern part of the district in the provision of social amenities. Non-Governmental Organizations as well as Financial Institutions should be encouraged to establish and operate in this part of the district.

A good and reliable data base for revenue generation is the key to further increasing our internally generated fund. In light of the above, the street naming and property addressing programme will be fully implemented especially in the major towns in order for the Assembly to derive the full benefits of the programme including increased revenue generation.

The Assembly would re-strategize and support local businesses and farmers as well as fisher folks in the district to expand their productive capacities and give them the impetus to benefit fully from the thriving extractive industry in the district and promote inclusive growth.

Aside the Assembly concentrating on few projects for full implementation, we must also conscientize all stakeholders and development partners on the need to implement a common development plan which captures needs of communities so that progress on planned activities can be tracked to avoid duplication of projects.

### Way Forward for DMTDP 2022-2025

The Assembly will be well positioned to put in place adequate measures to improve the revenue base, engage the communities more on issues, liaise with companies on their corporate social responsibilities as well as monitor and evaluate planned activities.

### Review of Assembly Finance

This section analyzes the revenue and expenditure pattern of the Assembly from 2018 – 2020.  An examination of the sources of revenue indicates two main sources.

- Internal Sources (own sources)

- External Source

Table 1. 2: Revenue Performance from 2018-2020

| REVENUE SOURCE | Baseline (2017) | 2018 | 2019 | 2020 |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | Target | Actual |
| IGF | 968,290.70 | 1,813,279.68 | 3,286,541.36 | 3,800,000.00 | 3,663,513.87 |
| DACF | 1,303,172.05 | 1,373,588.81 | 1,973,890.68 | 3,714,374.00 | 2,218,735.16 |
| MP’s COMMON FUND | 222,438.77 | 292,132.16 | 339,407.68 | 600,000.00 | 361,412.27 |
| Central Government – GoG | 962,071.04 | 1,281,923.64 | 1,638,731.59 | 2,009,985.00 | 2,072,471.45 |
| Hon. MP SIP | 40,000.00 | 20,000.00 | - | 0 | 0 |
| GSFP | - | - | - | 0 | 0 |
| Goods and Services Transfers | 5,008.01 | 60,027.62 | 17,890.68 | 67,917.00 | 72,586.99 |
| DDF | - | 506,072.00 | 834,831.30 | 1,309,929.00 | 134,903.08 |
| GSOP | - | - | - | 0 | 0 |
| CIDA (Agric Support) | 37,500.00 | 106,339.12 | 111,350.30 | 0 | 0 |
| Assets Transfers | - | - | - | 0 | 0 |
| MINERAL ROYALTIES | 205,378.00 | 700,522.00 | 703,198.00 | 1,000,000.00 | 490,203.00 |
| STOOL LANDS REVENUE | 842,329.00 | 247,249.00 | 376,247.00 | 800,000.00 | 657,125.00 |
| OTHERS (DONOR SUPPORT) | 65,120.38 | - | - | 134,993.00 | 474,744.01 |
| TOTAL | 4,651,307.95 | 6,401,134.03 | 9,282,088.59 | 13,437,198.00 | 10,145,694.83 |

Source: Annual Accounts 2018 - 2020

Table 1. 3: Financial Performance (2018-2021)

| SOURCE OF FUNDS | TOTAL ESTIMATED COST OF PLAN | TOTAL AMOUNT RECEIVED | VARIANCE |
| --- | --- | --- | --- |
| GOG | 12,124,588.14 | 9,551,044.67 | 2,573,543.47 |
| IGF | 15,481,699.80 | 12,249,391.75 | 3,232,308.05 |
| DACF | 16,424,640.00 | 7,432,183.07 | 8,992,456.93 |
| DACF-RFG | 3,480,212.00 | 2,588,089.38 | 892,122.62 |
| DPs | 203,219.00 | 217,689.42 | -14,470.42 |
| ABFA | 0 | 0 | 0.00 |
| Others | 8,470,521.00 | 4,467,166.49 | 4,003,354.51 |
| TOTAL | 56,184,879.94 | 36,505,564.78 | 19,679,315.16 |

Source: District Finance Officer, 2021

## Analysis of Existing Situation/Compilation of the District Profile

### Location and Size

The Ellembelle District is located at the southern part of the Western Region of Ghana between longitudes 2o 05’’ W and 2o 35’’ W and latitude 4o 40’’N and 5o 20’’N covering a total land size of 995.8 Square Kilometres (GSS, 2010 PHC). It is a coastal district sharing boundaries with Jomoro District to the West, Wassa Amenfi West and Amenfi Central Districts to the North, Nzema East Municipal to the East and a 70 km stretch of sandy beaches along the Atlantic Ocean to the south. The district capital is Nkroful which is the birth place of the first President of the Republic of Ghana, Osagyefo Dr. Kwame Nkrumah. The location of the district within the Oil and Gas enclave of Ghana strategically positions it for businesses and other economic activities ranging from farming, services, trading, fishing, mining, oil and gas, tourism to thrive.

The location of the district in Regional and National context is represented in figure 1.1 below.

Figure 1. 1: Ellembelle District assembly in National Context

ELLEMBELLE IN REGIONAL CONTEXT

ELLEMBELLE DISTRICT MAP

## 1.3.1 Physical and Natural Environment

The physical and natural environments are essential elements of the factors for determining socio – economic development of the district. This stems from the fact that, apart from being potential resources, they also serve as ingredients within which all development activities take place. The factors that need critical analysis and their implication for development in the district under physical and natural environment include location and size, climate, vegetation, relief and drainage, soil and geology and minerals.

### Soil, Vegetation and Agriculture

The soil in the District is mainly of the ferric acrisols and dysric fluvisols type. The ferric acrisols type of soil constitute about 98% of the entire land of the district, as such supports the cultivation of a wide range or variety of crops including cocoa, coffee, coconuts, oil palm, plantain, rubber and cassava. Due to this characteristic, the district has a comparative advantage in agriculture especially in the area of agro -processing and plantations.

The vegetation of the District as shown in figure 4 is made up of the moist semi-deciduous rain forest in the northern part of the district, but turns into secondary forest southwards mainly due to human activities like tree felling and farming. The Coastline, which is about 70km long, is mainly of savanna vegetation (ghanadistricts.com, 2013). The District has several timber species and other non-timber forest products like rattan, bamboo, among others. It also abounds in game and wildlife all of which offer opportunities for resources extraction, tourism and enterprise development.

There are also three forest reserves in the District. These are Shelter Forest Reserve, Draw River Forest Reserve (the largest and located at the Northern half of the District) and the Ndumfri Forest Reserve located in the North Eastern end of the District. The Community Resource Management Area (CREMA) concept, by Wild Life Division of the Forestry Commission is an initiative which is helping to curtail the unsustainable usage of natural resources.

The district has a rich diversity of fauna and flora, which has the potential of turning the district into a major tourist destination in the country in particular and the globe in general, if the needed tourist infrastructure such as good roads, hotels, restaurants and communication facilities are made available. There is therefore a great potential to generate huge revenue from tourism in the district using the forest resources and for this reason; the District Assembly should be supported and encouraged to develop the tourism industry into an investment attraction as an appropriate alternative revenue earner.

### Climate and Disaster

The District lies within the wet semi-equatorial climatic zone of the West African Sub-region.  The area experiences an all – year round rainfall with the highest or maximum monthly mean of rainfall occurring around May and June. Mean Annual rainfall figures ranges from 26.8mm to 46.6mm. The average temperature in the District is about 29.400C with variation in mean monthly ranging between 400C to 500C throughout the year.

The District records high relative humidity figures ranging from 27.6% to 26.6% between May and June and 27.3% to 27.9 during the rest of the year.

The climate of the District is suitable for the cultivation of various crops both food and cash.  The heavy and prolonged rains associated with this type of climate adversely affect cocoa harvest especially drying of the beans and aggravate the black pod diseases that attack cocoa. In addition, all the un-tarred roads become almost immotorable during the rainy season. The effects of this on the economy of the district are obvious.

Issues related to climate change and global warming start to occupying large spaces on our table, it is high time that we also made preparations to address them in a holistic manner. A lot of people especially from the localities are not ready to equip themselves with information on climate change either because they still believe it is too scientific or because it can easily divert their livelihoods. While it is important to remain focused on issues of interest, it is also necessary to keep our eyes and ears open to the world.

Climate change is a critical issue (as we have all been feeling about it in our homes) and all organizations and individuals should start considering it as an issue of highest relevant and work in its direction either in a full-fledged manner or as a cross-cutting theme.

Specifically, the Ellembelle District is affected with serious sea erosion along the beach, stretching from Ankobra community to Atuabo community, flooding in Ankobra community, depletion of the mangroves on the wetlands, endangering species in the sea especially where the Ankobra River enters the sea as a result of the illegal mining (Galamsey) activities in the river, sea weeds, coconut trees are heavily affected due to climate change and activities of the mining companies in the Nkroful Area Council.

According to the United Nations International Strategy for Disaster Reduction (UNISDR), climate change is increasing the risk of natural disasters, with more extreme weather events, the wet season becoming wetter and the dry season drier. Bush fires and floods have become a common occurrence in the country. This has negative effects on lives, the economy and the environment. The frequency and scale of natural disasters is increasing the need for disaster resilience, particularly prevention and preparedness measures. The National Disaster Management Organization (NADMO) is the body incharge of managing the Disasters issues of the District. It is worth noting that, NADMO carries out its disaster management in collaboration with Fire service, Environmental Health Department, Works, the police, the Physical Planning Department and others.

The rich natural resources of the District are being degraded as a result of mining, farming, lumbering and logging as well as building activities. The climate change stressors that the district is experiencing as a result of these activities include seasonal variability of rainfall, wind storms, and river and sea flooding. These could be attributed to the activities of timber firms with concessions in the Forest Reserves, bad agricultural practices, unplanned settlements, indiscriminate disposal of waste and illegal mining which pollutes the water bodies especially the Ankobra River have led to changes in the rainfall pattern. Traditional methods of farming which involves slash and burn have led to the depletion of the vegetation cover and increased soil erosion and loss of valuable nutrients.

High amount of rainfall as well as its intensity have affected communities that are found in low lying areas as they are mostly flooded by the Ankobra and Amanzule Rivers which overflow their banks during the raining season. The number of floods recorded in the district increase from 13 to 38 between 2012 and 2017. Windstorms recorded from to 2012 to 2017 also increased from 19 to 32.

The district to be able to address climate change issues would dialogue with relevant stakeholders especially from the affected communities accompanied with public sensitization and a Local Bye-law on climate change. Economic and social activities should be climate SMART related e.g. construction, farming, fishing, mining, etc.

Integration of critical issues of climate change into the Assembly’s Development Plans, Policies and Budgets is very essential and to adopt the appropriate measures.

### 1.3.4 Relief and Drainage

The District is endowed with a number of rivers and streams, the most important of which is the Ankobra River with its major tributaries like the Ahama and Nwini rivers.  Others like the Ankansa and Draw rivers and their tributaries drain the Northern part and act as boundaries between Ellembelle and Wassa Amenfi West District. The Amanzule River in the south – western part and some other minor rivers and streams also flow throughout the year in the district. These streams and rivers exhibit a dendritic pattern that forms the Ankobra basin.

The relief and drainage system favour the development of fish farming and cultivation of valley bottom rice, sugarcane and dry season vegetables. The presence of larger Rivers like the Ankobra has induced commercial fish farming in communities along the Ankobra basin.

### Spatial Analysis / Settlement

Various settlements have spread through the entire district. Larger portion of the population is concentrated in the forest zone of the District. Considerable part of the District which is mostly occupied by cocoa farmers (Northern Aiyinasi) is not accessible. These developments normally compel farmers to sell their produce to other neighboring districts to the detriment of the District’s Internally Generated Fund (IGF). The District is sparsely populated. However, the population is not evenly distributed; only a few settlements such as Aiyinasi, Esiama, Asasetre, Asanta etc. have the bulk of the population. Teleku-Bokazo and Nkroful are gradually becoming overpopulated due to the emergence of mining activities. This is as a result of concentration of certain amenities like electricity

In Ellembelle District, there are specific settlements of which are classified as Urban namely Aiyinasi, Asasetre and Esiama. This is based on settlement with the population of 5,000 people as minimum. Esiama and Aiyinasi especially have the potential to grow into bigger towns due the emergence of new economic and commercial activities. The location of these communities along the Takoradi-Cote D’Ivoire makes them good prospects for increased economic activities.

### Culture

#### Religious Composition

There is religious heterogeneity in the district. People are allowed to practice their faith without hindrance. Data from the 2010 PHC shows that Christians (81%) dominates in the district, 9% of the population belong to the Islamic religion, 8% are without any form of religion, Traditionalist (1%) whiles 1% are also with religious groups not specified as shown in the figure below:

Figure 1. 2: Showing the Religious Composition of the District

Source: 2010 PHC

#### Festivals

One significant feature in the District is the traditional festival of Kundum which is celebrated in all the communities of the District between August and October each year. It is important to note that during the celebration of the festival, a large number of people from far and near troop into town. During the season, general economic activities (especially buying and selling) are boosted. However, the economic boom comes with its own social and environmental impacts on the district.

The major language spoken all over the District is Nzema with other dialects like Evalue and Gwira, Fanti and Twi also widely spoken.

### Governance

The Ellembelle District Assembly is the highest political and administrative authority in the district and the District Chief Executive (DCE) is the head of the District Administration. The DCE also chairs the Executive Committee of the Assembly. There are 54 Assembly Members comprising 36 elected members and 16 government appointees, the DCE and a Member of Parliament who constitute the General Assembly - the highest decision-making body of The District Assembly. The Presiding Member (PM) chairs the Assembly’s meetings. The district has one constituency called the ‘Ellembelle Constituency’ with a total of seven Area Councils and 36 Electoral Areas. The Assembly has seven sub-committees namely;

- Finance and Administration sub-committee;

- Development Planning sub-committee;

- Social Services sub-committee;

- Agriculture sub-committee;

- Works sub-committee;

- Justice and Security sub-committee; and

- Mines and Environment sub-committee

The District Co-ordinating Director (DCD) performs the administrative role of coordinating the activities of all the eleven (11) decentralized departments (created by LI 1961) in the district.

### Security

It is obvious that with the emergence of oil and gas activities and gold mining in the district, the tendency for increased criminal activities cannot be overemphasized.  Social vices such as theft, teenage pregnancy, drug trade among several others are on the rise.  It is against this backdrop that the district fought for its own police command. The District currently has a police command, headquartered at Esiama. In all there are five (5) Police stations located at Atuabo, Esiama, Nkroful, Aiyinase and Salman. The Assembly has plans of creating an additional Police post at Aiyinase North to bridge the gap between the North and South. These developments would helped curtail or reduced crime and criminal activities which hither to was on the ascendency. Conducive environment has been created for investment as well as protection of lives and property. These notwithstanding, there is still a huge gap in the police citizenship ratio (1:1,774) because the District has only Sixty-Five (65) personnel. The Assembly also has a fire station, but yet to have immigration and other security agencies into the District.

### Health Facilities

As at 2010, the district had two health training institution; the community health training school (CHHTS) located at Esiama and Seventh-Day Adventist Health School (HATS) at Asanda. There is only one hospital in the District; the St. Martin de porres Catholic Hospital at Eikwe, Six (6) health Centres and about Twenty-Seven (27) CHPS. A subsidiary of ENI Ghana, an oil exploration and production company was engaged in the construction of a number of CHIPS compound in the district.  The national health insurance authority has established a scheme at Nkroful for the district in addition to that of the Nzema East Municipality.

Figure 1.3 Shows the Health facilities in the district

### Educational Facilities

According to the 2012 education management information system (EMIS) of the education directorate of the district, there were 74 pre-schools/kindergarten, 78 primary schools, 50 Junior High Schools, four Senior High Schools, one Technical School, one Vocational School and one Special school (i.e. the Trades Schools for the physically challenged) in the district. Most of these educational facilities (especially, the secondary ones) are situated in the northern part of the district.

### Information Communication Technology

Telecommunication in the district is mainly by individual cell phones either networked to MTN, TIGO or in some few areas by Vodafone. The whole of the New Aiyinase sub-district (northern portion of the district) can hardly be reached by phone. There were postal services located at Nkroful, Esiama and Aiyinase. Until recently, ICT facilities were absent in the district. The recent inclusion of ICT in the curricula of the Junior High Schools and Senior High Schools in the country has improved ICT awareness among the population leading to the springing up of few internet cafés and computer schools mainly at Nkroful, Esiama and Aiyinase. Additionally, Esiama and Aiyinase have benefited from the government’s commercial ICT centers. A community Information Center (CIC) has been established at Aiyinase with funds from the UNDP to improve ICT knowledge among student in the district. The district assembly and the Member of Parliament (MP) for the area commissioned another ICT facility at Nkroful on the 14th of October 2013. The only radio station in the district-West End Radio- is located at Esiama.

### Water and Sanitation

Most of the communities in the southern part of the district have good water supply either by borehole or running pipes. However, the other communities (especially those in the northern part) have no access to portable water and rather resort to the use of unprotected wells and streams/rivers. Communities such as Anyinse, Assastre, Kikam, Nkroful, Awiebo-Basake, had small town water supply systems from the community water and sanitation system agency (CWSA). Esiama is yet to benefit from the same small-town water supply systems under the sustainable rural water and sanitation project (SRWSP) as work on the project began in the January 2013. Also, safe water network and Komos energy are constructing a water supply system for Atuabo and the adjoining communities.

### Local Economic Development

The Assembly in its efforts to encourage local initiative through the transfer of skills has trained some community members in Kumgbunli, Eikwe and Nkroful in batik making, beads making and soap making. Other NGOs and Development Partners have engaged and trained some community members in areas such as bee-keeping, aqua-culture, snail rearing, vegetable growing, cassava and others in order to improve their income.

Currently, the district is the leading producer of cassava in the region but due to lack of market for the produce, farmers are not happy growing them. With a good technology, the cassava can be processed into several products which will give more income to the farmers.

Some development potentials like presence of Wetland, Forest Reserves, Rivers, vast bamboo resource and cultural practices like Kundum festival can be developed as tourist destination which would generate income for the local economy.

Also, coconut producers should be trained on the various uses of Coconut husk, doormat, interior designs etc. through the Business Advisory Center (BAC). These initiatives would help generate employment.

### Tourism

The District has a huge potential for Tourism development.  There are numerous potential tourist attractions, which if properly developed and packaged, could attract a lot of tourists to the district.  These include historical sites like the birth place and initial tomb of the first President of the Republic of Ghana, Dr.  Kwame Nkrumah at Nkroful, a 70km stretch of sandy coastline that boarders the district to the south, the navigable Ankobra River that links the northern and southern parts of the district through river transport, tracts of wetlands, the crocodile pond at Baku and the famous Kundum Festival celebrated by all the Chiefs and people of the district between the months of August and October every year is also a potential for tourist attraction.

The Assembly must be supported to identify and facilitate the development of these potentials through Public Private Partnerships (PPP). This would create employment and enhance revenue generation in the District. It will also open up the district to investment in the hospitality industry leading to the creation of various employment opportunities. The recent emergence of the Oil and Gas in the Western coast of Ghana and the Operation of mining companies such as the Adamus Resource Limited has greater potentials for the development of hospitality facilities (hotels) and beach resorts in the coastal belt communities especially in Esiama, Asanda and Bobrama. This will greatly give a boost to economic activities. The strengthening of security is also fundamental since the development of the hospitality industry will come with its ramifications such as crimes in the form of theft and arm robbery.

Figure 1. 3: Tourism Map of Ellembelle District

TOURISM MAP

### Food and Nutrition Security

Food security is the state of having reliable access to a sufficient quantity of affordable, nutritious food that meets dietary needs and food preferences for an active and healthy life. Food nourishes our bodies and influences our health. Poor nutrition also results in undernutrition and over nutrition. There is the need to maintain a healthy population in the district and quality food production is key to improved/good nutrition. The nutrition unit of the Ghana health service in collaboration with the food and Agriculture work together to improve on the health and nutrition of the people of Ellembelle District. The main objectives of the two Departments and the Assembly as a whole are;

- To improve food system (food production, collection, processing, distribution and consumption)

- To improve healthy food environment (factors that influence peoples food choices, food consumption and nutritional health).

In order to achieve the above objectives, sensitization activities are tailored towards the following strategies;

- Encouraging backyard garden.

- Encouraging growing of improved seeds.

- Providing extension support to farmers.

- Promoting healthy diets among School Children.

- Food demonstrations.

- Monitoring the implementation of school feeding programmes in the various beneficiary schools

- Visit LEAP beneficiaries to counsel diet.

The above practices have led to varieties of food stuff found in the various market centres within the district. These include Cereals (rice, maize, millet, sorghum), Legumes (cowpea, soyabean, groundnut), Starchy roots and tubers (cocoyam, yam, cassava, sweet potato), Fruits and Vegetables (orange, pineapple, coconut, water melon, banana, plantain, cabbage, pepper, okro, garden eggs). However, the major crops cultivated are cassava, rice, plantain, cocoyam, maize, oil palm and vegetables. Common fish species in the district are sardinellas (eben), frigate mackerel (apoku) and long finned herring (kanfla).

It can be concluded that, the Ellembelle District has access to sufficient, relatively safe and nutritious food that meets the dietary needs and preferences for a healthy active life.

### Trade and Commerce

The major marketing centers in the district are located at Aiyinasi, Asasetre and Esiama. While Asasetre and Esiama have one market day, Aiyinasi has two market days in a week. Items sold at the markets include a variety of foodstuffs, household items, and clothes, among others.

### Roads and Transport

The district has 154km of trunk roads of which 63.9km representing 41.5 percent is tarred. It must be noted that this forms part of the Trans-African Highway. The rest of the trunk roads are either graveled or earth surfaced. Apart from these trunk roads the district has 253km of feeder roads. Out of this, only about 150km is motorable all year round. It must also be noted that about 70 percent of these feeder roads are located in the southern part of the district.

Lack of maintenance coupled with the heavy rainfall make these roads unmotorable especially during the raining season. The absence of bridges and culverts along some feeder roads also render some of the major food and cocoa producing areas inaccessible. Besides the poor state of the roads, road density is also low.

### Financial Institution

The financial institutions in the district are commercial banks and rural banks including: Cal Bank Ltd at Esiama with an agency at Aiyinasi and ECO Bank Ltd at Esiama, the Nzema Manle Rural Bank (with its headquarters at Awiebo and branches at Asasetre and Aiyinasi); the Lower Pra Rural Bank at Nkroful; and the Ankobra West Rural Bank (with its headquarters at Esiama and a branch at Nkroful).

### Child and Vulnerability Issues

The Department of Social Welfare has undertaken various activities which include Case management, SWIMS, procurement of items and the District Child Protection Team embarking on sensitization in some selected communities with the primary objective of sensitizing traditional authorities, opinion leaders, community members and school children on responsible parenting, drug abuse, child labour, child neglect, safeguarding children from harm both intentional and unintentional, community harmony and cohesion among others.

Goal:

Poverty and vulnerability of children and families is reduced through increased access to an integrated set of social services.

Objectives:

- Strengthen capacity, coordination, and systems for delivery of integrated services with a focus on child protection, social protection and health services.

- To learn and document how social services can best be delivered in a more coordinated manner.

# CHAPTER TWO

# PRIORITIZATION OF DEVELOPMENT ISSUES

## Introduction

On the basis of the summarised key development issues identified from the previous chapter, the DPCU undertook the following activities to determine prioritised development issues for 2022-2025. This chapter highlights the steps that were taken to determine the prioritized development issues of the Ellembelle District Assembly for 2022-2025.

## Harmonization of Community Needs and Aspirations with Identified Key Development Issues

The community needs and aspirations identified through needs assessment have been harmonized with the summarized key development issues from the analysis of the current situation and performance review. Thus, each of the needs and aspirations of the communities have been matched against the summarized key development issues to determine the level of relationship between the two and scored. The criterion for the harmonization is as follows;

Table 2. 1: Scoring Scales

| DEFINITION | SCORE | MEANING |
| --- | --- | --- |
| Strong relationship | 2 | A strong harmony of community needs and aspirations and identified key development problem. |
| Weak relationship | 1 | A weak harmony of community needs and aspirations and identified key development issues. |
| No relationship | 0 | It signals a new or emerging concern which need to be considered. . |

## Impact Analysis

The issues harmonized above were subjected to impact analysis in order to ascertain the most pressing ones which when tackled earlier could help resolve many other issues. This was also to enable the planning team assess the impact of the issues in terms of the following:

- Significant linkage effect on meeting basic human needs/rights

- Significant multiplier effect on economic efficiency

- Impact on:

- The different population groups (e.g. girls, aged, disabled);

- Balanced development;

- Natural resource utilisation;

- Cultural acceptability;

- Resilience and disaster risk reduction;

- Climate change mitigation and adaptation;

- Institutional reforms.

- Opportunities for the promotion of cross-cutting issues such as

- HIV and AIDS in terms of the target groups in the sector for targeted interventions e.g. elimination of stigmatization;

- Gender equality with respect to practical and strategic needs and interests;

- Nutrition.

The impact analysis was very objective and guided by evidence of records. In conducting the impact analysis, members of the DPCU were grouped into four. Each group scored the adopted issues by consensus among the members. A scoring system of 1 – 3 in terms of priority in an ascending order was used. Thus, issues that were considered as having less impact were scored 1 whereas those considered to have a very high impact were scored 3 by the groups.

The scores of the four groups (labelled A, B, C and D) for each adopted issue were summed up to arrive at their total scores. The issues were then ranked based on their total scores. A consensus was reached by the DPCU to adopt issues that were ranked from 1st to 5th as the most prioritized in the district. The prioritized development issues from the impact analysis are listed as follows.

## 2.4 Prioritized Development Issues

Table 2. 2: List of Prioritized Development Issues

| S/N | Community Needs and Aspirations |
| --- | --- |
| 1 | Inadequate market infrastructure |
| 2 | Lack of financial support for traders |
| 3 | Lack of financial support for farmers |
| 4 | Lack of machines for palm oil extraction |
| 5 | Inability of local artisans to secure government contracts |
| 6 | Lack of commercial stores |
| 7 | Lack of aquaculture facilities |
| 8 | Inadequate classroom infrastructure |
| 9 | Inadequate health infrastructure |
| 10 | Poor conditions of classroom blocks |
| 11 | Low coverage of potable water |
| 12 | Inadequate institutional latrines |
| 13 | Lack of teacher accommodation |
| 14 | Inadequate school furniture |
| 15 | Lack of public toilet |
| 16 | Lack of incentives for teachers in rural areas |
| 17 | Lack of tools and equipment for artisans |
| 18 | Inadequate trained teachers |
| 19 | Lack of waste bins |
| 20 | Inadequate alternative livelihood programmes |
| 21 | Lack of scholarship programmes for PWDs |
| 22 | Lack of employable skills among PWDs |
| 23 | Low capacity in proposal writing by youth |
| 24 | Lack of library facilities |
| 25 | Inadequate support from Ghana Gas |
| 26 | High unemployment among the youth |
| 27 | Lack of skills for employment in the oil and gas industry |
| 28 | Poor road infrastructure |
| 29 | Lack of footbridge/ culverts |
| 30 | Poor telecommunications coverage |
| 31 | Lack of planning schemes |
| 32 | Inadequate ICT centres/laboratories |
| 33 | Affordable housing |
| 34 | Inadequate police station/post |
| 35 | Lack of bye-laws on gambling |
| 36 | Low level of revenue generation |
| 37 | Lack of office accommodation for area council |

Source: DPCU, 2021

# CHAPTER THREE

# DEVELOPMENT PROJECTIONS, GOALS, OBJECTIVES AND STRATEGIES

## Introduction

In this chapter, the development focus of the Ellembelle District Assembly has been established and a clear district goal consistent with the MTNDPF 2022-2025 has also been stated. The chapter also includes development projections for 2022-2025. Relevant policy objectives and strategies have also been adopted from the NMTDPF 2022-2025 to achieve the objectives of the district and national goals.

## Desired Future Conditions

The principal goal of the Ellembelle District is obtained and visualized in the vision statement which states “An attractive investment destination with highly skilled manpower where the natural resources are harnessed on sustainable basis to the benefit of the district and the nation at large”. This broad goal of the district is to be achieved through its mission statement which states that “The Ellembelle District Assembly exists to formulate and execute plans, programmes and strategies for the effective mobilization of resources necessary for the overall development of the district”. Following from the above, it is important to define the development projections of the district for the next four years (2022-2025) within the context of its vision and mission statements, while taking cognisance of the broad national goals. The Ellembelle District Assembly has designed multi strategies that would enable the district to achieve its future desire. Notably among the strategies include:

- Revised the existing MTDP (2018-2021) and prepared a new DMTDP (2022-2025)

- Integrated Development Approach (All key areas as provided in the NMTDPF (2022-2025).

- Boosting crops and fish production through innovative method agriculture.

- Formulating industrial plan and policy to attracting investments for industries in the District.

- Promoting tourism and hospitality services.

- Provision of socio-economic infrastructure to support human development.

- Enhance conservation of forest and coastal resources, environmental sensitive areas such as wetlands.

- Develop business data to identify all informal sector business to increase IGF.

- Improving spatial planning.

## Development Projections for 2022– 2025

Based on the population projections in chapter one and the community needs and aspirations, the following development projections are made in respect of education, health, district economy, and water and sanitation infrastructure. The projections were done to ascertain the additional social, economic and infrastructural services that should be provided in the medium term in order to achieve district and national development objectives.

### Education

Table 3. 1: Basic School Classroom Projections, 2022– 2025

| LEVEL | PROJECTED POPULATION OF COHORT (2025) | GES CLASSROOM REQUIREMENT | EXISTING CLASSROOMS 2020 | CLASSROOM BLOCKS REQUIRED | GAP TO BE FILLED |
| --- | --- | --- | --- | --- | --- |
| KG | 4,420 | 1:35 | 88 | 126 | 38 |
| PRIMARY | 11,575 | 1:45 | 217 | 256 | 48 |
| JHS | 5,051 | 1:35 | 99 | 144 | 45 |
| TOTAL CLASSROOMS TO BE PROVIDED BY 2025 |  |  |  |  | 132 |

Source: DPCU, 2021 (Based on Planning Standards from GES)

The district will need additional 132 classroom blocks in order to fill the gap and improve quality of education in the district. The needs at the various levels of education in the district is segregated as follows;

at the KG level, 38 classrooms which translates to 19No. 2-unit classroom blocks;

at the primary level, 48 classrooms which translates to 7No. 6-unit classroom blocks and

at the JHS level, 45 classrooms which translates to 15No. 3-unit classroom blocks are required.

The Assembly will however only be able to fund the construction of 57 classrooms within the plan period based on the resources available to the Assembly. The Assembly will therefore vigorously pursue partnership with development partners to and private sector to fill the gap.

### Water Facilities

Table 3. 2 Projections for Potable Water Facilities– 2022– 2025

| TYPE OF FACILITY | PLANNING STANDARD | TOTAL POPN TO BE SERVED BY 2025 | EXISTING FACILITIES (2021) | NO. OF FACILITIES REQUIRED | NO. OF FACILITIES TO BE PROVIDED BY 2025 |
| --- | --- | --- | --- | --- | --- |
| HDW | 75 – 300 | 2,517 | 27 | 34 | 7 |
| B.H | 300 - 1,999 | 48,264 | 139 | 161 | 22 |
| SCPS | 2,000 – 4,999 | 35,086 | 7 | 18 | 11 |
| STWS | 5,000+ | 27,897 | 6 | 6 | 0 |

KEY: HDW= Hand Dug Well, B.H= Borehole, SCPS= Small Community Piped System, STWS= Small Town Water System Source: DWST, 2021 (Based on Planning Standards from CWSA)

From the table above, in order to achieve 100% coverage within the plan period, the district would have to construct 7No. hand dug wells, 22No. boreholes and 11No. Small Community Piped Systems. At present, the district has an estimated total coverage of 73.93%.

However, there are a number of boreholes that have broken down and need rehabilitation. The district would therefore embark on a project to rehabilitate all broken down bore holes within the planning period.

### Health Facilities

Table 3. 3: Health Facilities Projections – 2022 – 2025

| Projected Population by 2021 | CHPS Compound |  |  | Clinic |  |  | Health Centre |  |  | Poly Clinic |  |  | Hospital |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | EX | RQ | BL | EX | RQ | BL | EX | RQ | BL | EX | RQ | BL | EX | RQ | BL |
| 113,764 | 28 | 36 | 8 | 3 | 7 | 4 | 7 | 8 | 1 | 0 | 2 | 2 | 1 | 2 | 1 |

KEY: EX= No. of Existing Facilities, RQ= Required No. of facilities based on the planning standards, BL= Backlog to be filled

Source: DCPU, 2021 (planning Standards from GHS)

The table above shows the projected district population for the planning period (2022-2025). It indicates the existing health facilities and shows how many are needed based on the planning standards from GHS. The backlog or gaps to be filled within the planning period is also stated. Thus there are 28 functional CHPS compounds in the district whereas 36 are needed based on the planning standards. The backlog or gap to be filled is therefore 8. However, there are also a number of CHPS Compounds that are in a deplorable state and needs renovation. This would also be addressed within the plan period.

3No. clinics exist whereas 7 are needed based on the planning standards, thus an additional 4No. Clinic would be constructed by 2025. 7No. Health Centres exist whereas 8 are needed based on the planning standards, the Kikam CHPS Compound will therefore be upgraded to a health centre within the plan period. The size of the district also requires 2No. Polyclinics. However, none exists at the moment. The only hospital that exists in the district is a CHAG hospital which is over-stretched by teeming patients from all the 3 Nzema districts. The need for a standard district hospital cannot be over-emphasized.

### Population Projections

Population is the single most central factor for the distribution and allocation of development programmes and projects among numerous persons, groups or communities in case of sharing social services and needs. Population projections are crucial in development planning and budgeting decisions.

Generally, assumptions under population projections affect investment decisions on schools, hospitals and roads as well as power, water and sanitation supplies.

Clearly, the supply of these facilities is restricted to age group, both aggregate and desegregation (according to age, sex, occupation etc.) of the population.

The projected population of the district serves as the basis for estimating service requirement of health, water, education etc up to the end of the plan period 2025. They form the basis for the planning and programming phase of the development plan. The district population is projected by using the exponential method based on the absolute figures and age distribution figures for the district in 2010 Population and Housing Census (PHC, 2010).

The assumptions made about the projections are:

- The ratio of the district population will grow at a constant rate throughout the plan period, 2022 - 2025.

- The district’s growth rate (2.3%) will remain the same up to the year 2025.

- Child mortality rate records in the district will reduce further or not change during the plan period.

- Also, the life expectancy at birth for both male and female in Ghana of 61/64 years remains the same till the end of 2025.

- Migration rate in the district will remain unchanged during the plan period, 2025.

- The age-cohorts of the district will not change much during the period.

### Population Size and Distribution

Data from the 2010 Population and Housing Census (PHC) indicates that the district has a population of 87,501 (115,313 projected figure for 2022 with a district growth rate of 2.3%) constituting 3.7 percent of the entire population of the Western Region (as at 2010). Out of this figure, the female population is 59,502 representing 51.6 percent while the remaining 55,811 (48.4 percent) are males. The population of 115,313 may suggest that there is not much pressure on the land, given population density of about 91 persons per km2. However, the same cannot be said of the pressure on resources.

Table 3.4 and 3.5 below present the projected population by sex and age groups respectively of the Ellembelle District. The population projection for the district from 2022 to 2025.

Table 3. 4: Yearly projected total population of the District: 2022–2025

| Yearly | Male | Percentage | Female | Percentage | Total Population | Percentage |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | (%) |  | (%) |  | (%) |
| 2022 | 55811 | 0.484 | 59502 | 0.516 | 115313 | 1 |
| 2023 | 57110 | 0.484 | 60886 | 0.516 | 117996 | 1 |
| 2024 | 58439 | 0.484 | 62302 | 0.516 | 120741 | 1 |
| 2025 | 59798 | 0.484 | 63752 | 0.516 | 123551 | 1 |

Source: DPCU Estimates, 2021 based on 2010 Population & Housing Census.

Table 3. 5: Age Distribution and Projected Population in the District, 2022-2025

| Age Group | 2022 |  | 2023 |  | 2024 |  | 2025 |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Total | % | Total | % | Total | % | Total | % |
| 0-14 | 45433 | 39.4 | 46490 | 39.4 | 47572 | 39.4 | 48679 | 39.4 |
| 15 - 64 | 64229 | 55.7 | 65724 | 55.7 | 67253 | 55.7 | 68818 | 55.7 |
| 65+ | 7726 | 6.7 | 7906 | 6.7 | 8090 | 6.7 | 8278 | 6.7 |
| All Ages | 115,313 | 100 | 117,996 | 100 | 120,741 | 100 | 123,551 | 100 |

Source: DPCU Estimates, 2021 based on 2010 Population & Housing Census

Figure 3. 1: Present the Ellembelle District Projected Population Age-Group 2022 - 2025

Source: DPCU Estimates, 2021 based on 2010 Population & Housing Census.

Table 3.5 and figure 3.1 above show that the age-sex structure of the population of the District is a reflection of typical demographic pattern observed in developing countries where high fertility and mortality rates are observed. This situation is characterized by a high proportion of children less than 15 years (39.4%) while the proportion of elderly persons 65 years and beyond and older (6.7%) is the lowest in the age group.

The table shows that majority of the population in the District (i.e. 79.4%) live in rural areas while only 20.6 percent live in urban areas. Thus, the population in the district is predominantly rural. The table further indicates that the 15-65 age group constitutes the highest proportion (i.e 55.7 percent) of the population in the district followed by the age groups 0-4 with 39.4 percent.  This is an indication that the district has more labour force for development both social and economic.

Table 3. 6: Population Projection of 20 Largest Communities in the District

| Community | 2010 Population | 2022 Projected Population | 2023 Projected Population | 2024 Projected Population | 2025 Projected Population |
| --- | --- | --- | --- | --- | --- |
| Ellembelle District | 87,501 | 115,313 | 117,996 | 120,741 | 123,551 |
| Aiyinase | 10,136 | 13,358 | 13,668 | 13,987 | 14,312 |
| Esiama | 7,874 | 10,377 | 10,618 | 10,865 | 11,118 |
| Asasetere | 4,155 | 5,476 | 5,603 | 5,733 | 5,867 |
| Kikam | 3,742 | 4,931 | 5,046 | 5,164 | 5,284 |
| Teleku Bokazo | 3,610 | 4,757 | 4,868 | 4,981 | 5,097 |
| Awiebo | 3,559 | 4,690 | 4,799 | 4,911 | 5,025 |
| Nkroful | 3,421 | 4,508 | 4,613 | 4,721 | 4,830 |
| Asanta | 3,300 | 4,349 | 4,450 | 4,554 | 4,660 |
| Kamgbunli | 2,562 | 3,376 | 3,455 | 3,535 | 3,618 |
| Eikwe | 2,052 | 2,704 | 2,767 | 2,832 | 2,897 |
| Tandan | 1,913 | 2,521 | 2,580 | 2,640 | 2,701 |
| Salman | 1,884 | 2,483 | 2,541 | 2,600 | 2,660 |
| Bokazo | 1,834 | 2,417 | 2,473 | 2,531 | 2,590 |
| Atuabo | 1,584 | 2,087 | 2,136 | 2,186 | 2,237 |
| Anwia | 1,506 | 1,985 | 2,031 | 2,078 | 2,126 |
| Baseke | 1,448 | 1,908 | 1,953 | 1,998 | 2,045 |
| Ampain | 1,394 | 1,837 | 1,880 | 1,924 | 1,968 |
| Ankobra | 1,373 | 1,809 | 1,852 | 1,895 | 1,939 |
| Sanzule | 1,326 | 1,747 | 1,788 | 1,830 | 1,872 |
| Akropong | 1,209 | 1,593 | 1,630 | 1,668 | 1,707 |

Source: DPCU Estimates, 2021 based on 2010 Population & Housing Census.

## District Development Goal

Achieve accelerated and sustainable growth and development, poverty reduction, promotion of gender equity, protection and empowerment of the vulnerable and excluded within a decentralized democratic environment.

## 3.5 Desired Future Maps

A spatial development framework is that which guides the overall spatial distribution of current and desirable land uses within a municipality in order to give effect to the vision, goals and objectives. Below are the spatial development and local plan maps of the district.

SDF OF ELLEMBELLE

STRUCTURAL PLAN

Figure 3. 2 Spatial Development Framework and Local Plan.

Table 3. 7: Adopted Thematic Goals, Focus Areas, Issues, Policy Objectives and Strategies from NMTDPF 2022-2025

| DEVELOPMENT DIMENSION | FOCUS AREAS | ADOPTED SUSTAINABLE PRIORITIZED ISSUES | ADOPTED POLICY OBJECTIVES | ADOPTED STRATEGIES |
| --- | --- | --- | --- | --- |
| ECONOMIC DEVELOPMENT | Strong and resilient economy | Weak expenditure management and budgetary controls | Ensure improved fiscal performance and sustainability | Strictly enforce the provisions of the Public Procurement Act, 2016 (Act 914), especially with regard to sole sourcing (SDG Targets 12.7, 16.6 |
|  |  |  |  | Extend and strengthen the GIFMIS system across all MDAs and MMDAs (SDG Targets 16.5, 16.6) |
|  | Industrial Transformation | Limited local participation in economic development | Pursue flagship industrial development initiatives | Implement One district, One factory initiative (SDG Targets 9.2, 9.3, 9.4, 9.b, 9.c) |
|  |  |  |  | Implement strategic anchor industrial initiatives (SDG Targets 9.2, 9.3, 9.4, 9.b, 9.c) |
|  | Private Sector Development | Limited access to credit by SMEs | Support entrepreneurship and SME Development | Create an entrepreneurial culture, especially among the youth (SDG Targets 4.4, 8.3, 8.6) |
|  |  | Predominant informal economy |  | Improve access to finance for informal economy operators and agricultural enterprises in rural areas, and strengthen consumer financial protection (SDG Targets 8.10, 9.3 |
|  | Agricultural and Rural Development | Poor marketing systems | Promote demand-driven approach to agricultural development | Ensure implementation of the Ghana Commercial Agriculture Project (GCAP) to link both smallholder and commercial producers to industry (SDG Targets 2.3, 2.c) |
|  |  |  |  | Develop market support services for selected horticulture, food and industrial crops to enhance production for export (SDG Target 2.3) |
|  |  | Inadequate development of and investing in processing and value addition | Ensure improved public investment | Accelerate the provision of critical public infrastructure such as feeder roads, electricity and water (SDG Targets 2.a, 9.1) |
|  |  |  |  | Introduce District Chambers of Agriculture, Commerce and Technology (DCACT) with the mandate to promote agribusiness through an enhanced interface between the private and public sectors at district level (SDG Target 16.6) |
|  |  |  |  | Create District Agriculture Advisory Services (DAAS) to provide advice on productivity enhancing technologies (SDG Targets 2.3, 2.a ,16.6) |
|  |  | Low application of technology especially among smallholder farmers leading to comparatively lower yields | Improve production efficiency and yield | Reinvigorate extension services (SDG Target 2.a) |
|  |  |  |  | Ensure effective implementation of the yield improvement programme (SDG Targets 2.1, 2.4) |
|  |  |  |  | Intensify and increase access to mechanisation along the agriculture value chain (SDG Targets 2.3) |
|  |  | Inadequate start-up capital for the youth | Promote agriculture as a viable business among the youth | Support youth to go into agricultural enterprise along the value chain (SDG Targets 2.1, 2.3, 8.6) |
|  |  |  |  | Provide financial support for youth by linking them to financial institutions for the provision of start-up capital (SDG Target 8.3) |
|  | Fisheries and Aquaculture Development | Weak extension services delivery | Ensure sustainable development and management of aquaculture | Provide consistent and quality extension service delivery (SDG Target 2.a) |
|  |  | Low levels of private sector investment in aquaculture (small-medium scale producers) |  | Provide adequate economic incentives to stimulate private sector investment in aquaculture development (SDG Target 14. b) |
|  |  | Weak involvement of communities in fisheries resource management | Ensure sustainable development and management of aquatic fisheries resources | Promote marine conservation and protection in a sustainable manner (SDG Targets 14.1, 14.2, 14.c) |
|  | Tourism and Creative Arts development | Poor tourism infrastructure and Service | Diversify and expand the tourism industry for economic development | Promote and enforce local tourism and develop available and potential sites to meet international standards (SDG Target 8.9) |
|  |  |  |  | Develop palace museums to preserve national culture and promote tourism in the communities (SDG Targets 8.9, 12.b) |
|  |  |  |  | Promote the establishment of tourism clubs in all educational institutions (SDG Target 12.b) |
| bSOCIAL DEVELOPMENT | Education and Training | Poor quality of education at all levels | Enhance inclusive and equitable access to and participation in quality education at all levels | Expand infrastructure and facilities at all levels (SDG Target 4.a) |
|  |  | Poor linkage between management processes and schools’ operations | Strengthen school management systems | Enhance quality of teaching and learning (SDG Targets 4.7, 4.c) |
|  |  |  |  | Ensure adequate supply of teaching and learning materials (SDG Target 4.c) |
|  | Health and Health Services | Gaps in physical access to quality health care | Ensure affordable, equitable and easily accessible and Universal Health Coverage (UHC) | Accelerate implementation of Community-based Health Planning and Services (CHPS) policy to ensure equity in access to quality healthcare (SDG Targets 1.2, 1.3, 3.1, 3.2, 3.3, 3.8, 16.6) |
|  |  |  |  | Expand and equip health facilities (SDG Target 3.8) |
|  |  | Inadequate emergency services |  | Revamp emergency medical preparedness and response services (SDG Target 3.d) |
|  |  | Poor quality of healthcare services |  | Strengthen the district and sub-district health systems as thebedrock of the national primary healthcare strategy (SDG Targets 1.2, 1.3, 3.1, 3.2, 3.3, 3.4, 3.6, 3.7, 3.8, 16.6) |
|  |  | Unmet health needs of women and girls |  | Ensure gender mainstreaming in the provision of healthcare services (SDG Targets 1.4, 5.c) |
|  |  | Increasing morbidity, mortality and disability due to communicable, non-communicable and emerging diseases | Reduce, disability, morbidity and mortality | Strengthen maternal, newborn care and adolescent services (SDG Targets 3.1, 3.2) |
|  |  |  |  | Intensify implementation of Malaria Control Programme (SDG Target 3.3) |
|  |  |  |  | Implement the non-communicable diseases (NCD) control strategy (SDG Targets 3.4, 3.b) |
|  |  |  |  | Intensify polio eradication efforts (SDG Target 3.2) |
|  |  | High stigmatization and discrimination of HIV and AIDs | Ensure the reduction of new HIV and AIDS/STIs infections especially among the vulnerable group | Intensify education to reduce stigmatisation (SDG Target 3.7 |
|  |  | Lack of comprehensive knowledge of HIV and AIDS/STIs especially among vulnerable groups |  | Expand and intensify HIV Counselling and Testing (HTC) programmes (SDG Targets 3.3, 3.7) |
|  |  |  |  | Intensify efforts to eliminate mother-to-child transmission of HIV (MTCTHIV) (SDG Target 3.3) |
|  |  | Periodic shortages of HIV& AIDS commodities (ARV’s, Test Kits, Condoms) |  | Ensure access to antiretroviral therapy (SDG Target 3.8) |
|  |  | Infant and adult malnutrition | Ensure food and nutrition security | Reduce infant and adult malnutrition (SDG Target 2.2) |
|  |  | Increased incidence of diet-related non-communicable diseases |  | Promote healthy diets and lifestyles (SDG Target 2.1) |
|  |  | Inadequate social mobilization, advocacy and communication on nutrition | Strengthen food and nutrition security governance | Develop and disseminate a multi-stakeholder social mobilisation, advocacy and communication strategy on food and nutrition security (SDG Target ) |
|  | Population Management | Inadequate coverage of reproductive health and family planning services | Improve population management | Improve maternal and adolescent reproductive health (SDG Targets 3.1, 3.7) |
|  |  | Growing incidence of child marriage, teenage pregnancy and accompanying school drop-out rates |  | Eliminate child marriage and teenage pregnancy (SDG Targets 3.7, 5.3) |
|  |  | Inadequate sexual education for young people |  | Strengthen the integration of family planning and nutrition education in adolescent reproductive healthcare (SDG Target 3.7) |
|  | Water and Environmental Sanitation | Increasing demand for household water supply | Improve access to safe and reliable water supply services for all | Provide mechanised boreholes and small-town water systems (SDG Target 6.1) |
|  |  | Inadequate maintenance of facilities |  | Build capacity for development and implementation of sustainable plans for all water facilities (SDG Targets 6.a, 17.9) |
|  |  | High prevalence of open defecation | Improve access to improved and reliable environmental sanitation services | Implement the Toilet for All and Water for All programmes under the IPEP initiative (SDG Targets 6.1, 6.2 |
|  |  |  |  | Develop and implement strategies to end open defecation (SDG Target 6.2) |
|  |  | Poor sanitation and waste management |  | Promote National Total Sanitation Campaign (SDG Target 6.2) |
|  |  |  |  | Provide public education on solid waste management (SDG Target 12.8) |
|  |  | Poor planning and implementation of sanitation plans |  | Monitor and evaluate implementation of sanitation plan (SDG Target 16.6) |
|  | Child and Family Welfare | Weak enforcement of laws and rights of children | Ensure effective child protection and family welfare system | Increase awareness of child protection (SDG Targets 5.3, 16.2, 16.3) |
|  |  | High incidence of children’s rights violation | Ensure the rights and entitlements of children | End harmful traditional practices such as female genital mutilation and early child marriage. (SDG Targets 5.3, 16.2, 16.3) |
|  |  |  |  | Increase access to education and educational materials for orphans, vulnerable children and children with special needs (SDG Targets 4.1, 4.2, 4.5, 4.a) |
|  |  | Abuse and exploitation of children engaged in hazardous forms of labour |  | Eliminate the worst forms of child labour by enforcing laws on child labour and child protection (SDG Targets 5.3, 16.2, 16.3) |
|  | Gender Equality | Unfavorable socio-cultural environment for gender equality | Attain gender equality and equity in in political, social and economic development systems and outcomes | Introduce measures to promote change in socio-cultural norms and values inhibiting gender equality (SDG Targets 5.1, 5.2, 5.3, 10.2) |
|  | Social Protection | Inadequate and limited coverage of social protection programmes for vulnerable groups | Strengthen social protection especially for children, women, persons with disability and the elderly | Strengthen and effectively implement existing social protection intervention programmes and expand their coverage to include all vulnerable groups (SDG Targets 1.3, 5.4, 10.4) |
|  | Disability and Development | Negative perceptions and attitudes towards PWDs | Promote full participation of PWDs in social and economic development of the country | Ensure effective implementation of the 3% increase in District Assemblies Common Fund disbursements to PWDs (SDG Target 16.6) |
|  |  | Lack of physical access to public and private structures for PWDs | Ensure that PWDs enjoy all benefits of Ghanaian citizenship | Ensure the implementation of the Ghana Accessibility Standards to ensure access of PWDs to the built environment, goods, services and assistive devices (SDG Targets 10.2, 11.1) |
|  |  | Poor living conditions of PWDs |  | Provide sustainable employment opportunities and decent living conditions for persons with disability (SDG Targets 4.4, 8.5, 8.8) |
|  | Employment and Decent Work | Low levels of technical and vocational skills | Promote the creation of decent jobs | Develop and promote schemes that support skills training, internship and modern apprenticeship (SDG Targets 8.3, 8.6) |
|  |  | Lack of entrepreneurial skills for self-employment |  | Promote entrepreneurship and financial support for PWDs (SDG Target 8.3) |
|  |  |  |  | Build capacity of informal economy (SDG Target 8.3) |
|  | Sports and Recreation | Inadequate and poor sports infrastructure | Enhance sports and recreational infrastructure | Develop and maintain sports and recreational infrastructure (SDG Target 9.1) |
|  |  |  |  | Promote partnerships with private sector in development of sports and recreation infrastructure (SDG Target 17.17) |
| ENVIRONMENT, INFRASTRUCTURE AND HUMAN SETTLEMENT | Protected Areas | Loss of forest cover | Expand forest conservation areas | Promote alternative sources of livelihood, including provision of bee-hives to forest fringe communities (SDG Target 15.c) |
|  |  |  |  | Map and assign conservation status through bye-laws to mangrove forests, wetlands and sensitive marine areas in district spatial plans (SDG Targets 14.1 14.2, 14.3, 14.5, 15.9) |
|  |  | Weak enforcement of regulations | Protect forest reserves | Strengthen involvement of local communities in the management of forests and wetlands through mechanisms such as comanagement systems (SDG Targets 6.a, 6b) |
|  | Mineral Extraction | Environmental degradation | Ensure sustainable extraction of mineral resources | Ensure mining and logging activities are undertaken in an environmentally sustainable manner (SDG Targets 6.5, 8.4, 12.2, 12.8, 14.2, 15.1, 15.2, 15.3, 15.4, 15.5) |
|  |  | Destruction of forests and farmlands |  | Ensure land restoration after mining operations (SDG Targets 15.1, 15.3) |
|  | Coastal and Marine Area Erosion | Vulnerability of coastal zone to the impact of climate change | Reduce coastal and marine erosion | Promote investment in hard control structures including gabions and boulders (SDG Targets 10.b, 17.5) |
|  |  |  |  | Promote mangrove forest replanting and planting of other vegetative cover to contain erosion (SDG Target 15.2) |
|  |  |  |  | Control sand mining along beaches (SDG Targets 14.2, 14.5) |
|  | Environmental Pollution | Improper disposal of solid and liquid waste | Reduce Environmental Pollution | Improve liquid and solid waste management |
|  |  | Inadequate engineered landfill sites and waste water treatment plants |  | Promote science and technology in waste recycling and waste-toenergy technologies (SDG Targets 6.a, 7.1, 12.5) |
|  | Deforestation, Desertification and Soil Erosion | Illicit trade in forest and wildlife resources | Combat deforestation, desertification and Soil erosion | Promote alternative livelihoods, including eco-tourism, in forest fringe communities. (SDG Target 15.1) |
|  | Climate Variability and Change | Low economic capacity to adapt to climate change | Enhance climate change resilience | Promote and document improved, climate-smart, indigenous agricultural knowledge (SDG Targets 2.4, 16.6) |
|  |  | Vulnerability and variability to climate change |  | Develop climate-responsive infrastructure (SDG Target 9.1) |
|  |  |  | Reduce greenhouse gases | Promote tree planting and green landscaping in communities (SDG Targets 11.7, 15.2) |
|  |  |  |  | Promote urban forestry (SDG Target 11.7) |
|  | Disaster Management | Weak legal and policy frameworks for disaster prevention, preparedness and response | Promote proactive planning for disaster prevention and mitigation | Educate public and private institutions on natural and man-made hazards and disaster risk reduction (SDG Targets 3.d, 13.3) |
|  |  |  |  | Strengthen capacity of the National Disaster Management Organisation (NADMO) to perform its functions effectively (SDG Targets 3.d, 11.5, 11.b, 16.6) |
|  | Transport Infrastructure | Poor quality and inadequate road transport network | Improve efficiency and effectiveness of road transport infrastructure and services | Expand and maintain the national road network (SDG Targets 9.1, 11.2) |
|  |  | Rapid deterioration of roads |  | Provide bitumen surface for road networks in district capitals and areas of high agricultural production and tourism. (SDG Targets 7.3, 11.2) |
|  |  | High incidence of road accidents | Ensure safety and seecurity for all categories of road users | Incorporate pedestrian safety facilities in planning, design, construction and maintenance of road infrastructure (SDG Targets 3.6, 9.1, 11.2) |
|  | Information Communication Technology | Poor quality ICT services | Enhance application of ICT in national development | Improve the quality of ICT services, especially internet and telephony (SDG Target 9.c) |
|  |  |  |  | Accelerate investment in development of ICT infrastructure (SDG Target 17.17) |
|  | Energy and Petroleum | Limited awareness of energy conservation measures | Ensure efficient utilization of energy | Promote the use and design of energy efficient technologies in public and private buildings (SDG Targets 7.3, 7.a) |
|  |  |  |  | Implement energy use efficiency policy and programmes (SDG Targets 7.3, 7.a, 17.14) |
|  |  | Inadequate local content and local participation especially in the upstream oil and gas industry | Promote development and use of indigenous capabilities for exploitation of petroleum resources | Develop local capability in all aspects of the oil and gas value chain (SDG Target 8.3) |
|  |  |  |  | Promote education and skills enhancement initiatives to manage the petroleum sector. (SDG Target 16.6) |
|  | Drainage and Flood Control | Poor drainage system | Address recurrent devastating floods | Intensify public education on indiscriminate disposal of waste (SDG Target 11.6) |
|  |  | Poor waste disposal practices |  | Prepare and implement adequate drainage plans for all MMDAs (SDG Targets 11.3, 11.b) |
|  | Infrastructure Maintenance | Poor and inadequate maintenance of infrastructure | Promote proper maintenance culture | Establish timely and effective preventive maintenance plan for all public infrastructure (SDG Target 9.a) |
|  | Human Settlements and Housing | Weak enforcement of planning and building regulations | Promote sustainable, spatially integraed, balanced and orderly development of human settlements | Fully implement Land Use and Spatial Planning Act, 2016 (Act 925) (SDG Targets 16.6, 17.16) |
|  |  | Inadequate spatial plans for regions and MMDAs |  | Strengthen the human and institutional capacities for effective land use planning and management nationwide (SDG Targets 16.6, 16.a) |
|  | Rural Development | Poor and inadequate rural infrastructure and services | Enhance quality of life in rural areas | Promote rural enterprise development, financial inclusion, service delivery, capacity building and local economic development (SDG Targets 2.a, 11.a) |
|  | Urban Development | Urban concentration in coastal zone | Promote resilient urban development | Prepare and implement structure plans for all grade 1, 2 and 3 settlements (SDG Targets 11.3, 11.a, 11.b) |
|  | Zongos and Inner Cities Development | Limited investment in social programmes in zongos and inner cities | Improve quality of life in slums, zongos and inner cities | Promote investment in social programmes, including education and training, supporting local businesses, and culture and arts in Zongos (SDG Targets 1.b, 10.b, 11.c, 17.17 |
| GOVERNANCE, CORRUPTION AND PUBLIC ACCOUNTABILITY | Local Government and Decentralization | Ineffective sub-district structures | Deepen political and administrative decentralization | Strengthen sub-district structures (SDG Targets 16.6, 17.9) |
|  |  | Weak capacity of local governance practitioners |  | Strengthen local level capacity for participatory planning and budgeting (SDG Targets 16.6, 16.7) |
|  |  | Limited capacity and opportunities for revenue mobilization | Strengthen fiscal decentralization | Enhance revenue mobilisation capacity and capability of MMDAs (SDG Targets 16.6, 17.1) |
|  |  | Inadequate and delays in central government transfers |  | Improve service delivery at MMDA level (SDG Targets 16.6, 16.a) |
|  |  | Weak involvement and participation of citizenry in planning and budgeting | Improve popular participation at regional and district levels | Promote effective stakeholder involvement in development planning process, local democracy and accountability (SDG Target 16.7) |
|  | Human Security and Public Safety | Inadequate and poor quality equipment and infrastructure | Enhance Security Service delivery | Transform security services into a world-class security institution with modern infrastructure, including accommodation, health and training infrastructure facilities (SDG Targets 16.6, 16.a) |
|  |  | Inadequate community and citizen involvement in public safety | Enhance public safety | Promote security awareness of the various communities through neighborhood watch schemes (SDG Targets 16.1, 16.7) |
|  |  |  |  | Intensify enforcement of fire auditing and inspection of public facilities (SDG Targets 16.6, 16.a) |
|  | Attitudinal Change and Patriotism | Political and civic apathy | Promote discipline in all aspects of life | Strengthen advocacy to promote attitudinal change (SDG Target 17.15) |
|  |  |  |  | Promote culture and a good value system as ingredients and catalysts for economic growth (SDG Targets 4.7, 12.b) |

Source: DPCU, 2021

# CHAPTER FOUR

# DEVELOPMENT PROGRAMMES AND SUB-PROGRAMMES

## Introduction

This chapter gives a summary of the broad district development programmes to be undertaken within the medium term by the Ellembelle District Assembly to leverage the implementation of the NMTDPF 2022-2025 in the district. It also includes an indicative financial plan which explains how the Ellembelle District Assembly plans to raise funds for the implementation of the composite programme of action.

## Composite Programmes of Action Linked to the Programme Based Budgeting

The table below shows the composite Programme of Action (PoA) for all the programmes and sub-programmes including monitoring, evaluation and communications from 2022 to 2025. The composite PoA includes the set of activities to be undertaken to address the adopted issues and achieve the stated district objectives.

Table 4. 1: Composite Programme of Action

| Programmes |  | Sub-programmes |  | Objectives | Time Frame |  |  |  |  | Cost |  |  | Prog. Status |  |  |  | Implementing Dep'ts |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | 22 | 23 | 24 |  | 25 | GoG | IGF | Others | New |  | Ongoing |  | Lead |  |  |  | Coll. |
| BUILD A PROSPEROUS SOCIETY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ECONOMIC DEVELOPMENT |  | Local and economic development |  | Support entrepreneurship and MSME Development |  |  |  |  |  |  | 180,000.00 | 8,000.00 |  |  |  |  | GEA |  |  |  | Central Admin. |
|  |  |  |  | Enhance domestic trade. |  |  |  |  |  | 4,480,000.00 | 130,000.00 | 210,000.00 |  |  |  |  | GEA |  |  |  | Central Admin. |
|  |  |  |  | Pursue Strategic Industrial Development Initiatives |  |  |  |  |  | 2,670,000.00 |  |  |  |  |  |  | GEA |  |  |  | CENTRAL ADMIN. |
|  |  | Agricultural and Rural Development |  | Collaborate with private sector to establish a commercial rice farm Improve Public-Private Investments in the Agric sector |  |  |  |  |  |  | 100,000.00 | 1,900,200.00 |  |  |  |  | Agri Dept. |  |  |  | Private Sector (ENI) |
|  |  |  |  | Modernize and enhance agricultural production systems |  |  |  |  |  | 148,170.00 | 134,220.00 | 20,000.00 |  |  |  |  | Agri Dept. |  |  |  | MOFA/CENTRAL ADMIN./ Private Sector |
|  |  |  |  | Ensure sustainable development and management of aquaculture |  |  |  |  |  | 4,100 | 28,400.00 | 16,500.00 |  |  |  |  | Agri Dept |  |  |  | CENTRAL ADMIN./Statistics |
|  |  | Tourism and Creative arts development |  | Diversify and expand the tourism sector for economic development |  |  |  |  |  |  | 540,000.00 | 200,000 |  |  |  |  | Agri Dept |  |  |  | Works Dep't, CENTRAL ADMIN./ NCCE |
| GOAL 2: CREATE OPPORTUNITIES FOR ALL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| EDUCATION AND TRAINING |  | Pre-Tertiary Education | Enhance inclusive and equitable access to and participation in quality education at all levels |  |  |  |  |  |  | 16,559,169.90 | 1,972,368.34 | 2,123,443.57 |  |  |  | GES |  |  |  | CENTRAL ADMIN. |  |
|  |  |  | Strengthen competency-based skill development in Technical and Vocational Schools |  |  |  |  |  |  | 1, 112,000.00 | 47,500.00 |  |  |  |  | CENTRAL ADMIN. |  |  |  | GES |  |
|  |  |  | Promote equitable access to e-learning |  |  |  |  |  |  | 800,000.00 | 480,000.00 | 180,000.000 |  |  |  | CENTRAL ADMIN. |  |  |  | GES |  |
|  |  |  | Strengthen school management systems |  |  |  |  |  |  | 86,000 | 166,400.00 | 452,500,00 |  |  |  | CENTRAL ADMIN. |  |  |  | GES |  |
|  |  |  | Promote inclusive education |  |  |  |  |  |  |  | 76,000 | 28,000 |  |  |  | CENTRAL ADMIN. |  |  |  | GES |  |
|  |  |  | Promote literacy and lifelong learning |  |  |  |  |  |  |  | 28,400 | 16,500 |  |  |  | CENTRAL ADMIN. |  |  |  | GES |  |
| HEALTH AND HEALTH SERVICE DELIVERY |  | Primary Healthcare Delivery | Ensure accessible, and quality Universal Health Coverage (UHC) for all |  |  |  |  |  |  | 124, 430,000.00 | 114,000.00 | 36,274,000.00 |  |  |  | GHS |  |  |  | CENTRAL ADMIN. |  |
|  |  |  | Strengthen healthcare delivery management system |  |  |  |  |  |  | 62,000 |  | 88,000 |  |  |  | GHS |  |  |  | CENTRAL ADMIN. |  |
|  |  |  | Improve Mental Health Administration and Service Delivery |  |  |  |  |  |  |  | 32,000 |  |  |  |  | GHS |  |  |  | CENTRAL ADMIN. |  |
|  |  |  | Improve maternal and adolescent reproductive health |  |  |  |  |  |  |  | 76,400.00 |  |  |  |  | GHS |  |  |  | NGO |  |
|  |  | Communicable and Non-communicable diseases | Reduce the incidence of HIV, AIDS/STIs, other infections and communicable diseases |  |  |  |  |  |  | 106,800.00 |  | 29,080.00 |  |  |  | GHS |  |  |  | CENTRAL ADMIN. |  |
|  |  | Food and Nutrition | Promote nutrition specific and sensitive programmes and interventions |  |  |  |  |  |  | 48,500.00 | 52,000.00 |  |  |  |  | GHS |  |  |  | CENTRAL ADMIN. |  |
| POPULATION MANAGEMENT AND MIGRATION FOR DEVELOPMENT |  | Population Management | Improve population management |  |  |  |  |  |  | 50,800 | 4,000 |  |  |  |  | GHS |  |  |  | CENTRAL ADMIN. |  |
| WATER AND ENVIRONMENTAL SANITATION |  | Potable Water Supply | Improve access to safe, reliable and sustainable water and sanitation supply services for all |  |  |  |  |  |  | 1,800,000.0 |  | 40,000 |  |  |  | CENTRAL ADMIN. |  |  |  | DWST |  |
|  |  | Waste Management and Environmental Sanitation | Enhance access to improved and sustainable environmental sanitation |  |  |  |  |  |  | 862,000 | 8,000 |  |  |  |  | CENTRAL ADMIN. |  |  |  | DWST |  |
|  |  |  | Promote efficient and sustainable wastewater management |  |  |  |  |  |  | 60,000 | 18,000 |  |  |  |  | CENTRAL ADMIN. |  |  |  | DWST |  |
| GENDER, CHILDREN AND SOCIAL PROTECTION |  | Child Protection and youth development | Prevent and protect children from all forms of violence, abuse, neglect and exploitation |  |  |  |  |  |  | 20,000.00 | 206,000.00 | 2,500 |  |  |  | SWCD |  |  |  | CENTRAL ADMIN. |  |
|  |  | Support for the Aged | Enhance the wellbeing and inclusion of the aged in national development. |  |  |  |  |  |  | 10,800.00 |  | 9,600.00 |  |  |  | SWCD |  |  |  | CENTRAL ADMIN. |  |
|  |  | Women empowerment | Attain gender equality and equity in political, cultural social and economic development |  |  |  |  |  |  | 28,400.00 | 68,000.00 | 10,000.00 |  |  |  | SWCD |  |  |  | CENTRAL ADMIN. |  |
|  |  |  | Promote economic empowerment of particularly women |  |  |  |  |  |  |  | 80,000.00 | 12,000.00 |  |  |  | SWCD |  |  |  | CENTRAL ADMIN. |  |
|  |  | Social Protection | Strengthen social protection for the vulnerable |  |  |  |  |  |  | 8,000 |  |  |  |  |  | SWCD |  |  |  | CENTRAL ADMIN. |  |
|  |  | Disability-inclusive Development | Promote equal opportunities for Persons with Disabilities in social and economic development |  |  |  |  |  |  | 800,000.00 |  |  |  |  |  | SWCD |  |  |  | CENTRAL ADMIN. |  |
| GOAL 3: SAFEGUARD THE NATURAL ENVIRONMENT AND ENSURE A RESILIENT BUILT ENVIRONMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| NATURAL RESOURCE MANAGEMENT |  | Mineral Extraction | Promote sustainable extraction of mineral resources |  |  |  |  |  |  | 360,000.00 | 544,000.00 | 400,000.00 |  |  |  | Security Agencies |  |  |  | EHSU,CENTRAL ADMIN. |  |
|  |  | Coastal and Marine Erosion | Reduce coastal and marine erosion |  |  |  |  |  |  | 16,800.00 |  |  |  |  |  | DPU |  |  |  | CENTRAL ADMIN. |  |
|  |  | Deforestation, Desertification and Soil Erosion | Combat deforestation, desertification and Soil erosion |  |  |  |  |  |  | 266,000.00 | 60,000.00 |  |  |  |  | EHSU |  |  |  | PPD, CENTRAL ADMIN. |  |
| CLIMATE CHANGE AND DISASTER RISK |  | Climate Variability and Change | Enhance climate change resilience |  |  |  |  |  |  | 8,000 | 20,000.00 |  |  |  |  |  |  |  |  |  |  |
| RESILIENT BUILT ENVIRONMENT |  | Transport Infrastructure | Improve efficiency and effectiveness of road transport infrastructure and services |  |  |  |  |  |  | 8,002,000.00 | 400,000.00 |  |  |  |  | Works dept |  |  |  | CENTRAL ADMIN. |  |
|  |  |  | Enhance safety and security for all categories of road users |  |  |  |  |  |  | 480,000 |  |  |  |  |  | ICT Dept. |  |  |  | GIFEC |  |
|  |  | Information Communication Technology | Enhance application of ICT in national development |  |  |  |  |  |  | 258,000.00 | 1,016,800.00 |  |  |  |  | PPD |  |  |  | Works Dep't, CENTRAL ADMIN. |  |
|  |  | Human Settlements Development and Housing | Promote sustainable spatially integrated development of human settlements |  |  |  |  |  |  | 128,000.00 | 57,000.00 |  |  |  |  | HR |  |  |  | CENTRAL ADMIN. |  |
| GOAL 4: MAINTAIN A STABLE, UNITED AND SAFE SOCIETY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Resource Mobilization and Expenditure Management | Ensure improved fiscal performance and sustainability through economic data collection, valuation of ratable properties and enforcement of the PFM and Public Procurement Acts |  |  |  |  |  |  | 536,000.00 | 458,000.00 |  |  |  |  | Statistical Dept. |  | Revenue Unit |  |  |  |
| DEMOCRACY, GOVERNANCE AND PUBLIC ACCOUNTABILITY |  | Local Government and Decentralization | Deepen Democratic Governance |  |  |  |  |  |  | 21,259,500 | 2,589,200 |  |  |  |  | CENTRAL ADMIN. |  | WORKS/DPO |  |  |  |
|  |  |  | Deepen participation transparency and public accountability |  |  |  |  |  |  | 200,000.00 | 56,000.00 | 40,000.00 |  |  |  |  |  | CENTRAL ADMIN. |  |  |  |
|  |  | Human Security and Public Safety | Enhance security service delivery |  |  |  |  |  |  | 59,200.00 | 410,000.00 | 20,000.00 |  |  |  | CENTRAL ADMIN. |  | GPS |  |  |  |
|  |  | Corruption and Economic Crimes | Promote the fight against corruption and economic crimes |  |  |  |  |  |  | 40,000 | 20,000.00 |  |  |  |  | Internal Audit |  | External Audit |  |  |  |
|  |  | Civil Society and Civic Engagement | Improve participation of civil society in national development |  |  |  |  |  |  | 87,200 | 38,000.00 | 10,000.00 |  |  |  |  |  |  |  |  |  |
|  |  | Culture | Promote culture in the development process |  |  |  |  |  |  | 8,000.00 | 110,000.00 |  |  |  |  | GES |  | CENTRAL ADMIN. |  |  |  |
| GOAL 5: MAINSTREAM EMERGENCY PLANNING AND PREPAREDNESS INTO GHANA’S DEVELOPMENT PLANNING AGENDA AT ALL LEVELS TO RESPOND TO POTENTIAL INTERNAL AND EXTERNAL THREATS (INCLUDING COVID-19) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| EMERGENCY PLANNING AND RESPONSE (INCLUDING COVID-19 RECOVERY PLAN) | Hydrometeological Threats |  | Promote proactive planning for disaster prevention and mitigation |  |  |  |  |  |  | 94,000.00 | 166,000.00 |  |  |  |  | NADMO |  |  | CENTRAL ADMIN., NCCE |  |  |
|  | Biological Threats |  | Enhance surveillance system and build response capacity to prevent, detect, contain, and respond to epidemics and pandemics |  |  |  |  |  |  |  | 72,000.00 |  |  |  |  | DHD |  |  | NCCE |  |  |
|  | Security |  | Ensure safety of life, property and social wellbeing |  |  |  |  |  |  | 24,000.00 | 18,000.00 |  |  |  |  | CENTRAL ADMIN. |  |  |  |  |  |
|  | Covid-19 Response |  | Strengthen the social protection system to include emergency preparedness and response |  |  |  |  |  |  | 207,200.00 |  |  |  |  |  | DHD |  |  | NCCE |  |  |
| GOAL 6: IMPROVE DELIVERY OF DEVELOPMENT OUTCOMES AT ALL LEVELS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| IMPLEMENTATION, COORDINATION, MONITORING AND EVALUATIO |  | Implementation and Coordination | Strengthen plan preparation, implementation and coordination at all levels |  |  |  |  |  |  | 124,000 | 30,000.00 | 12,000.00 |  |  |  | Dev't Planning |  |  | HODs |  |  |
|  |  | Monitoring and Evaluation | Strengthen monitoring and evaluation systems at all levels |  |  |  |  |  |  | 68,000.00 | 10,000.00 | 10,000.00 |  |  |  | Dev't Planning |  |  | HODs, DA |  |  |
| PRODUCTION AND UTILISATION OF STATISTICS |  | Data-Based Planning and Budgeting | Strengthen production and utilisation of statistics |  |  |  |  |  |  | 84,000.00 |  |  |  |  |  | Statistical Dept. |  |  | HODs |  |  |

PROPOSED PROJECT MAP (2022-2025)

## Programme Financing

This section presents in details the financial requirements for the smooth implementation of the plan. The Indicative Financial Plan has been prepared based on the Indicative Ceilings provided by the Ministry of Finance as well as Internally Generated Revenue Projections by the Assembly. The indicative financial strategy for implementing the Medium-Term Development Plan (2022-2025) of the Ellembelle District Assembly is presented in table 4.2 below.

However, the following are some risks and assumptions for costing the plan all things being equal;

- The District would write development proposals to various development partners in the district for their support.

- The District Assembly would continue to receive funds from the District Assembly’s’ Common Fund (DACF), District Assembly’s’ Common Fund Response Factor Grant (DACF-RFG) and others

- The District Assembly would do its possible best to continue to increase its internally generated funds (IGF) on yearly basis.

The total activities planned for the DMTDP, 2022-2025 have been estimated with the cost of Seventy-Five million, Seven Hundred and Seven Thousand, Four Hundred and Fifty-Two Ghana Cedis (GH¢ 75,707,452) while total projected revenue for the four years is Seventy-One million, Four Hundred and Nine Thousand, Six Hundred and Forty Ghana Cedis (GH¢ 71,409,640). All things being equal, the District Assembly requires an additional amount of Four million, Two-Hundred and Ninety-Seven Thousand, Eight Hundred and Twelve Ghana Cedis (GH¢ 4,297,812).

Table 4. 2: Programme Financing

| DEVELOPMENT DIMENSION | PROGRAMME | PROG. COST (GH₵) | EXPECTED REVENUE & SOURCE OF FUNDING |  |  |  |  | TOTAL | GAP | MECHANISM TO FILL THE GAP |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | GOG | IGF | DACF | DACF-RFG | OTHERS |  |  |  |
| Economic Development | Program 1. | 13,073,896 | 300,000 | 378,000 | 500,560 |  | 1,400,000 | 2,578,560 | -10,495,336 | Intensify the collection of revenue on rateable item and fines Intensify sensitization and education on the need to pay tax, building permits, etc Intensify lobbying and proposals to solicit more from donors and private partners Put in place a tracking mechanisms to track revenue collection |
| Social Development | Program 2. | 48,982,156 | 33,836,000 | 1,116,000 | 7,601,800 | 2,945,000 | 2,134,500 | 47,633,300 | -1,348,856 |  |
| Environment, Infrastructure and Human Settlement | Program 3. | 5,974,700 | 7,535,000 | 1,518,380 | 2,840,000 | 2,330,000 | 4,778,000 | 19,001,380 | 13,026,680 |  |
| Governance, Corruption and Public Accountability | Program 4. | 5,278,500.00 | 300,000 | 550,000 | 215,000 |  | 200,000 | 1,265,000 | -4,013,500 |  |
| Emergency Planning and Response (Including Covid-19) | Program 5. | 1,133,200 | 400,000 | 44,400 |  |  | 150,000 | 594,400 | -538,800 |  |
| Implementation, Coordination, M & E | Program 6. | 1,265,000 |  | 60,000 | 264,000 |  | 13000 | 337,000 | -928,000 |  |
| TOTAL |  | 75,707,452 | 42,371,000 | 3,666,780 | 11,421,360 | 5275000 | 8,675,500 | 71,409,640 | -4,297,812 |  |

## Maintenance Plan of the DMTDP 2022 – 2025

A maintenance plan is critical for the sustainability of assets and infrastructure. The maintenance plan is intended to provide organized guidelines and instructions for preservation activities. Containing specific itemized lists of instructions on how to keep each component of an asset in good working order.

The programmes and projects captured in the plan include assets and related facilities that require regular maintenance in order to ensure sustainability and optimum use by the beneficiaries. In this regard, an effective strategy containing measures for maintaining the assets/infrastructure within the district have been put in place. This represents the execution schedule for the proper maintenance of all assets/infrastructure within the plan period.

Table 4. 3: Maintenance Plan for Projects and Programmes (2022-2025)

| Type of Infrastructure/Assets | Type Of Maintenance | Schedule Of Maintenance (Start Date – End Date) | Estimated Cost of Program GH₵ | Location | Responsibility |
| --- | --- | --- | --- | --- | --- |
| Create Industrial village | - Biannual inspection | - January to March | 600,000.00 | Ampain | Works Dept., EPA & PPD |
| Establish a ceramics factory | - Annually inspection - Painting | - October to December | 2,050,000.00 | Teleku-Bokazo | Works Dept., EPA & PPD |
| Construction of market sheds | - Annually inspection - Rewiring | - January to March | 7,160,000 | Kikam, Akropong Baseke, New Bakanta, Asomase, Nkroful, Aiyinase Esiama, Teleku Bokazo, Eikwe, Sanzule, Atuabo, Asasetre | Works Dept. |
| Establish a commercial rice farm | - Seasonal inspection - Replanting | - April to June | 300,000.00 | Nkroful - Kikam | Agric. |
| Strengthen non-formal education, form clubs in 8 communities to establish piggery and fish ponds | - Annually inspection - Vaccinating | - April to June | 84,900.00 | Asasetre, Asanta, Kotokuom, Sanzule | Agric. |
| Development crocodile pond | - Annually inspection - Vaccinating | - October to December | 300,000.00 | Baku | Agric. & Works Dept. |
| Complete the construction of classroom blocks | - Quarterly inspection - Painting - Renovating | - October to December | 9,443,682.70 | Anwia, T. Bokazo Aluku, Ngabawie, Akropong, Kotokuom Nyamebekyere, Kambunli, Esiama, Pelegkpolenu, Domeabra, Obengkrom, Awiebo, Awiaso, Ankobra Ampain, Azulenloanu, Mantukwa A.B Bokazo Baseke, Kwasikrom New Adiembra, Menzezor, Aiyinase North, Kikam, Bobrama, Asanta | Works Dept.& GES |
| Construction of 4No teachers quarters | - Annually inspection - Painting | - January to March | 440,000.00 | Aiyinasi North, Kwasikrom, Mantukwa, Kotokuom, Adubrim | Works Dept.& GES |
| Construction of Assembly Halls in SHS | - Annually inspection Painting | - April to June | 459,500.00 | Esiama, Kamgbunli | Works Dept.& GES |
| Construct of 4No ICT Centers | - Annually inspection - Painting - Servicing of computers | - January to March | 1,200,000.00 | Aiyinase, Anwia Asanda, Teleku Bokazo | Works Dept. & GES |
| Completion of 2No and Construction of 8No CHPS Compounds | - Annually inspection - Painting | - April to June | 600,000.00 | Aluku,AzulenoanuOld Bakanta, Ankobra, New Adubrim, Ebi, Ayawora, Mpeasem, pelekpolenu, Akoto, kotokuom, Basake, Boamoakpole, Nvelesolo, Ngabawie, Tandan | Works Dept. & DHD |
| Upgrading and expansion works at St. Martin De Porres Hospital | - Quarterly inspection - Painting - Fumigating | - January to March | 9,000,000.00 | Eikwe | Works Dept. & DHD |
| Construct a District Hospital | - Quarterly inspection - Painting - Fumigating | - April to June | 14,000,000.00 | Nkroful | Works Dept. & DHD |
| Construction of NHIS Office | - Quarterly inspection - cleaning Painting | - April to June | 500,000.00 | Nkroful | Works Dept. & DHD |
| Construction of slaughter slabs | - Quarterly inspection - Fumigating | - July to September | 600,000.00 | Aiyinasi, Esiama, Asasetre | Works Dept. & DEHU |
| Completion/ Construction of 5No. gender-friendly and disability friendly institutional latrines | - Quarterly inspection - Cleaning | - July to September | 480,000.00 | Anwia, Teleku Bokazo, Boamoakpole, Asasetre, Tandan, Adurim Baseke, Asanta, Nvelesolo, Salman. | Works Dept. & SWCD |
| Establish a Youth Training Centre | - Quarterly inspection - Painting | - July to September | 100,000.00 |  | Works Dept. & YEA |
| Construction /desilting of drains | - Quarterly inspection - Desilting and dredging - construction | - quarterly - annually | 420,000.00 | Aiyinase | Works Dept. |
| Construction of town road network | - Quarterly inspection - Re shaping | - January to March | 2,000,000.00 | Esiama- Nkrofu- Bokazo Eikwe, Sanzule, Baku, Ngalekyi, Bobrama, Aiyinase South, Aiyinase North, and others | Works Dept. |
| Construction of Modern lorry parks and stores | - Quarterly inspection - Re shaping | - April to June | 400,000.00 | Aiyinase, Esiama | Works Dept. |
| Rehabilitate of existing post offices | - Quarterly inspection - Painting | - July to September | 200,000.00 | Nkroful, Esiama, Aiyinase | Works Dept. |
| Construction of Community Centers | - Annually inspection Painting | - October to December | 780,000.00 | New Bakanta, Adurim, Aiyinasi North, and others | Works Dept. |
| Construction of 6No. Area Council Office | - Quarterly inspection - Painting | - July to September | 1,000,000.00 | All Area Councils | Works Dept. |
| Construction of 1No. Police Stations | - Quarterly inspection Painting | - April to June | 350,000.00 | Asomase | Works Dept. |
| Maintenance of Assembly vehicles, computers and other logistics | - Quarterly inspection | - April to June | 400,000.00 |  | Procurement |

## CHAPTER FIVE

## 5.0 ANNUAL ACTION PLANS

## 5.1 Introduction

This section of the plan indicates the arrangements put in place for the implementation of the plan of each year over the 4-year period.

The Annual Action Plan would be implemented by the Departments, and Agencies of the DAs in collaboration with the NGOs, CSOs, FBOs and the Private sector. The implementation of the Annual Action Plans is expected to be supported by timely inflow of resources in order not to distort its schedule.

## 5.2 Yearly Action Plans (2022-2025)

| Programmes | Sub-programmes | Projects/activities | Location | Time Frame |  |  |  | Cost |  |  | Prog Status |  | Implementing Dep'ts |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | 1 | 2 | 3 | 4 | GoG | IGF | Others | New | Old | Lead | Coll. |
|  |  | Goal 1: Build a Prosperous Society |  |  |  |  |  |  |  |  |  |  |  |  |
| ECONOMIC DEVELOPMENT | Local and Economic Development | - Support 1000 local businesses with training and funding | District Wide |  |  |  |  |  | 30,000 |  |  |  | GEA | CENTRAL ADMIN. |
|  |  | - Construction of 3No market and completion of 1No market. | Adubrim Esiama Nkroful Aiyinase |  |  |  |  | 1,500.000.00 |  |  |  |  | Works Dep't | CENTRAL ADMIN. |
|  |  | - Registration and training of local businesses. | District Wide |  |  |  |  |  | 5,000 |  |  |  | GEA | RGD |
|  |  | - Create a marketing platform for sellers and buyers of agro produce | District Wide |  |  |  |  |  | 10,000 |  |  |  | GEA | Agri Dept/ENI |
|  |  | - Establish agro-processing Centres in rural communities | Aiyinasi North |  |  |  |  | 50,000 | 90,000 |  |  |  | GEA | NBSSI, Agric Dept,CENTRAL ADMIN. |
|  |  | - Train 50 forest fringe community members in bee keeping, snail and grass cutter rearing | District wide |  |  |  |  |  | 5,000.00 | 10,000.00 |  |  | GEA | MOFA, CENTRAL ADMIN. |
|  |  | - Prepare and implement Local Economic Development (ED) Plan | District wide |  |  |  |  |  | 7,500.00 | 7,500 |  |  | GEA | CENTRAL ADMIN. |
|  |  | - Organize annual Business Expo | District wide |  |  |  |  |  | 30,000 | 45,000 |  |  | GEA | CENTRAL ADMIN., Agri Dept., Private Sector, |
|  | Agricultural and Rural Development | - Collaborate with private sector to establish a commercial rice farm | Nkroful |  |  |  |  |  | 25,000 | 50,000 |  |  | Agri Dept. | Private Sector |
|  |  | - Support the Implementation of the EDGE Project | Menzezor |  |  |  |  |  |  | 1,900,000.00 |  |  | ENI | MOFA/CENTRAL ADMIN. |
|  |  | - .Establish and update database on all farmers in the district | District Wide |  |  |  |  | 4,100 |  |  |  |  | Agri Dept | Central Admin/Statistics |
|  |  | - .Advanced E-Extension and sensitization activities (study tour, malaria, COVID 19, child labour, HIV, pest and infections) | Menzezor, District Wide |  |  |  |  | 4.800 | 2,000 |  |  |  | Agri Dept | WORKS DEP'T, CENTRAL ADMIN./ NCCE/GHS |
|  |  | - Train 500 and equip 200 youth in modern agriculture and agro-business | District Wide |  |  |  |  |  | 5,000 | 10,000 |  |  | Agri Dept | Agri Dept. |
|  |  | - Organize District Level Farmers Day Celebration | Selected Community |  |  |  |  | 50,000 |  | 100,000 |  |  | Agri Dept | DPO, CENTRAL ADMIN. |
|  |  | - Conduct yield studies on selected crops (rice, maize, cassava and plantain) | District Wide |  |  |  |  |  | 5,375 | 5,200 |  |  | Agri Dept. | MOFA |
| ECONOMIC DEVELOPMENT | Agricultural and Rural Development | - Collaborate with forestry commission to plant and nature 5,000 trees | District wide |  |  |  |  | 5000.00 |  |  |  |  | Forestry | Agric Dept |
|  |  | - Early warning systems and emergency preparedness for livestock and crop production. (small ruminant, COVID,PPE and FAW) | District wide |  |  |  |  | 5,810.00 |  |  |  |  | Agric Dept | CENTRAL ADMIN./NADMO |
|  |  | - Support the distribution of 10,000 (PERD) rubber seedling and 50,000 oil palm seedling by CSIR and MDF. | District wide |  |  |  |  |  | 21,500 |  |  |  | Agric Dept | CENTRAL ADMIN. |
|  |  | - Organise capacity building training for staffs ( AEAs, DDOs) |  |  |  |  |  |  | 15,000 | 3,000 |  |  | Agric Dept | CENTRAL ADMIN. |
|  |  | - Undertake M&E of implemented activities |  |  |  |  |  |  | 10,000 | 15,180 |  |  | Agric Dept | CENTRAL ADMIN. |
|  |  | - Train 20 women farmers and 5 AEAs on local food utilization |  |  |  |  |  | 3,950.00 |  |  |  |  | Agric Dept | CENTRAL ADMIN. |
|  |  | - Showcase to 20 women farmers the establishment of home gardens |  |  |  |  |  | 3,230 |  |  |  |  | Agric Dept | CENTRAL ADMIN. |
| ECONOMIC DEVELOPMENT | Agricultural and Rural Development | - Train 10 farmers (5 males and 5 females) on safe use and handling of Agro-Chemicals by the end of October 2022. |  |  |  |  |  | 2,790 |  |  |  |  | Agric Dept | CENTRAL ADMIN. |
|  |  | - Support the District Chamber of Agriculture, Commerce and Technology (Training for DCAT officers) | District Assembly |  |  |  |  |  | 5,000 | 5,000 |  |  | Agri Dept | CENTRAL ADMIN. |
|  |  | - Organize /Participate in meeting (RELC and Others) | District Assembly |  |  |  |  |  | 1,500 | 3,364 |  |  | Agri Dept | CENTRAL ADMIN. |
|  | Tourism and creative Arts development | - Promotion of drama, poetry festive and cultural activities (kundum festival) | District wide |  |  |  |  |  | 25,000 | 10,000 |  |  | Culture Unit | CENTRAL ADMIN. |
|  |  | - Form 10 tourism clubs in basic and Senior High Schools | Selected Schools |  |  |  |  |  | 2,500 | 1,500 |  |  | GES | Culture/ CENTRAL ADMIN. |
|  |  | - Rehabilitation of Kwame Nkrumah Motel/Mausoleum | Nkroful |  |  |  |  |  | 330,000 |  |  |  | Works | DA |
|  |  | Goal 2: Create Opportunities for All |  |  |  |  |  |  |  |  |  |  |  |  |
| EDUCATION AND TRAINING | Pre-Tertiary Education | - Support STMIE programme | District wide |  |  |  |  | 3,625 | 3,000 |  |  |  | GES | CENTRAL ADMIN. |
|  |  | - Completion/Construction of 2No. 6-unit classroom block | Esiama SDA, Anwia(N), Ngabawie(N) |  |  |  |  | 1,110,000.00 | 169,500 |  |  |  | CENTRAL ADMIN. | GES |
|  |  | - Completion of 7No. 3-unit classroom blocks and construction of 1No 3-unit classroom block | Aiyinase Nyamebekyere, Basake, Akropong, Awiebo, Awiaso, Salman, Nvelesolo Asomase (N) |  |  |  |  | 616,223.9 |  | 465,196.79 |  |  | CENTRAL ADMIN. | GES |
|  |  | - Completion 2No. KG and construction of 1No KG block | Ankobra, Teleku Bokazu, Kotokuom(N) |  |  |  |  | 500,000 | 315,368.34 |  |  |  | CENTRAL ADMIN. | GES |
|  |  | - Completion/ Construction of 1No. 4-unit teachers quarters | Adubrim, Awiebo |  |  |  |  | 230,000 | 20,000 | 50,000 |  |  | CENTRAL ADMIN. | GES |
|  |  | - Completion of Assembly Hall for Esiama Sec-Tec | Esiama |  |  |  |  | 412,000 | 47,500 |  |  |  | CENTRAL ADMIN. | GES |
|  |  | - Support to organize inter-school sports Competitions | District Wide |  |  |  |  |  | 10,000.00 |  |  |  | CENTRAL ADMIN. | GES |
| EDUCATION AND TRAINING | Pre-Tertiary Education | - Provide items for "my first day at school" celebrations and institute Best Teacher Award especially in deprived schools | District wide |  |  |  |  | 20,000 | 18,500 | 15,000.00 |  |  | DA | GES/Private Schools |
|  |  | - Supply of classroom furniture/Uniforms to schools | Some Selected Schools |  |  |  |  | 90,000 | 50,000 |  |  |  | Works /Procurement | GES |
|  |  | - facilitate the completion of GETFUND,MSDI, GNPC project | NASS, Esiama Sec Tech, KIMTECH. Charlotte Dolphine training institute |  |  |  |  | 200,000 |  | 700,000 |  |  | Central Admin. | GES |
|  |  | - Support needed but brilliant students and Award scholarship to PWDs in higher education | District wide |  |  |  |  |  | 15,000 | 7,000 |  |  | SWCD | GES |
|  |  | - Facilitate the provision of resource persons such as sign language interpreters and braille transcribers at all levels | District wide |  |  |  |  |  | 4,000 |  |  |  | SWCD | PWD |
|  |  | - Promote the re-entry of dropouts and adolescent mothers back to school after childbirth | Predominant Communities |  |  |  |  |  | 5,000 |  |  |  | SWCD | GES |
| EDUCATION AND TRAINING | Pre-Tertiary Education | - Construct 4No. ICT Centres | Asanta |  |  |  |  | 200,000.00 | 100,000.00 |  |  |  | Works Dep't | GES |
|  |  | - Procure and supply 100 computers and accessories to basic schools and senior high schools | All SHS and basic schools in the District |  |  |  |  |  | 20,000 | 27,000 |  |  | Central Admin. | GES/Pivate Sector |
|  |  | - Conduct induction workshop for newly trained teachers | District wide |  |  |  |  | 15,000 |  |  |  |  | GES | CENTRAL ADMIN./HRM |
|  |  | - Conduct SPAM in basic schools and Organize yearly mock exams for JHS students | District wide |  |  |  |  | 6,500 | 10,000.00 |  |  |  | GES | CENTRAL ADMIN. |
|  |  | - Support regular inspection and monitoring of schools, SMCs and PTAs | District wide |  |  |  |  | 2,000 | 4,500 |  |  |  | GES | CENTRAL ADMIN. |
|  |  | - Strengthen non-formal education, form clubs in 4 communities to establish a rice farm, piggery, poultry and fishponds | Asanta Kotokro, Sanzule, Aiyinase |  |  |  |  |  | 17,100 | 4,125 |  |  | GES | Agric Dept, Private Sector |
| HEALTH AND HEALTH SERVICE DELIVERY | Primary Healthcare Delivery | - Construct a District Hospital at Nkroful | Nkroful |  |  |  |  | 14,000,000 |  |  |  |  | GHS | CENTRAL ADMIN. |
|  |  | - Provision of medical supplies to CHPS Compounds (BP apparatus, weighing scale and motor bikes) | All facilities |  |  |  |  |  | 6,000 | 7,500 |  |  | CENTRAL ADMIN. | GHS |
|  |  | - Completion and construction of 2No. CHPS Compounds | Aluku, Azulenoanu Tandan, Mantukwa, |  |  |  |  | 600,000.00 |  |  |  |  | CENTRAL ADMIN. | GHS |
|  |  | - Complete the upgrading and expansion works at St. Martin De Porres Hospital, Eikwe | Eikwe |  |  |  |  |  |  | 9,000,000 |  |  | CENTRAL ADMIN. | GNPC |
|  |  | - Complete the construction of NHIS Office at Nkroful | Nkroful |  |  |  |  | 500,000 |  |  |  |  | CENTRAL ADMIN. | NHIS |
|  |  | - Conduct public health education and organize campaigns on mental health | District Wide |  |  |  |  | 1,500 | 8,000 |  |  |  | GHS | SWCD,Religious groups |
|  |  | - Support to organize capacity building programmes for Health Staff for effective monitoring and evaluation | District Wide |  |  |  |  | 15,500 |  | 22,000 |  |  | GHS | NGO |
|  |  | - Distribute 2500 insecticide treated mosquito nets | District Wide |  |  |  |  | 2,250 | 8,500 |  |  |  | GHS | CENTRAL ADMIN. |
|  |  | - Promote ante/post natal services and organize district health wide health screening activities. | District Wide |  |  |  |  | 7,500 |  | 4,000 |  |  | GHS | CENTRAL ADMIN. |
|  |  | - Continue the administration of vaccines under the NID programme | District Wide |  |  |  |  | 3,000 | 6,000 | 2,000 |  |  | GHS | CENTRAL ADMIN. |
|  |  | - Organize District wide Health Screening | District Wide |  |  |  |  |  | 12,000 | 33,000 |  |  | GHS | NGOs |
|  |  | - Embark on quarterly regenerative health and nutrition outreach programmes | District Wide |  |  |  |  | 12,125 | 5,000 |  |  |  | GHS | CENTRAL ADMIN. |
| HEALTH AND HEALTH SERVICE DELIVERY | HIV, AIDS/STIs and other infections | - Intensify comprehensive education on HIV/AIDS and STIs, including reduction of stigmatisation | District wide |  |  |  |  | 6,625 |  | 6,250 |  |  | GHS | NGOs |
|  |  | - Organize quarterly HIV/AIDS Committee Meetings and world AIDS day. | Nkroful |  |  |  |  | 11,000.00 |  |  |  |  | DAC | GHS |
|  |  | - Counsel and test for HIV in all pregnant women | District wide |  |  |  |  | 7,575 |  | 1,020 |  |  | GHS | CENTRAL ADMIN. |
|  |  | - Organize HIV/AIDS and TB campaigns in schools | District wide |  |  |  |  | 7,500 |  |  |  |  | GHS | GES |
|  | Population Management |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | - Ensure registration of all birth and death in the district | District wide |  |  |  |  |  | 1,000 |  |  |  | Birth & death Dept. | CENTRAL ADMIN. |
|  |  | - Organize quarterly sensitization programmes on teenage pregnancy and child marriage | District wide |  |  |  |  |  | 19,100 |  |  |  | SWCD | CENTRAL ADMIN./NCCE |
|  |  | - Provide support for family planning activities | District wide |  |  |  |  | 5,000 |  | 2,000 |  |  | GHS | CENTRAL ADMIN. |
| HEALTH AND HEALTH SERVICE DELIVERY | Food and Nutrition | - Organize food and nutrition campaign in schools and health centres and on radio | District wide |  |  |  |  |  | 13,000 | 2,000 |  |  | GHS/EHSU | CENTRAL ADMIN. |
|  |  | - Monitor the school feeding programme to ensure quality and well-balanced diet is served | District wide |  |  |  |  | 10000 | 3000 |  |  |  | Central Admin | CENTRAL ADMIN. |
| WATER AND ENVIRONMENTAL SANITATION | Water Supply, Waste Management and Environmental Sanitation | - Drilling of 10No. Disability friendly Mechanized boreholes | Anokye, Baku, Asanta. Ngalakyi Baku, Asomase, Aluku, Ankobra, Ewe community, health centers. |  |  |  |  | 250,000 |  | 10,000 |  |  | CENTRAL ADMIN. | DWST |
|  |  | - Construction/ Extension of water supply for selected communities | Nkroful, Kamgbuli,Asomase, Teleku Bokazo |  |  |  |  | 200,000 | 100,000 |  |  |  | CENTRAL ADMIN. | DWST |
|  |  | - Completion of 7No. Boreholes with Hand pumping Machines | Bobrama,Baku Nvuma, Kamgbunli,Beposo,At ababo and Pelepolena |  |  |  |  |  | 200,000.00 |  |  |  | CENTRAL ADMIN. | DWST |
|  |  | - Siting, Drilling and Developing of 4no. Boreholes and Construction of Aprons and Drains with soakway Pit and Installation of hand pumping Machines | Asastre -Nyamebyere, Ngabawie, Agbeyeye and Aluku |  |  |  |  | 400,000 | 200,000 |  |  |  | CENTRAL ADMIN. | DWST |
| WATER AND ENVIRONMENTAL SANITATION | Water Supply, Waste Management and Environmental Sanitation |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | - Prepare, and implement the District Water and Sanitation Plan | District Assembly |  |  |  |  |  | 8,500 |  |  |  | DWST | CENTRAL ADMIN. |
|  |  | - Form and train 10No. WATSan Committees | Selected Communities |  |  |  |  | 15,000 |  |  |  |  | DWST | CENTRAL ADMIN. |
|  |  | - Construction of 3No. gender-friendly and disability friendly institutional latrines | Basake, Asanta, Nvenlosolo |  |  |  |  | 360,000.00 |  |  |  |  | Works Dept. | EHSU |
|  |  | - Completion/ constriction of Toilets | Tandan, Awiebo, Aiyinase |  |  |  |  | 150,000.00 |  |  |  |  | EHSU | CENTRAL ADMIN. |
|  |  | - Implement the CLTS programme and intensify environmental health education campaigns | Distict wide |  |  |  |  | 25,000 |  |  |  |  | EHSU | CENTRAL ADMIN. |
|  |  | - Construction of slaughter slabs at market places | Aiyinasi, Esiama, |  |  |  |  | 100,000 |  |  |  |  | CENTRAL ADMIN. | EHSU |
|  |  | - Conduct screening of food vendors | District wide |  |  |  |  | 7,500 | 5,000 |  |  |  | EHSU | GHS, CENTRAL ADMIN. |
|  |  | - Support the Conveyance/ waste management activities | District wide |  |  |  |  | 320000 |  |  |  |  | EHSU | CENTRAL ADMIN. |
|  |  | - Monitor waste collection by zoomlion | Market Places |  |  |  |  |  | 10,000 |  |  |  | EHSU | CENTRAL ADMIN. |
|  |  | - Procure a cespit emptier | District Assembly |  |  |  |  | 500,000.00 |  |  |  |  | EHSU | CENTRAL ADMIN. |
| GENDER, CHILDREN AND SOCIAL PROTECTION | Child Protection and Youth Development | - Mobilize and sensitize 10 communities on parental responsibilities | District Wide |  |  |  |  |  | 25,000 |  |  |  | CENTRAL ADMIN. | GES, SWCD |
|  |  | - Enforce child right and Gender related Bye laws | District Wide |  |  |  |  |  | 25,000 |  |  |  | SWCD | GES, NCCE,DA, Police etc. |
|  |  | - Monitor Day Care Centres and orphanages within the district | District Wide |  |  |  |  | 5,000 | 2,000 |  |  |  | SWCD | CENTRAL ADMIN. |
|  |  | - organize sensitization programmes on child protection issues | District Wide |  |  |  |  |  | 13,000 UNICEF |  |  |  | SWCD | CENTRAL ADMIN., NCCE, LABOUR DEP'T, NCCE |
|  |  | - Institute Child Protection Committees in 20 Communities | District wide |  |  |  |  |  | 5,000 UNICEF |  |  |  | SWCD | CENTRAL ADMIN. |
|  |  | - Settle child maintenance cases Organize community engagements and behavioural change campaigns to promote positive parenting | District wide |  |  |  |  |  | 5,000 UNICEF |  |  |  | SWCD | UNICEF |
|  |  | - Organize girls empowerment summits in Senior High Schools and create a pool of potential female leaders | District wide |  |  |  |  |  | 17,000.00 |  |  |  | SWCD | GES |
|  |  | - Establish adolescent clubs in schools and communities | District wide |  |  |  |  |  | 3,500 | 3,000 |  |  | SWCD | Gender Desk, GES |
|  | Support for the Aged | - Create a database on the aged and support the Ellembelle Elderly Care Centre with Food Items | Ampain |  |  |  |  | 8,000 |  | 2,400 |  |  | SWCD/DPU | CENTRAL ADMIN. |
|  | Women empowerment | - Organize quarterly sensitization Campaigns on gender-based violence and other harmful cultural practices | District Wide |  |  |  |  | 10,000 |  | 3,500 |  |  | SWCD/DPCU | CENTRAL ADMIN. |
|  |  | - Organize skills training for 1000 women | District Wide |  |  |  |  |  | 20,000 | 5,000 |  |  | SWCD | CENTRAL ADMIN., GEA |
|  | Social Protection | - Mobilize indigenes and vulnerable people for NHIS registration | District Wide |  |  |  |  | 10,000 |  |  |  |  | SWCD | NHIS, CENTRAL ADMIN. |
|  |  | - Support People With Disabilities (PWDs) with training skills, items, cash, school fees medical bills and start-up capital. | District Wide |  |  |  |  | 200,000.00 |  |  |  |  | SWCD | GEA, CENTRAL ADMIN. |
|  |  | - Monitor and support the Livelihood Empowerment Against Poverty (LEAP) programme | District wide |  |  |  |  | 10,000 |  |  |  |  | SWCD | CENTRAL ADMIN. |
|  |  | Goal 3: Safeguard the Natural Environment and Ensure A Resiliant Built Environment |  |  |  |  |  |  |  |  |  |  |  |  |
| NATURAL RESOURCE MANAGEMENT | Mineral Extraction | - Arrest and prosecute illegal, sand winners, miners, lumbers | District Wide |  |  |  |  | 30,000 | 30,000.00 |  |  |  | Security Agencies | EHSU,CENTRAL ADMIN. |
|  |  | - Establish a community mining scheme in 3 communities. | Salma, Teleku Bokazo, Nkroful |  |  |  |  |  | 6,000 | 3,000 |  |  | Works Dept. | CENTRAL ADMIN. |
|  |  | - Ensure the reclamation of degraded land after mining | Mining communities |  |  |  |  |  | 100,000 | 100,000 |  |  | PPD | CENTRAL ADMIN. |
|  | Coastal and Marine Erosion | - Revive conservation committee groups and build women capacity in conservation | District Assembly |  |  |  |  | 5,000 |  |  |  |  | DPU | CENTRAL ADMIN. |
|  | Deforestation, Desertification and Soil Erosion | - Develop landfill site into a modern engineered site | Ala Bokazo |  |  |  |  | 300,000 |  |  |  |  | EHSU | PPD, EPA |
|  |  | - Protect natural reserves (mangroves and forest) and recreation areas from encroachment | District Wide |  |  |  |  | 26,500 | 15,000.00 |  |  |  | Forestry | Works/NADMO/PPD |
| CLIMATE CHANGE AND DISASTER RISK REDUCTION | Climate Variability and Change |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | - Organize Capacity Building Training in Climate Change for DPCU/HODS Members | District Assembly |  |  |  |  |  |  | 6,500 |  |  | Agri Dept. | CENTRAL ADMIN. |
|  |  | - farmers on climate smart agriculture technologies | District wide |  |  |  |  | 5,000 |  |  |  |  | Agric .Dept. | MOFA |
|  |  | - Complete the construction of town roads | Esiama- Nkrofu- Bokazo Eikwe, Sanzule, Baku, Ngalekyi, Bobrama, Aiyinase South, Aiyinase North, and others |  |  |  |  | 2,000,000 |  |  |  |  | GHA, Dep't of Feeder Roads | CENTRAL ADMIN. |
|  |  | - Develop of Modern lorry parks and stores at Aiyinase and Esiama | Aiyinase |  |  |  |  |  | 100,000 |  |  |  | GHA | CENTRAL ADMIN. |
|  |  | - Support road safety activities in the District | District Wide |  |  |  |  | 120,000.00 |  |  |  |  | GHA | CENTRAL ADMIN. |
| CLIMATE CHANGE AND DISASTER RISK REDUCTION | Information Communication Technology | - Rehabilitate existing post offices | Aiyinase, Nkroful Esiama |  |  |  |  |  | 200,000 |  |  |  | Works dept | CENTRAL ADMIN. |
|  |  | - Renovation of ICT Centre at Aiyinase and Install Wi-Fi at the District Assembly Office | Aiyinase Nkroful |  |  |  |  | 64,500 | 54,200 |  |  |  | ICT Dept. | GIFEC |
|  | Human Settlements Development and Housing | - Organize technical and statutory planning committee meetings | District Assembly |  |  |  |  |  | 12,000 |  |  |  | PPD | HODs |
|  |  | - Preparation of local plans | Bomoakpole |  |  |  |  |  | 20,000 |  |  |  | PPD | CENTRAL ADMIN. |
|  |  | - Sensitization of the public on Land use planning and permitting | District Wide |  |  |  |  |  | 3,000 |  |  |  | PPD | Works Dep't, CENTRAL ADMIN. |
|  |  | - Organize joint inspections to check unauthorised developments | District Wide |  |  |  |  |  | 20,000.00 |  |  |  | PPD | Works Dep't, CENTRAL ADMIN. |
|  | Drainage and Flood Control | - Prepare and implement drainage plans for flood prone areas | District Assembly |  |  |  |  |  | 5,000 |  |  |  | PPD | Works Dep't, CENTRAL ADMIN. |
|  |  | - Construct and frequently desilt chocked drains | District Assembly |  |  |  |  | 200,000.00 | 20,000 |  |  |  | EHSU | PPD,WORKS,NADMO |
| CLIMATE CHANGE AND DISASTER RISK REDUCTION | Infrastructure Maintenance | - Organize capacity building training in inventory and asset management for selected staff | District Assembly |  |  |  |  |  | 7,000 |  |  |  | HR | CENTRAL ADMIN. |
|  |  | - Prepare operation and maintenance (O&M) Plan | District Assembly |  |  |  |  | 5,000 |  |  |  |  | Works Dep't | Dev't Planning Unit |
|  |  | - Undertake building inspections and ensure that all public buildings are disability friendly | District wide |  |  |  |  |  | 10,000 |  |  |  | Works Dep't | CENTRAL ADMIN. |
|  |  | Goal 4: Maintain a Stable, United and Safe Society |  |  |  |  |  |  |  |  |  |  |  |  |
| DEMOCRACY, GOVERNANCE AND PUBLIC ACCOUNTABILITY | Resource Mobilization and Expenditure Management | - Update economic/ Tourism data to improve revenue | District wide |  |  |  |  | 100,000.00 |  |  |  |  | Statistical Dept. | Revenue Unit,DPO, PPD, Budget |
|  |  | - Provide revenue collection and management logistics | District Assembly |  |  |  |  | 12,000 |  |  |  |  | Revenue Unit | GIZ, CENTRAL ADMIN. |
|  |  | - Organize public sensitization on revenue mobilization in market places and lorry stations | Aiyinase, Asasetre, Esiama, Teleku Bokazo |  |  |  |  |  | 7,500 |  |  |  | Revenue Unit | Budget/Finance, Works, PPA, NCCE |
|  |  | - Mount and update revenue performance and Accountability Bill Boards at the Various Area Councils | Esiama, Asasetre, Awiebo Basake, Aiyinase, Kikam, Nkroful, Atoabo |  |  |  |  | 22,000 |  |  |  |  | Fin. Dep't | CENTRAL ADMIN. |
|  |  | - Prepare and Implement a Revenue Improvement Action Plan and Concept note | District Assembly |  |  |  |  | 5,000.00 | 7,000 |  |  |  | DBU | DPO, Fin Dept |
| Democracy, Governance and Public Accountability | Local Government and Decentralization | - Furnishing/ Construction of 2No. Area Council Office | Esiama, Aiyinase, Awiebo |  |  |  |  | 500,000.00 | 500,000 .00 |  |  |  | CENTRAL ADMIN. | WORKS/DPO |
|  |  | - Support and build the capacity of women to contest for political positions | District Wide |  |  |  |  | 4,500 |  | 6,000 |  |  | NCCE | CENTRAL ADMIN. |
|  |  | - Organize other statutory meetings and celebration of National days | District Assembly |  |  |  |  | 90,000.00 | 50,000.00 | 40,000.00 |  |  | Central Admin | Adamus, Ghana Gas, ENI, etc |
|  |  | - Secure/furnish office accommodation for area councils | District Assembly |  |  |  |  | 100,000.00 |  |  |  |  | Planning | Finance, CENTRAL ADMIN. |
|  |  | - Coordinate the preparation of Community Action Plans | District Assembly |  |  |  |  | 10,000.00 |  |  |  |  | Dev't Planning/PP | HODs |
|  |  | - Review and prepare Annual Action Plans, Composite Budgets, Procurement plans | District Assembly |  |  |  |  | 50,000.00 |  |  |  |  | Planning, Budget Unit, Procurement | HODs |
|  |  | - Undertake Town Hall Meetings on AAPs, fee-fixing and composite annual budget | All Area Council Offices |  |  |  |  | 50,000 | 10,000.00 | 5,000 |  |  | Dev't Planning/Budget | HODs, CENTRAL ADMIN. |
|  |  | - Organize Public Hearings of the MTDP (2022-2025). | District Assembly |  |  |  |  |  | 40,000 | 5,000 |  |  | DPO | HODs, other stakeholders |
| Democracy, Governance and Public Accountability | Local Government and Decentralization | - Administer comprehensive HRMIS and submit monthly returns to RCC | District Assembly |  |  |  |  |  | 4,000 |  |  |  | HR | HODs |
|  |  | - Organize capacity building training for revenue collectors and Area Council members on effective revenue mobilization | District Assembly |  |  |  |  |  | 40,000.00 |  |  |  | HR/DPU | NGO |
|  |  | - Organize capacity building training for all staff and Assembly members | District Assembly |  |  |  |  | 35,000 |  |  |  |  | HR | Fin. Dep't, HODs |
|  |  | - Procure office stationery, logistics, Vehicles and others | District Assembly |  |  |  |  | 600,000.00 |  |  |  |  | Procurement | CENTRAL ADMIN. |
|  |  | - Maintenance of Assembly Accomodation, vehicles, computers and other logistics | District Assembly |  |  |  |  | 100,000.00 | 10,000.00 |  |  |  | Procurement | CENTRAL ADMIN. |
| Democracy, Governance and Public Accountability | Human Security and Public Safety | - Construction of Police Station | Asomase |  |  |  |  |  | 350,000 |  |  |  | CENTRAL ADMIN. | GPS |
|  |  | - Form 4No. Neighbourhood watchdog committees | Selected Communities |  |  |  |  |  | 5,000 |  |  |  | GPS | CENTRAL ADMIN. |
|  |  | - Conduct fire safety inspections at all public places | Selected premises |  |  |  |  | 20,000 |  |  |  |  | GNFS | CENTRAL ADMIN., NADMO |
|  | Corruption and Economic Crimes | - Support all activities of the Audit unit including audit committees | District Assembly |  |  |  |  | 40,000 |  |  |  |  | Internal Audit | External Audit |
|  |  | - Ensure that all HODs complete the Assets Declaration Form | District Assembly |  |  |  |  |  | 5,000 |  |  |  | CENTRAL ADMIN. |  |
|  | Law and Order | - Lobby for the posting of more Police Personnel into the district | District Assembly |  |  |  |  |  | 20,000 |  |  |  | DISEC | GPS |
|  |  | - Support the Police Service, fire service, ambulance service, immigration, BNI | District Assembly |  |  |  |  | 30,000 | 5,000 |  |  |  | DISEC | All security agencies |
|  |  | - Organize DISEC Meetings | District Wide |  |  |  |  |  | 60,000.00 |  |  |  | Central Admin | CENTRAL ADMIN. |
| Democracy, Governance and Public Accountability | Civil Society and Civic Engagement | - Collaborate with NGO to implement the Youth inclusive development programme | District Assembly |  |  |  |  |  | 4,000 | 2,500 |  |  | DPU | NGO |
|  |  | - Attend Nzema Maanle TC Meetings to engage TAs on the works of the Assembly | Ampain |  |  |  |  |  | 5,500 |  |  |  | DPU | CENTRAL ADMIN. |
|  |  | - Support Religious activities | District Wide |  |  |  |  | 21,800 |  |  |  |  | CENTRAL ADMIN. |  |
|  |  | - Collaborate with Youth Bridge to implement youth involvement programme | District Wide |  |  |  |  |  | 10,200 |  |  |  | DPU | CENTRAL ADMIN. |
|  | Culture | - Organize story telling competition in Nzema and Fanti and cultural festivals for basic schools | Selected Schools |  |  |  |  | 12,000 |  |  |  |  | GES | CENTRAL ADMIN. |
|  |  | Goal 5: Mainstream Emergency Planning and Preparedness Into Ghana’s Development Planning Agenda At All Levels To Respond To Potential Internal And External Threats (Including Covid-19 |  |  |  |  |  |  |  |  |  |  |  |  |
| EMERGENCY PLANNING AND RESPONSE (INCLUDING COVID-19 RECOVERY PLAN) | Hydrometeological Threats | - Organize community sensitizations on disaster prevention | District Wide |  |  |  |  | 12,500 |  |  |  |  | NADMO | CENTRAL ADMIN., NCCE |
|  |  | - Organize pests and insect infection sensitization campaign in communities | District Wide |  |  |  |  |  | 6,000 | 4,500 |  |  | NADMO | MOFA, NCCE |
|  |  | - Formation of Disaster Risk Reduction clubs in schools and communities | Selected Schools |  |  |  |  |  | 8,000 |  |  |  | NADMO | GES, CENTRAL ADMIN. |
|  |  | - Organize DRR training programmes at zonal levels | District Wide |  |  |  |  |  | 2,000 | 3,000 |  |  | NADMO | GNFS, CENTRAL ADMIN. |
|  |  | - Supply stationery and logistics to NADMO | District Assembly |  |  |  |  | 8,000 |  |  |  |  | CENTRAL ADMIN. | REG/NAT NADMO |
|  |  | - Train Area Council Members and Traditional Authorities on impact of sand winning and galamsey on the environment | District Wide |  |  |  |  |  | 16,000 |  |  |  | NADMO | CENTRAL ADMIN., NCCE |
| EMERGENCY PLANNING AND RESPONSE (INCLUDING COVID-19 RECOVERY PLAN) | Biological Threats | - Undertake surveillance, monitoring and evaluation of Health threats and epidemics and pandemics | District Wide |  |  |  |  |  | 10,000 |  |  |  | DHD | NCCE |
|  | Anthropogenic Threats | - Support National Ambulance Service | District Wide |  |  |  |  |  | 15,000 |  |  |  | GHS | CENTRAL ADMIN. |
|  |  | - Intensify monitoring at Filling Stations to ensure adherence to Standard Operating Procedures. | District Wide |  |  |  |  |  | 6,000 |  |  |  | GNFS | Security agencies |
|  |  | - Establish a well-resourced Emergency Centre | District Wide |  |  |  |  |  | 50,000 | 10,000 |  |  | CENTRAL ADMIN. | Private Sector/GHS |
|  | Security | - Organize Annual ADR week Celebration | District Wide |  |  |  |  |  | 6,000 |  |  |  | CENTRAL ADMIN. |  |
|  |  | - Support Police and other Security Forces | District Wide |  |  |  |  |  | 6,000 |  |  |  | CENTRAL ADMIN. | NGO |
|  |  | - Create awareness on the consequences of ethnic and chieftaincy conflicts | District Wide |  |  |  |  |  |  | 4,500 |  |  | NCCE | CENTRAL ADMIN., ETC |
| EMERGENCY PLANNING AND RESPONSE (INCLUDING COVID-19 RECOVERY PLAN) | Covid-19 Response | - Conduct sensitization on covid-19 Prepare and implement a covid-19 recovery Plan | District Wide |  |  |  |  |  | 6,000 |  |  |  | DHD | NCCE |
|  |  | - Support Public Health Emergency Management Committee | District Wide |  |  |  |  | 10,000 | 4,800 |  |  |  | CENTRAL ADMIN. | DHD |
|  |  | - Vaccinate 50,000 people against covid-19 | District Wide |  |  |  |  |  | 35,000 |  |  |  | DHD | CENTRAL ADMIN. |
|  |  | Goal 6: Improve Delivery of Development Outcomes at all Levels |  |  |  |  |  |  |  |  |  |  |  |  |
| Implementation, Coordination, Monitoring And Evaluation | Implementation and Coordination | - Organize quarterly DPCU Meetings | District Assembly |  |  |  |  | 15,000 | 5,000 |  |  |  | Dev't Planning | HODs |
|  |  | - Prepare quarterly and Annual Progress Reports | District Assembly |  |  |  |  | 10,000 |  | 3,000 |  |  | Dev't Planning | HODs |
|  |  | - Organize Capacity Building programme for DPCU members and HODs | District Assembly |  |  |  |  | 6,000 | 2,500 |  |  |  | Dev't Planning | HODs |
|  | Monitoring and Evaluation | - Organize quarterly Participatory Project Monitoring | District Assembly |  |  |  |  | 120,000 |  |  |  |  | Dev't Planning | HODs, CENTRAL ADMIN. |
|  |  | - Conduct mid-term review of 2022 AAP | District Assembly |  |  |  |  | 5,000 |  | 2,500 |  |  | Dev't Planning | HODs, CENTRAL ADMIN. |
|  |  | - Organize Quarterly M&E Review Meetings | District Assembly |  |  |  |  | 6,000 | 2,000 |  |  |  | Dev't Planning | HODs |
| Production And Utilisation Of Statistics | Data-Based Planning and Budgeting | - Establish District Statistical Working Group and train Field Officers | District Assembly |  |  |  |  | 2,000 | 2,000 |  |  |  | Statistical Dept. | HODs |
|  |  | - Establish and update Central Database for Planning and Budgeting | District Assembly |  |  |  |  | 10,000 |  |  |  |  | Statistical Dept. | HODs |
|  |  | - Support the GSS to collect population data | District wide |  |  |  |  | 30,000 |  |  |  |  | Statistical Dept. | CENTRAL ADMIN. |
|  |  | - Conduct Monthly Market Survey | District Assembly |  |  |  |  | 5,000 | 2,500 |  |  |  | Statistical Dept. | HODs |
|  |  | - Disseminate statistical Data and projections with Relevant Units, Departments and Agencies in the District. | District Assembly |  |  |  |  | 10,000 |  | 5,000 |  |  | Statistical Dept. | HODs |

Table 5. 1: 2022 Annual Action Plan

Table 5. 2. 2023 Annual Action Plan

| Programmes |  | Sub-programmes | Projects/activities |  | Location | Time Frame |  |  |  |  | Cost |  |  |  | Prog status |  |  | Implementing Dep'ts |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | 1 | 2 | 3 | 4 | GoG |  | IGF | Others | New |  | Old | Lead |  | Coll. |  |
|  |  |  | Goal 1: Build a Prosperous Society |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ECONOMIC DEVELOPMENT |  | Local and Economic Development | - Support 1000 local businesses with training and funding |  | District Wide |  |  |  |  |  |  | 30,000 |  |  |  |  | GEA |  | CENTRAL ADMIN. |  |
|  |  |  | - Completion of 2No market and construction of 2No market. |  | Nkroful Aiyinase, Basake, Sanzule |  |  |  |  | 1,580,000.00 |  |  |  |  |  |  | Works Dep't |  | CENTRAL ADMIN. |  |
|  |  |  | - Create industrial village |  | Ampain |  |  |  |  | 450,000 |  |  | 150,000 |  |  |  | CENTRAL ADMIN. |  | GEA/NBSSI |  |
|  |  |  | - Establish a ceramics factory |  | Teleku Bokazo |  |  |  |  | 500,000 |  | 50,00 | 1,500.000 |  |  |  | CENTRAL ADMIN. |  | GFZB |  |
|  |  |  | - Registration and training of local businesses. |  | District Wide |  |  |  |  |  |  | 5,000 |  |  |  |  | GEA |  | RGD |  |
|  |  |  | - Create a marketing platform for sellers and buyers of agro produce |  | District Wide |  |  |  |  |  |  | 10,000 |  |  |  |  | ENI/ GEA |  | Agri Dept/ENI |  |
|  |  |  | - Establish agro-processing Centres in rural communities |  | Aiyinasi North |  |  |  |  | 5,000 |  | 9,000 |  |  |  |  | Agri Dept. |  | CENTRAL ADMIN. |  |
|  |  |  | - Train 50 forest fringe community members in bee keeping, snail and grass cutter rearing |  | District wide |  |  |  |  |  |  | 5,000.00 | 10,000.00 |  |  |  | GEA |  | MOFA, CENTRAL ADMIN. |  |
|  |  |  | - Prepare and implement Local Economic Development (LED) Plan |  | District wide |  |  |  |  |  |  | 7,500.00 | 7,500 |  |  |  | GEA |  | CENTRAL ADMIN. |  |
|  |  |  | - Organize annual Business Expo |  | District wide |  |  |  |  |  |  | 30,000 | 45,000 |  |  |  | GEA |  | Agri Dept, Private Sector HODs |  |
|  |  | Agricultural and Rural Development | - Collaborate with private sector to establish a commercial rice farm |  | Nkroful |  |  |  |  |  |  | 25,000 | 50,000 |  |  |  | Agri Dept. |  | Private Sector |  |
|  |  |  | - Establish youth training centre |  | Nkroful |  |  |  |  |  |  | 100,000 |  |  |  |  | YEA |  | GEA, WORKS |  |
|  |  |  | - Support the Implementation of the EDGE Project |  | Menzezor |  |  |  |  |  |  |  | 1,900,000.00 |  |  |  | ENI |  | MOFA/CENTRAL ADMIN. |  |
|  |  |  | - Establish and update database on all farmers in the district |  | District Wide |  |  |  |  | 4,100 |  |  |  |  |  |  | Agri Dept |  | CENTRAL ADMIN./Statistics |  |
|  |  |  | - Advanced E-Extension and sensitization activities (study tour, malaria, COVID 19, child labour, HIV, pest and infections) |  | Menzezor, District Wide |  |  |  |  | 4.800 |  | 2,000 |  |  |  |  | Agri Dept |  | Works Dep't, CENTRAL ADMIN./ NCCE/GHS |  |
|  |  |  | - Train 500 and equip 200 youth in modern agriculture and agro-business |  | District Wide |  |  |  |  |  |  | 5,000 | 10,000 |  |  |  | Agri Dept |  | Agri Dept. |  |
|  |  |  | - Organize District Level Farmers Day Celebration |  | Selected Community |  |  |  |  | 50,000 |  |  | 100,000 |  |  |  | Agri Dept |  | DPO, CENTRAL ADMIN. |  |
|  |  |  | - Conduct yield studies on selected crops (rice, maize, cassava and plantain) |  | District Wide |  |  |  |  |  |  | 5,375 | 5,200 |  |  |  | Agri Dept. |  | MOFA |  |
| ECONOMIC DEVELOPMENT |  | Agricultural and Rural Development | - Collaborate with forestry commission to plant and nature 5,000 trees |  | District wide |  |  |  |  | 5000.00 |  |  |  |  |  |  | Forestry |  | Agric Dept |  |
|  |  |  | - Early warning systems and emergency preparedness for livestock and crop production. (small ruminant, COVID,PPE and FAW) |  | District wide |  |  |  |  | 5,810.00 |  |  |  |  |  |  | Agric Dept |  | CENTRAL ADMIN./NADMO |  |
|  |  |  | - Support the distribution of 10,000 (PERD) rubber seedling and 50,000 oil palm seedling by CSIR and MDF. |  | District wide |  |  |  |  |  |  | 21,500 |  |  |  |  | Agric Dept |  | CENTRAL ADMIN. |  |
|  |  |  | - Organise capacity building training for staffs ( AEAs, DDOs) |  |  |  |  |  |  |  |  | 15,000 | 3,000 |  |  |  | Agric Dept |  | CENTRAL ADMIN. |  |
|  |  |  | - Undertake M&E of implemented activities |  |  |  |  |  |  |  |  | 10,000 | 15,180 |  |  |  | Agric Dept |  | CENTRAL ADMIN. |  |
|  |  |  | - Train 20 women farmers and 5 AEAs on local food utilization |  |  |  |  |  |  | 3,950.00 |  |  |  |  |  |  | Agric Dept |  | CENTRAL ADMIN. |  |
|  |  |  | - Showcase to 20 women farmers the establishment of home gardens |  |  |  |  |  |  | 3,230 |  |  |  |  |  |  | Agric Dept |  | CENTRAL ADMIN. |  |
| ECONOMIC DEVELOPMENT |  | Agricultural and Rural Development | - Train 10 farmers (5 males and 5 females) on safe use and handling of Agro-Chemicals by the end of October 2022. |  |  |  |  |  |  | 2,790 |  |  |  |  |  |  | Agric Dept |  | CENTRAL ADMIN. |  |
|  |  |  | - Support the District Chamber of Agriculture, Commerce and Technology (Training for DCAT officers) |  | District Assembly |  |  |  |  |  |  | 5,000 | 5,000 |  |  |  | Agri Dept |  | CENTRAL ADMIN. |  |
|  |  |  | - Organize /Participate in meeting (RELC and Others) |  | District Assembly |  |  |  |  |  |  | 1,500 | 3,364 |  |  |  | Agri Dept |  | CENTRAL ADMIN. |  |
|  |  | Tourism and creative Arts development | - Promotion of drama, poetry festive and cultural activities (kundum festival) |  | District wide |  |  |  |  |  |  | 25,000 | 10,000 |  |  |  | Culture Unit |  | CENTRAL ADMIN. |  |
|  |  |  | - Development of the Baku crocodile pond |  | Baku |  |  |  |  |  |  | 100,000.00 | 200,000.00 |  |  |  | CENTRAL ADMIN. |  | GTDA |  |
|  |  |  | - Form 10 tourism clubs in basic and Senior High Schools |  | Selected Schools |  |  |  |  |  |  | 2,500 | 1,500 |  |  |  | GES |  | Culture/ CENTRAL ADMIN. |  |
|  |  |  | - Rehabilitation of Kwame Nkrumah Motel/Mausoleum |  | Nkroful |  |  |  |  |  |  | 330,000 |  |  |  |  | Works |  | CENTRAL ADMIN. |  |
|  |  |  | Goal 2: Create Opportunities for All |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| EDUCATION AND TRAINING |  | Pre-Tertiary Education | - Support STMIE programme |  | District wide |  |  |  |  | 3,625 |  | 3,000 |  |  |  |  | GES |  | CENTRAL ADMIN. |  |
|  |  |  | - Completion of 3No. and Construction of 1No. 6-unit classroom block |  | Esiama SDA, Anwia(O), Ngabawie(O), Domeabra |  |  |  |  | 1,110,000.00 |  | 169,500 |  |  |  |  | CENTRAL ADMIN. |  | GES |  |
|  |  |  | - Renovate 2No. Basic/primary school buildings |  | Aluku and Ankobra |  |  |  |  | 50,000.00 |  | 100,000.00 |  |  |  |  | CENTRAL ADMIN. |  | GES |  |
|  |  |  | - Construction of 50 meters walkway for Kikam SDA basic school |  | Kikam |  |  |  |  | 30,000.00 |  |  |  |  |  |  | CENTRAL ADMIN. |  | GES |  |
|  |  |  | - Completion of 7No. 3-unit classroom blocks and construction of 1No 3-unit classroom block |  | Aiyinase Nyamebekyere, Basake, Akropong, Awiebo, Awiaso, Salman, Nvelesolo Asomase (N) |  |  |  |  | 616,223.9 |  |  | 465,196.79 |  |  |  | CENTRAL ADMIN. |  | GES |  |
|  |  |  | - Construction of assembly hall at UBAISH |  | Kangbunli |  |  |  |  | 3,000,000 |  |  | 50,000 |  |  |  | CENTRAL ADMIN. |  | GES |  |
|  |  |  | - Completion 2No. KG and construction of 1No KG block |  | Ankobra, Teleku Bokazu, Kotokuom(N) |  |  |  |  | 500,000 |  | 315,368.34 |  |  |  |  | CENTRAL ADMIN. |  | GES |  |
|  |  |  | - Construction of 1No. 4-unit teachers quarters |  | Adubrim, Awiebo |  |  |  |  | 40,000 |  | 20,000 | 50,000 |  |  |  | CENTRAL ADMIN. |  | GES |  |
|  |  |  | - Completion of Assembly Hall for Esiama Sec-Tec |  | Esiama |  |  |  |  | 412,000 |  | 47,500 |  |  |  |  | CENTRAL ADMIN. |  | GES |  |
|  |  |  | - Support to organize inter-school sports Competitions |  | District Wide |  |  |  |  |  |  | 10,000.00 |  |  |  |  | CENTRAL ADMIN. |  | GES |  |
| EDUCATION AND TRAINING |  | Pre-Tertiary Education | - Provide items for "my first Central Admin.y at school" celebrations and institute Best Teacher Award especially in deprived schools |  | District Wide |  |  |  |  | 20,000 |  | 18,500 | 15,000.00 |  |  |  | Central Admin. |  | GES/Private Schools |  |
|  |  |  | - Supply of classroom furniture/Uniforms to schools |  | Some Selected Schools |  |  |  |  | 90,000 |  | 50,000 |  |  |  |  | Works /Procurement |  | GES |  |
|  |  |  | - facilitate the completion of GETFUND,MSDI, GNPC project. |  | NASS, Esiama Sec Tech, KIMTECH, charlotte Dolphine training institute |  |  |  |  | 200,000 |  |  | 700,000 |  |  |  | Central Admin. |  | GES |  |
|  |  |  | - Support needy but brilliant students and Award scholarship to PWDs in higher education |  | District wide |  |  |  |  |  |  | 15,000 | 7,000 |  |  |  | SWCD |  | GES |  |
|  |  |  | - Facilitate the provision of resource persons such as sign language interpreters and braille transcribers at all levels |  | District wide |  |  |  |  |  |  | 4,000 |  |  |  |  | SWCD |  | PWD |  |
|  |  |  | - Promote the re-entry of dropouts and adolescent mothers back to school after childbirth |  | Predominant Communities |  |  |  |  |  |  | 5,000 |  |  |  |  | SWCD |  | GES |  |
| DUCATION AND TRAINING |  | Pre-Tertiary Education | - Completion/Construct ICT Centres |  | Aiyinasi, Asanta, |  |  |  |  | 200,000.00 |  | 100,000.00 |  |  |  |  | Works Dep't |  | GES |  |
|  |  |  | - Procure and supply 100 computers and accessories to basic schools and senior high schools |  | All SHS and basic schools in the District |  |  |  |  |  |  | 20,000 | 27,000 |  |  |  | CENTRAL ADMIN. |  | GES/Pivate Sector |  |
|  |  |  | - Conduct induction workshop for newly trained teachers |  | District wide |  |  |  |  | 15,000 |  |  |  |  |  |  | GES |  | CENTRAL ADMIN./HRM |  |
|  |  |  | - Conduct SPAM in basic schools and Organize yearly mock exams for JHS students |  | District wide |  |  |  |  | 6,500 |  | 10,000.00 |  |  |  |  | GES |  | CENTRAL ADMIN. |  |
|  |  |  | - Support regular inspection and monitoring of schools, SMCs and PTAs |  | District wide |  |  |  |  | 2,000 |  | 4,500 |  |  |  |  | GES |  | CENTRAL ADMIN. |  |
|  |  |  | - Strengthen non-formal education, form clubs in 4 communities to establish a rice farm, piggery, poultry and fishponds |  | Asanta Kotokro, Sanzule, Aiyinse |  |  |  |  |  |  | 17,100 | 4,125 |  |  |  | GES |  | Agric Dept, Private Sector |  |
| HEALTH AND HEALTH SERVICE DELIVERY |  | Primary Healthcare Delivery | - Construct a District Hospital at Nkroful |  | Nkroful |  |  |  |  | 14,000,000 |  |  |  |  |  |  | GHS |  | CENTRAL ADMIN. |  |
|  |  |  | - Provision of medical supplies to CHPS Compounds (BP apparatus, weighing scale and motor bikes) |  | All facilities |  |  |  |  |  |  | 6,000 | 7,500 |  |  |  | CENTRAL ADMIN. |  | GHS |  |
|  |  |  | - Completion and construction of 2No. CHPS Compounds |  | Tandan, Matukwa, New Adiembra, Ebi |  |  |  |  | 600,000.00 |  |  |  |  |  |  | CENTRAL ADMIN. |  | GHS |  |
|  |  |  | - Complete the upgrading and expansion works at St. Martin De Porres Hospital, Eikwe |  | Eikwe |  |  |  |  |  |  |  | 9,000,000 |  |  |  | CENTRAL ADMIN. |  | GNPC |  |
|  |  |  | - Complete the construction of NHIS Office at Nkroful |  | Nkroful |  |  |  |  | 500,000 |  |  |  |  |  |  | CENTRAL ADMIN. |  | NHIS |  |
|  |  |  | - Conduct public health education and organize campaigns on mental health |  | District Wide |  |  |  |  | 1,500 |  | 8,000 |  |  |  |  | GHS |  | SWCD,Religious groups |  |
|  |  |  | - Support to organize capacity building programmes for Health Staff for effective monitoring and evaluation |  | District Wide |  |  |  |  | 15,500 |  |  | 22,000 |  |  |  | GHS |  | NGO |  |
| HEALTH AND HEALTH SERVICE DELIVERY |  | Primary Healthcare Delivery | - Distribute 2500 insecticide treated mosquito nets |  | District Wide |  |  |  |  | 2,250 |  | 8,500 |  |  |  |  | GHS |  | CENTRAL ADMIN. |  |
|  |  |  | - Promote ante/post-natal services and organize district health wide health screening activities. |  | District Wide |  |  |  |  | 7,500 |  |  | 4,000 |  |  |  | GHS |  | CENTRAL ADMIN. |  |
|  |  |  | - Continue the administration of vaccines under the NID programme |  | District Wide |  |  |  |  | 3,000 |  | 6,000 | 2,000 |  |  |  | GHS |  | CENTRAL ADMIN. |  |
|  |  |  | - Organize District wide Health Screening |  | District Wide |  |  |  |  |  |  | 12,000 | 33,000 |  |  |  | GHS |  | NGOs |  |
|  |  |  | - Embark on quarterly regenerative health and nutrition outreach programmes |  | District Wide |  |  |  |  | 12,125 |  | 5,000 |  |  |  |  | GHS |  | CENTRAL ADMIN. |  |
| HEALTH AND HEALTH SERVICE DELIVERY |  | HIV, AIDS/STIs and other infections | - Intensify comprehensive education on HIV/AIDS and STIs, including reduction of stigmatisation |  | District wide |  |  |  |  | 6,625 |  |  | 6,250 |  |  |  | GHS |  | NGOs |  |
|  |  |  | - Organize quarterly HIV/AIDS Committee Meetings and world AIDS day. |  | Nkroful |  |  |  |  | 11,000.00 |  |  |  |  |  |  | DAC |  | GHS |  |
|  |  |  | - Counsel and test for HIV in all pregnant women |  | District wide |  |  |  |  | 7,575 |  |  | 1,020 |  |  |  | GHS |  | CENTRAL ADMIN. |  |
|  |  |  | - Organize HIV/AIDS and TB campaigns in schools |  | District wide |  |  |  |  | 7,500 |  |  |  |  |  |  | GHS |  | GES |  |
|  |  | Population Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | - Ensure registration of all birth and death in the district |  | District wide |  |  |  |  |  |  | 1,000 |  |  |  |  | Birth & death Dept. |  | CENTRAL ADMIN. |  |
|  |  |  | - Organize quarterly sensitization programmes on teenage pregnancy and child marriage |  | District wide |  |  |  |  |  |  | 19,100 |  |  |  |  | SWCD |  | CENTRAL ADMIN./NCCE |  |
|  |  |  | - Provide support for family planning activities |  | District wide |  |  |  |  | 5,000 |  |  | 2,000 |  |  |  | GHS |  | CENTRAL ADMIN. |  |
| HEALTH AND HEALTH SERVICE DELIVERY |  | Food and Nutrition | - Organize food and nutrition campaign in schools and health centres and on radio |  | District wide |  |  |  |  |  |  | 13,000 | 2,000 |  |  |  | GHS/EHSU |  | CENTRAL ADMIN. |  |
|  |  |  | - Monitor the school feeding programme to ensure quality and well balanced diet is served |  | District wide |  |  |  |  | 10000 |  | 3000 |  |  |  |  | Central Admin |  | CENTRAL ADMIN. |  |
| WATER AND ENVIRONMENTAL SANITATION |  | Water Supply, Waste Management and Environmental Sanitation | - Drilling of 10No. Disability friendly Mechanized boreholes |  | Anokye, Baku, Asanta. Ngalakyi Baku, Asomase, Aluku, Ankobra, Ewe community, health facilities |  |  |  |  | 250,000 |  |  | 10,000 |  |  |  | CENTRAL ADMIN. |  | DWST |  |
|  |  |  | - Completion, Construction/ Extension of water supply for selected communities |  | Nkroful, Kamgbuli,Asomase, Teleku Bokazo new and old Bakanta, Asanta. |  |  |  |  | 200,000 |  | 100,000 |  |  |  |  | CENTRAL ADMIN. |  | DWST |  |
|  |  |  | - Completion of 7No. Boreholes with Hand pumping Machines |  | Bobrama,Baku Nvuma, Kamgbunli,Beposo,At ababo and Pelepolena |  |  |  |  |  |  | 200,000.00 |  |  |  |  | CENTRAL ADMIN. |  | DWST |  |
|  |  |  | - Siting, Drilling and Developing of 4no. Boreholes and Construction of Aprons and Drains with soakway Pit and Installation of hand pumping Machines |  | Asastre -Nyamebyere, Ngabawie, Agbeyeye and Aluku |  |  |  |  | 400,000 |  | 200,000 |  |  |  |  | CENTRAL ADMIN. |  | DWST |  |
| WATER AND ENVIRONMENTAL SANITATION |  | Water Supply, Waste Management and Environmental Sanitation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | - Prepare, and implement the District Water and Sanitation Plan |  | District Assembly |  |  |  |  |  |  | 8,500 |  |  |  |  | DWST |  | CENTRAL ADMIN. |  |
|  |  |  | - Form and train 10No. WATSan Committees |  | Selected Communities |  |  |  |  | 15,000 |  |  |  |  |  |  | DWST |  | CENTRAL ADMIN. |  |
|  |  |  | - Completion of 3 No. and Construction of 1No. gender-friendly and disability friendly institutional latrines |  | Basake (O), Asanta(O) Nvenlosolo (O), Bomaokpole |  |  |  |  | 400,000 |  |  |  |  |  |  | Works Dept. |  | EHSU |  |
|  |  |  | - Completion of Toilets |  | Tandan, Awiebo, Aiyinase |  |  |  |  | 150,000.00 |  |  |  |  |  |  | EHSU |  | CENTRAL ADMIN. |  |
|  |  |  | - Implement the CLTS programme and intensify environmental health education campaigns |  | Social gatherings, schools and helath facilities |  |  |  |  | 25,000 |  |  |  |  |  |  | EHSU |  | CENTRAL ADMIN. |  |
|  |  |  | - Construction of slaughter slabs at market places |  | Aiyinasi, Esiama, |  |  |  |  | 200,000 |  |  |  |  |  |  | CENTRAL ADMIN. |  | EHSU |  |
|  |  |  | - Conduct screening of food vendors |  | District wide |  |  |  |  | 7,500 |  | 5,000 |  |  |  |  | EHSU |  | GHS, CENTRAL ADMIN. |  |
|  |  |  | - Support the Conveyance/ waste management activities |  | District wide |  |  |  |  | 320000 |  |  |  |  |  |  | EHSU |  | CENTRAL ADMIN. |  |
|  |  |  | - Monitor waste collection by zoomlion |  | Market Places |  |  |  |  |  |  | 10,000 |  |  |  |  | EHSU |  | CENTRAL ADMIN. |  |
|  |  |  | - Procure a cespit emptier |  | District Assembly |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| GENDER, CHILDREN AND SOCIAL PROTECTION |  | Child Protection and Youth Development | - Mobilize and sensitize 10 communities on parental responsibilities |  | District Wide |  |  |  |  |  |  | 25,000 |  |  |  |  | CENTRAL ADMIN. |  | GES, SWCD, NCCE |  |
|  |  |  | - Enforce child right and Gender related Bye laws |  | District Wide |  |  |  |  |  |  | 25,000 |  |  |  |  | SWCD |  | GES, NCCE,DA, Police etc. |  |
|  |  |  | - Monitor day Care Centres and orphanages within the district |  | District Wide |  |  |  |  | 5,000 |  | 2,000 |  |  |  |  | SWCD |  | CENTRAL ADMIN. |  |
|  |  |  | - organize sensitization programmes on child protection issues |  | District Wide |  |  |  |  |  |  | 13,000 UNICEF |  |  |  |  | SWCD |  | Central Admin, NCCE, LABOUR DEP'T, NCCE |  |
|  |  |  | - Institute Child Protection Committees in 20 Communities |  | District wide |  |  |  |  |  |  | 5,000 UNICEF |  |  |  |  | SWCD |  | CENTRAL ADMIN. |  |
|  |  |  | - Settle child maintenance cases Organize community engagements and behavioural change campaigns to promote positive parenting |  | District wide |  |  |  |  |  |  | 5,000 UNICEF |  |  |  |  | SWCD |  | UNICEF |  |
|  |  |  | - Organize girls empowerment summits in Senior High Schools and create a pool of potential female leaders |  | District wide |  |  |  |  |  |  | 17,000.00 |  |  |  |  | SWCD |  | GES |  |
|  |  |  | - Establish adolescent clubs in schools and communities |  | District wide |  |  |  |  |  |  | 3,500 | 3,000 |  |  |  | SWCD |  | Gender Desk |  |
|  |  | Support for the Aged | - Create a database on the aged and support the Ellembelle Elderly Care Centre with Food Items |  | Ampain |  |  |  |  | 8,000 |  |  | 2,400 |  |  |  | DPU |  | CENTRAL ADMIN. |  |
|  |  | Women empowerment | - Organize quarterly sensitization Campaigns on gender-based violence and other harmful cultural practices |  | District Wide |  |  |  |  | 10,000 |  |  | 3,500 |  |  |  | SWCD/DPCU |  | CENTRAL ADMIN. |  |
|  |  |  | - Organize skills training for 1000 women |  | District Wide |  |  |  |  |  |  | 20,000 | 5,000 |  |  |  | SWCD |  | CENTRAL ADMIN., GEA |  |
|  |  | Social Protection | - Mobilize indigenes and vulnerable people for NHIS registration |  | District Wide |  |  |  |  | 10,000 |  |  |  |  |  |  | SWCD |  | NHIS, CENTRAL ADMIN. |  |
|  |  |  | - Construct 5No. Disability friendly Community parks |  | District wide |  |  |  |  | 300,000 |  |  |  |  |  |  | Works Dept. |  | Sport Committee |  |
|  |  |  | - Support People With Disabilities (PWDs) with training skills, items, cash, school fees medical bills and start-up capital. |  | District Wide |  |  |  |  | 200,000.00 |  |  |  |  |  |  | SWCD |  | GEA, CENTRAL ADMIN. |  |
|  |  |  | - Monitor and support the Livelihood Empowerment Against Poverty (LEAP) programme |  | District wide |  |  |  |  | 10,000 |  |  |  |  |  |  | SWCD |  | CENTRAL ADMIN. |  |
|  |  |  | Goal 3: Safeguard the Natural Environment and Ensure A Resiliant Built Environment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| NATURAL RESOURCE MANAGEMENT |  | Mineral Extraction | - Arrest and prosecute illegal, sand winners, miners, lumbers |  | District Wide |  |  |  |  | 30,000 |  | 30,000.00 |  |  |  |  | Security Agencies |  | EHSU,CENTRAL ADMIN. |  |
|  |  |  | - Establish a community mining scheme in 3 communities. |  | Salma, Teleku Bokazo, Nkroful |  |  |  |  |  |  | 6,000 | 3,000 |  |  |  | Works Dept. |  | CENTRAL ADMIN. |  |
|  |  |  | - Ensure the reclamation of degraded land after mining |  | Mining communities |  |  |  |  |  |  | 100,000 | 100,000 |  |  |  | PPD |  | CENTRAL ADMIN. |  |
|  |  | Coastal and Marine Erosion | - Revive conservation committee groups and build women capacity in conservation |  | District Assembly |  |  |  |  | 5,000 |  |  |  |  |  |  | DPU |  | CENTRAL ADMIN. |  |
|  |  | Deforestation, Desertification and Soil Erosion | - Develop landfill site into a modern engineered site |  | Ala Bokazo |  |  |  |  | 300,000 |  |  |  |  |  |  | EHSU |  | PPD, EPA |  |
|  |  |  | - Protect natural reserves (mangroves and forest) and recreation areas from encroachment |  | District Wide |  |  |  |  | 26,500 |  | 15,000.00 |  |  |  |  | Forestry |  | Works/NADMO/PPD |  |
| CLIMATE CHANGE AND DISASTER RISK REDUCTION |  | Climate Variability and Change |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | - Organize Capacity Building Training in Climate Change for DPCU/HODS Members |  | District Assembly |  |  |  |  |  |  |  | 6,500 |  |  |  | Agri Dept. |  | CENTRAL ADMIN. |  |
|  |  |  | - Train farmers on climate smart agriculture technologies |  | District wide |  |  |  |  | 5,000 |  |  |  |  |  |  | Agric .Dept. |  | MOFA |  |
|  |  |  | - Complete the construction of town roads |  | Esiama- Nkrofu- Bokazo Eikwe, Sanzule, Baku, Ngalekyi, Bobrama, Aiyinase South, Aiyinase North, and others |  |  |  |  | 2,000,000 |  |  |  |  |  |  | GHA, Dep't of Feeder Roads |  | CENTRAL ADMIN. |  |
|  |  |  | - Develop of Modern lorry parks and stores |  | Aiyinase,Esiama |  |  |  |  |  |  | 100,000 |  |  |  |  | GHA |  | CENTRAL ADMIN. |  |
|  |  |  | - Support road safety activities in the District |  | District Wide |  |  |  |  | 120,000.00 |  |  |  |  |  |  | GHA |  | CENTRAL ADMIN. |  |
| CLIMATE CHANGE AND DISASTER RISK REDUCTION |  | Information Communication Technology | - Rehabilitate existing post offices |  | Aiyinase, Nkroful Esiama |  |  |  |  |  |  | 200,000 |  |  |  |  | Works dept |  | CENTRAL ADMIN. |  |
|  |  |  | - Renovation of ICT Centre at Aiyinase and Install Wi-Fi at the District Assembly Office |  | Aiyinase Nkroful |  |  |  |  | 64,500 |  | 54,200 |  |  |  |  | ICT Dept. |  | GIFEC |  |
|  |  | Human Settlements Development and Housing | - Organize technical and statutory planning committee meetings |  | District Assembly |  |  |  |  |  |  | 12,000 |  |  |  |  | PPD |  | HODs |  |
|  |  |  | - Preparation of local plans |  | Bomoakpole |  |  |  |  |  |  | 20,000 |  |  |  |  | PPD |  | CENTRAL ADMIN. |  |
|  |  |  | - Sensitization of the public on Land use planning and permitting |  | District Wide |  |  |  |  |  |  | 3,000 |  |  |  |  | PPD |  | Works Dep't, CENTRAL ADMIN. |  |
|  |  |  | - Organize joint inspections to check unauthorised developments |  | District Wide |  |  |  |  |  |  | 20,000.00 |  |  |  |  | PPD |  | Works Dep't, CENTRAL ADMIN. |  |
|  |  |  | - Construction of 5No. Community Centres |  | New Bakanta, Adurim, Aiyinasi North |  |  |  |  | 780,000 |  |  |  |  |  |  | CENTRAL ADMIN. |  | COCOBOD |  |
|  |  | Drainage and Flood Control | - Prepare and implement drainage plans for flood prone areas |  | District Assembly |  |  |  |  |  |  | 5,000 |  |  |  |  | PPD |  | Works Dep't, CENTRAL ADMIN. |  |
|  |  |  | - Construct and frequently desilt chocked drains |  | District Assembly |  |  |  |  | 200,000.00 |  | 20,000 |  |  |  |  | EHSU |  | PPD,WORKS,NADMO |  |
| CLIMATE CHANGE AND DISASTER RISK REDUCTION |  | Infrastructure Maintenance | - Organize capacity building training in inventory and asset management for selected staff |  | District Assembly |  |  |  |  |  |  | 7,000 |  |  |  |  | HR |  | CENTRAL ADMIN. |  |
|  |  |  | - Prepare operation and maintenance (O&M) Plan |  | District Assembly |  |  |  |  | 5,000 |  |  |  |  |  |  | Works Dep't |  | Dev't Planning Unit |  |
|  |  |  | - Undertake building inspections and ensure that all public buildings are disability friendly |  | District wide |  |  |  |  |  |  | 10,000 |  |  |  |  | Works Dep't |  | CENTRAL ADMIN. |  |
|  |  |  |  | Goal 4: Maintain a Stable, United and Safe Society |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| DEMOCRACY, GOVERNANCE AND PUBLIC ACCOUNTABILITY |  | Resource Mobilization and Expenditure Management | - Update economic/ Tourism data to improve revenue |  | District wide |  |  |  |  | 100,000.00 |  |  |  |  |  |  | Statistical Dept. |  | Revenue Unit,DPO, PPD, Budget |  |
|  |  |  | - Provide revenue collection and management logistics |  | District Assembly |  |  |  |  | 12,000 |  |  |  |  |  |  | Revenue Unit |  | GIZ, CENTRAL ADMIN. |  |
|  |  |  | - Organize public sensitization on revenue mobilization in market places and lorry stations |  | Aiyinase, Asasetre, Esiama, Teleku Bokazo |  |  |  |  |  |  | 7,500 |  |  |  |  | Revenue Unit |  | Budget/Finance, Works, PPA, NCCE |  |
|  |  |  | - Mount and update revenue performance and Accountability Bill Boards at the Various Area Councils |  | Esiama, Asasetre, Awiebo Basake, Aiyinase, Kikam, Nkroful, Atoabo |  |  |  |  | 22,000 |  |  |  |  |  |  | Fin. Dep't |  | CENTRAL ADMIN. |  |
|  |  |  | - Prepare and Implement a Revenue Improvement Action Plan and Concept note |  | District Assembly |  |  |  |  | 5,000.00 |  | 7,000 |  |  |  |  | DBU |  | DPO, Fin Dept |  |
| Democracy, Governance and Public Accountability |  | Local Government and Decentralization | - Completion of 2No, Furnishing/ Construction of 2No. Area Council Office |  | Esiama, Aiyinase, Asasetre, Nkroful |  |  |  |  | 500,000.00 |  | 500,000 .00 |  |  |  |  | CENTRAL ADMIN. |  | WORKS/DPO |  |
|  |  |  | - Support and build the capacity of women to contest for political positions |  | District Wide |  |  |  |  | 4,500 |  |  | 6,000 |  |  |  | NCCE |  | CENTRAL ADMIN. |  |
|  |  |  | - Organize all statutory meetings and celebration of National days |  | District Assembly |  |  |  |  | 90,000.00 |  | 50,000.00 | 40,000.oo |  |  |  | Central Admin |  |  |  |
|  |  |  | - Secure/furnish office accommodation for area councils |  | District Assembly |  |  |  |  | 100,000.00 |  |  |  |  |  |  | Planning |  | Finance, CENTRAL ADMIN. |  |
|  |  |  | - Coordinate the preparation of Community Action Plans |  | District Assembly |  |  |  |  | 10,000.00 |  |  |  |  |  |  | Dev't Planning/PP |  | HODs |  |
|  |  |  | - Review and prepare Annual Action Plans, Composite Budgets, Procurement plans |  | District Assembly |  |  |  |  | 50,000.00 |  |  |  |  |  |  | Planning, Budget Unit, Procurement |  | HODs |  |
|  |  |  | - Undertake Town Hall Meetings on AAPs, fee-fixing and composite annual budget |  | All Area Council Offices |  |  |  |  | 50,000 |  | 10,000.00 | 5,000 |  |  |  | Dev't Planning/Budget |  | HODs, CENTRAL ADMIN. |  |
| Democracy, Governance and Public Accountability |  | Local Government and Decentralization | - Administer comprehensive HRMIS and submit monthly returns to RCC |  | District Assembly |  |  |  |  |  |  | 4,000 |  |  |  |  | HR |  | HODs |  |
|  |  |  | - Organize capacity building training for revenue collectors and Area Council members on effective revenue mobilization |  | District Assembly |  |  |  |  |  |  | 40,000.00 |  |  |  |  | HR/DPU |  | NGO |  |
|  |  |  | - Organize capacity building training for all staff and Assembly members |  | District Assembly |  |  |  |  | 35,000 |  |  |  |  |  |  | HR |  | Fin. Dep't, HODs |  |
|  |  |  | - Procure office stationery, logistics, Vehicles and others |  | District Assembly |  |  |  |  | 600,000.00 |  |  |  |  |  |  | Procurement |  | CENTRAL ADMIN. |  |
|  |  |  | - Maintenance of Assembly Accommodation, vehicles, computers and other logistics |  | District Assembly |  |  |  |  | 100,000.00 |  | 100.000.00 |  |  |  |  | Procurement |  | Central Admin. |  |
| Democracy, Governance and Public Accountability |  | Human Security and Public Safety | - Construction of Police Station |  | Asomase |  |  |  |  |  |  | 350,000 |  |  |  |  | CENTRAL ADMIN. |  | GPS |  |
|  |  |  | - Form 4No. Neighbourhood watchdog committees |  | Selected Communities |  |  |  |  |  |  | 5,000 |  |  |  |  | GPS |  | CENTRAL ADMIN. |  |
|  |  |  | - Conduct fire safety inspections at all public places |  | Selected premises |  |  |  |  | 20,000 |  |  |  |  |  |  | GNFS |  | CENTRAL ADMIN., NADMO |  |
|  |  | Corruption and Economic Crimes | - Support all activities of the Audit unit including audit committees |  | District Assembly |  |  |  |  | 40,000 |  |  |  |  |  |  | Internal Audit |  | External Audit |  |
|  |  |  | - Ensure that all HODs complete the Assets Declaration Form |  | District Assembly |  |  |  |  |  |  | 5,000 |  |  |  |  | CENTRAL ADMIN. |  |  |  |
|  |  | Law and Order | - Lobby for the posting of more Police Personnel into the district |  | District Assembly |  |  |  |  |  |  | 20,000 |  |  |  |  | DISEC |  | GPS |  |
|  |  |  | - Support the Police Service, fire service, ambulance service, immigration, BNI |  | District Assembly |  |  |  |  | 30,000 |  | 5,000 |  |  |  |  | DISEC |  | All security agencies |  |
|  |  |  | - Organize DISEC Meetings |  | District Wide |  |  |  |  |  |  | 60,000.00 |  |  |  |  | Central Admin |  | CENTRAL ADMIN. |  |
| Democracy, Governance and Public Accountability |  | Civil Society and Civic Engagement | - Collaborate with NGO to implement the Youth inclusive development programme |  | District Assembly |  |  |  |  |  |  | 4,000 | 2,500 |  |  |  | DPU |  | NGO |  |
|  |  |  | - Attend Nzema Maanle TC Meetings to engage TAs on the works of the Assembly |  | Ampain |  |  |  |  |  |  | 5,500 |  |  |  |  | DPU |  | CENTRAL ADMIN. |  |
|  |  |  | - Support Religious activities |  | District Wide |  |  |  |  | 21,800 |  |  |  |  |  |  | CENTRAL ADMIN. |  |  |  |
|  |  |  | - Collaborate with Youth Bridge to implement youth involvement programme |  | District Wide |  |  |  |  |  |  | 10,200 |  |  |  |  | DPU |  | CENTRAL ADMIN. |  |
|  |  | Culture | - Organize story telling competition in Nzema and Fanti and cultural festivals for basic schools |  | Selected Schools |  |  |  |  | 12,000 |  |  |  |  |  |  | GES |  | CENTRAL ADMIN. |  |
|  |  |  | Goal 5: Mainstream Emergency Planning and Preparedness Into Ghana’s Development Planning Agenda At All Levels To Respond To Potential Internal And External Threats (Including Covid-19 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| EMERGENCY PLANNING AND RESPONSE (INCLUDING COVID-19 RECOVERY PLAN) |  | Hydrometeological Threats | - Organize community sensitizations on disaster prevention |  | District Wide |  |  |  |  | 12,500 |  |  |  |  |  |  | NADMO |  | CENTRAL ADMIN., NCCE |  |
|  |  |  | - Organize pests and insect infection sensitization campaign in communities |  | District Wide |  |  |  |  |  |  | 6,000 | 4,500 |  |  |  | NADMO |  | MOFA, NCCE |  |
|  |  |  | - Formation of Disaster Risk Reduction clubs in schools and communities |  | Selected Schools |  |  |  |  |  |  | 8,000 |  |  |  |  | NADMO |  | GES, CENTRAL ADMIN. |  |
|  |  |  | - Organize DRR training programmes at zonal levels |  | District Wide |  |  |  |  |  |  | 2,000 | 3,000 |  |  |  | NADMO |  | GNFS, CENTRAL ADMIN. |  |
|  |  |  | - Supply stationery and logistics to NADMO |  | District Assembly |  |  |  |  | 8,000 |  |  |  |  |  |  | CENTRAL ADMIN. |  | REG/NAT NADMO |  |
|  |  |  | - Train Area Council Members and Traditional Authorities on impact of sand winning and galamsey on the environment |  | District Wide |  |  |  |  |  |  | 16,000 |  |  |  |  | NADMO |  | CENTRAL ADMIN., NCCE |  |
| EMERGENCY PLANNING AND RESPONSE (INCLUDING COVID-19 RECOVERY PLAN) |  | Biological Threats | - Undertake surveillance, monitoring and evaluation of Health threats and epidemics and pandemics |  | District Wide |  |  |  |  |  |  | 10,000 |  |  |  |  | DHD |  | NCCE |  |
|  |  | Anthropogenic Threats | - Support National Ambulance Service |  | District Wide |  |  |  |  |  |  | 15,000 |  |  |  |  | GHS |  | CENTRAL ADMIN. |  |
|  |  |  | - Intensify monitoring at Filling Stations to ensure adherence to Standard Operating Procedures. |  | District Wide |  |  |  |  |  |  | 6,000 |  |  |  |  | GNFS |  | Security agencies |  |
|  |  |  | - Establish a well-resourced Emergency Centre |  | District Wide |  |  |  |  |  |  | 50,000 | 70,000 |  |  |  | CENTRAL ADMIN. |  | Private Sector/GHS |  |
|  |  | Security | - Organize Annual ADR week Celebration |  | District Wide |  |  |  |  |  |  | 6,000 |  |  |  |  | CENTRAL ADMIN. |  |  |  |
|  |  |  | - Create awareness on the consequences of ethnic and chieftaincy conflicts |  | District Wide |  |  |  |  |  |  |  | 4,500 |  |  |  | NCCE |  | CENTRAL ADMIN., ETC |  |
| EMERGENCY PLANNING AND RESPONSE (INCLUDING COVID-19 RECOVERY PLAN) |  | Covid-19 Response | - Conduct sensitization on pandemics and implement a recovery Plan |  | District Wide |  |  |  |  |  |  | 6,000 |  |  |  |  | DHD |  | NCCE |  |
|  |  |  | - Support Public Health Emergency Management Committee |  | District Wide |  |  |  |  | 10,000 |  | 4,800 |  |  |  |  | CENTRAL ADMIN. |  | DHD |  |
|  |  |  | - Vaccinate 50,000 people against covid-19 and other pandemics. |  | District Wide |  |  |  |  |  |  | 35,000 |  |  |  |  | DHD |  | CENTRAL ADMIN. |  |
|  |  |  | Goal 6: Improve Delivery of Development Outcomes at all Levels |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Implementation, Coordination, Monitoring And Evaluation |  | Implementation and Coordination | - Organize quarterly DPCU Meetings |  | District Assembly |  |  |  |  | 15,000 |  | 8,000 |  |  |  |  | Dev't Planning |  | HODs |  |
|  |  |  | - Prepare quarterly and Annual Progress Reports |  | District Assembly |  |  |  |  | 10,000 |  |  | 3,000 |  |  |  | Dev't Planning |  | HODs |  |
|  |  |  | - Organize Capacity Building programme for DPCU members and HODs |  | District Assembly |  |  |  |  | 6,000 |  | 2,500 |  |  |  |  | Dev't Planning |  | HODs |  |
|  |  | Monitoring and Evaluation | - Organize quarterly Participatory Project Monitoring |  | District Assembly |  |  |  |  | 120,000 |  |  |  |  |  |  | Dev't Planning |  | HODs, CENTRAL ADMIN. |  |
|  |  |  | - Organize Quarterly M&E/ AAP Review Meetings |  | District Assembly |  |  |  |  | 12,000 |  | 5,000 |  |  |  |  | Dev't Planning |  | HODs |  |
| Production And Utilisation Of Statistics |  | Data-Based Planning and Budgeting | - Establish District Statistical Working Group and train Field Officers |  | District Assembly |  |  |  |  | 2,000 |  | 2,000 |  |  |  |  | Statistical Dept. |  | HODs |  |
|  |  |  | - Establish and update Central Database for Planning and Budgeting |  | District Assembly |  |  |  |  | 10,000 |  |  |  |  |  |  | Statistical Dept. |  | HODs |  |
|  |  |  | - Support the GSS to collect population data |  | District wide |  |  |  |  | 30,000 |  |  |  |  |  |  | Statistical Dept. |  | CENTRAL ADMIN. |  |
|  |  |  | - Conduct Monthly Market Survey |  | District Assembly |  |  |  |  | 5,000 |  | 2,500 |  |  |  |  | Statistical Dept. |  | HODs |  |
|  |  |  | - Disseminate statistical Data and projections with Relevant Units, Departments and Agencies in the District. |  | District Assembly |  |  |  |  | 10,000 |  |  | 5,000 |  |  |  | Statistical Dept. |  | HODs |  |

Table 5. 2: 2024 Annual Action Plan

| Programmes |  | Sub-programmes |  | Projects/activities | Location | Time Frame |  |  |  | Cost |  |  | Prog Status |  | Implementing Dep'ts |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | 1 | 2 | 3 | 4 | GoG | IGF | Others | New | Old | Lead | Coll. |
|  |  |  | Goal 1: Build a Prosperous Society |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ECONOMIC DEVELOPMENT |  | Local and Economic Development |  | - Support 1000 local businesses with training and funding | District Wide |  |  |  |  |  | 30,000 |  |  |  | GEA | CENTRAL ADMIN. |
|  |  |  |  | - Completion of 4No market and construction of 2No market. | Nkroful Aiyinase, Basake, Sanzule, Atuabo, Eikwe |  |  |  |  | 2,000,000.00 |  |  |  |  | Works Dep't | CENTRAL ADMIN. |
|  |  |  |  | - Create industrial village | Ampain |  |  |  |  | 450,000 |  | 150,000 |  |  | CENTRAL ADMIN. | GEA/NBSSI |
|  |  |  |  | - Establish a ceramics factory | Teleku Bokazo |  |  |  |  | 500,000 | 50,00 | 1,500.000 |  |  | CENTRAL ADMIN. | GFZB |
|  |  |  |  | - Registration and training of local businesses. | District Wide |  |  |  |  |  | 5,000 |  |  |  | GEA | RGD |
|  |  |  |  | - Create a marketing platform for sellers and buyers of agro produce | District Wide |  |  |  |  |  | 10,000 |  |  |  | ENI/ GEA | Agri Dept/ENI |
|  |  |  |  | - Establish agro-processing Centres in rural communities | Aiyinase North |  |  |  |  | 5,000 | 9,000 |  |  |  | Agri Dept. | CENTRAL ADMIN. |
|  |  |  |  | - Train 50 forest fringe community members in bee keeping, snail and grass cutter rearing | District wide |  |  |  |  |  | 5,000.00 | 10,000.00 |  |  | GEA | MOFA, CENTRAL ADMIN. |
|  |  |  |  | - Prepare and implement Local Economic Development (LED) Plan | District wide |  |  |  |  |  | 7,500.00 | 7,500 |  |  | GEA | CENTRAL ADMIN. |
|  |  |  |  | - Organize annual Business Expo | District wide |  |  |  |  |  | 30,000 | 45,000 |  |  | GEA | Agri Dept., Private Sector,HODs |
|  |  | Agricultural and Rural Development |  | - Collaborate with private sector to establish a commercial rice farm | Nkroful |  |  |  |  |  | 25,000 | 50,000 |  |  | Agri Dept. | Private Sector |
|  |  |  |  | - Establish youth training centre | Nkroful |  |  |  |  |  | 100,000 |  |  |  | YEA | GEA, WORKS |
|  |  |  |  | - Support the Implementation of the EDGE Project | Menzezor |  |  |  |  |  |  | 1,900,000.00 |  |  | ENI | MOFA/CENTRAL ADMIN. |
|  |  |  |  | - Establish and update database on all farmers in the district | District Wide |  |  |  |  | 4,100 |  |  |  |  | Agri Dept | CENTRAL ADMIN./Statistics |
|  |  |  |  | - Advanced E-Extension and sensitization activities (study tour, malaria, COVID 19, child labour, HIV, pest and infections) | Menzezor, District Wide |  |  |  |  | 4.800 | 2,000 |  |  |  | Agri Dept | Works Dep't, CENTRAL ADMIN./ NCCE/GHS |
|  |  |  |  | - Train 500 and equip 200 youth in modern agriculture and agro-business | District Wide |  |  |  |  |  | 5,000 | 10,000 |  |  | Agri Dept | Agri Dept. |
|  |  |  |  | - Organize District Level Farmers Day Celebration | Selected Community |  |  |  |  | 50,000 |  | 100,000 |  |  | Agri Dept | DPO, CENTRAL ADMIN. |
|  |  |  |  | - Conduct yield studies on selected crops (rice, maize, cassava and plantain) | District Wide |  |  |  |  |  | 5,375 | 5,200 |  |  | Agri Dept. | MOFA |
| ECONOMIC DEVELOPMENT |  | Agricultural and Rural Development |  | - Collaborate with forestry commission to plant and nature 5,000 trees | District wide |  |  |  |  | 5000.00 |  |  |  |  | Forestry | Agric Dept |
|  |  |  |  | - Early warning systems and emergency preparedness for livestock and crop production. (small ruminant, COVID,PPE and FAW) | District wide |  |  |  |  | 5,810.00 |  |  |  |  | Agric Dept | CENTRAL ADMIN./NADMO |
|  |  |  |  | - Support the distribution of 10,000 (PERD) rubber seedling and 50,000 oil palm seedling by CSIR and MDF. | District wide |  |  |  |  |  | 21,500 |  |  |  | Agric Dept | CENTRAL ADMIN. |
|  |  |  |  | - Organise capacity building training for staffs ( AEAs, DDOs) |  |  |  |  |  |  | 15,000 | 3,000 |  |  | Agric Dept | CENTRAL ADMIN. |
|  |  |  |  | - Undertake M&E of implemented activities |  |  |  |  |  |  | 10,000 | 15,180 |  |  | Agric Dept | CENTRAL ADMIN. |
|  |  |  |  | - Train 20 women farmers and 5 AEAs on local food utilization |  |  |  |  |  | 3,950.00 |  |  |  |  | Agric Dept | CENTRAL ADMIN. |
|  |  |  |  | - Showcase to 20 women farmers the establishment of home gardens |  |  |  |  |  | 3,230 |  |  |  |  | Agric Dept | CENTRAL ADMIN. |
| ECONOMIC DEVELOPMENT |  | Agricultural and Rural Development |  | - Train 10 farmers (5 males and 5 females) on safe use and handling of Agro-Chemicals by the end of October 2022. |  |  |  |  |  | 2,790 |  |  |  |  | Agric Dept | CENTRAL ADMIN. |
|  |  |  |  | - Support the District Chamber of Agriculture, Commerce and Technology (Training for DCAT officers) | District Assembly |  |  |  |  |  | 5,000 | 5,000 |  |  | Agri Dept | CENTRAL ADMIN. |
|  |  |  |  | - Organize /Participate in meeting (RELC and Others) | District Assembly |  |  |  |  |  | 1,500 | 3,364 |  |  | Agri Dept | CENTRAL ADMIN. |
|  |  | Tourism and creative Arts development |  | - Promotion of drama, poetry festive and cultural activities (kundum festival) | District wide |  |  |  |  |  | 25,000 | 10,000 |  |  | Culture Unit | CENTRAL ADMIN. |
|  |  |  |  | - Development of the Baku crocodile pond | Baku |  |  |  |  |  | 100,000.00 | 200,000.00 |  |  | CENTRAL ADMIN. | GTDA |
|  |  |  |  | - Form 10 tourism clubs in basic and Senior High Schools | Selected Schools |  |  |  |  |  | 2,500 | 1,500 |  |  | GES | Culture/ DA |
|  |  |  |  | - Rehabilitation of Kwame Nkrumah Motel/Mausoleum | Nkroful |  |  |  |  |  | 330,000 |  |  |  | Works | DA |
|  |  |  | Goal 2: Create Opportunities for All |  |  |  |  |  |  |  |  |  |  |  |  |  |
| EDUCATION AND TRAINING |  | Pre-Tertiary Education |  | - Support STMIE programme | District wide |  |  |  |  | 3,625 | 3,000 |  |  |  | GES | CENTRAL ADMIN. |
|  |  |  |  | - Completion of 3No. and Construction of 2No. 6-unit classroom block | Anwia(O), Ngabawie(O), Domeabra Obengkrom, |  |  |  |  | 1,110,000.00 | 169,500 |  |  |  | CENTRAL ADMIN. | GES |
|  |  |  |  | - Renovate 2No. Basic/primary school buildings | Asemko, Mezzizor |  |  |  |  | 50,000.00 | 100,000.00 |  |  |  | CENTRAL ADMIN. | GES |
|  |  |  |  | - Construction of 50 meters walkway for Kikam SDA basic school | Kikam |  |  |  |  | 30,000.00 |  |  |  |  | CENTRAL ADMIN. | GES |
|  |  |  |  | - Completion of 7No. 3-unit classroom blocks and construction of 1No 3-unit classroom block | Asomase (O) Aluku, Azulenloanu |  |  |  |  | 616,223.9 |  | 465,196.79 |  |  | CENTRAL ADMIN. | GES |
|  |  |  |  | - Construction of assembly hall at UBAISH | Kamgbunli |  |  |  |  | 3,000,000 |  | 50,000 |  |  | CENTRAL ADMIN. | GES |
|  |  |  |  | - Completion 2No. KG and construction of 1No KG block | Kotokuom(N)\ Kikam |  |  |  |  | 500,000 | 315,368.34 |  |  |  | CENTRAL ADMIN. | GES |
|  |  |  |  | - Completion of 2No. and construction of 1No. 4-unit teachers quarters | Adubrim, Awiebo Kotokuom |  |  |  |  | 40,000 | 20,000 | 50,000 |  |  | CENTRAL ADMIN. | GES |
|  |  |  |  | - Completion of 4 No. and Construction of 1No. gender-friendly and disability friendly institutional latrines | Basake (O), Asanta(O) Nvenlosolo (O), Bomaokpole (O), Salman |  |  |  |  | 480,000.00 |  |  |  |  | Works Dept. | EHSU |
|  |  |  |  | - Completion of Assembly Hall for Esiama Sec-Tec | Esiama |  |  |  |  | 412,000 | 47,500 |  |  |  | CENTRAL ADMIN. | GES |
|  |  |  |  | - Support to organize inter-school sports Competitions | District Wide |  |  |  |  |  | 10,000.00 |  |  |  | CENTRAL ADMIN. | GES |
| EDUCATION AND TRAINING |  | Pre-Tertiary Education |  | - Provide items for "my first day at school" celebrations and institute Best Teacher Award especially in deprived schools | District Wide |  |  |  |  | 20,000 | 18,500 | 15,000.00 |  |  | CENTRAL ADMIN. | GES/Private Schools |
|  |  |  |  | - Supply of classroom furniture/Uniforms to schools | Some Selected Schools |  |  |  |  | 90,000 | 50,000 |  |  |  | Works /Procurement | GES |
|  |  |  |  | - facilitate the completion of GETFUND,MSDI, GNPC project | NASS, Esiama Sec Tech, KIMTECH. Charlotte Dolphine training institute |  |  |  |  | 200,000 |  | 700,000 |  |  | CENTRAL ADMIN. | GES |
|  |  |  |  | - Support needy but brilliant students and Award scholarship to PWDs in higher education | District wide |  |  |  |  |  | 15,000 | 7,000 |  |  | SWCD | GES |
|  |  |  |  | - Facilitate the provision of resource persons such as sign language interpreters and braille transcribers at all levels | District wide |  |  |  |  |  | 4,000 |  |  |  | SWCD | PWD |
|  |  |  |  | - Promote the re-entry of dropouts and adolescent mothers back to school after childbirth | Predominant Communities |  |  |  |  |  | 5,000 |  |  |  | SWCD | GES |
| EDUCATION AND TRAINING |  | Pre-Tertiary Education |  | - Completion/Construct ICT Centres | Aiyinasi AB,Bokazo |  |  |  |  | 200,000.00 | 100,000.00 |  |  |  | Works Dep't | GES |
|  |  |  |  | - Procure and supply 100 computers and accessories to basic schools and senior high schools | All SHS and basic schools in the District |  |  |  |  |  | 100,000 | 30,000 |  |  | CENTRAL ADMIN. | GES/Pivate Sector |
|  |  |  |  | - Conduct induction workshop for newly trained teachers | District wide |  |  |  |  | 15,000 |  |  |  |  | GES | CENTRAL ADMIN./HRM |
|  |  |  |  | - Conduct SPAM in basic schools and Organize yearly mock exams for JHS students | District wide |  |  |  |  | 6,500 | 10,000.00 |  |  |  | GES | CENTRAL ADMIN. |
|  |  |  |  | - Support regular inspection and monitoring of schools, SMCs and PTAs | District wide |  |  |  |  | 2,000 | 4,500 |  |  |  | GES | CENTRAL ADMIN. |
|  |  |  |  | - Strengthen non-formal education, form clubs in 4 communities to establish a rice farm, piggery, poultry and fishponds | Asanta Kotokro, Sanzule Aiyinase North, |  |  |  |  |  | 17,100 | 4,125 |  |  | GES | Agric Dept, Private Sector |
| HEALTH AND HEALTH SERVICE DELIVERY |  | Primary Healthcare Delivery |  | - Construct a District Hospital at Nkroful | Nkroful |  |  |  |  | 14,000,000 |  |  |  |  | GHS | CENTRAL ADMIN. |
|  |  |  |  | - Provision of medical supplies to CHPS Compounds (BP apparatus, weighing scale and motor bikes) | All facilities |  |  |  |  |  | 6,000 | 7,500 |  |  | CENTRAL ADMIN. | GHS |
|  |  |  |  | - Completion of 4No. and construction of 1No. CHPS Compounds | Matukwa, Tandan, Ebi, New Adeimbra, Ankobra |  |  |  |  | 600,000.00 |  |  |  |  | CENTRAL ADMIN. | GHS |
|  |  |  |  | - Complete the upgrading and expansion works at St. Martin De Porres Hospital, Eikwe | Eikwe |  |  |  |  |  |  | 9,000,000 |  |  | CENTRAL ADMIN. | GNPC |
|  |  |  |  | - Complete the construction of NHIS Office at Nkroful | Nkroful |  |  |  |  | 500,000 |  |  |  |  | CENTRAL ADMIN. | NHIS |
|  |  |  |  | - Conduct public health education and organize campaigns on mental health | District Wide |  |  |  |  | 1,500 | 8,000 |  |  |  | GHS | SWCD,Religious groups |
|  |  |  |  | - Support to organize capacity building programmes for Health Staff for effective monitoring and evaluation | District Wide |  |  |  |  | 15,500 |  | 22,000 |  |  | GHS | NGO |
| HEALTH AND HEALTH SERVICE DELIVERY |  | Primary Healthcare Delivery |  | - Distribute 2500 insecticide treated mosquito nets | District Wide |  |  |  |  | 2,250 | 8,500 |  |  |  | GHS | CENTRAL ADMIN. |
|  |  |  |  | - Promote ante/post natal services and organize district health wide health screening activities. | District Wide |  |  |  |  | 7,500 |  | 4,000 |  |  | GHS | CENTRAL ADMIN. |
|  |  |  |  | - Continue the administration of vaccines under the NID programme | District Wide |  |  |  |  | 3,000 | 6,000 | 2,000 |  |  | GHS | CENTRAL ADMIN. |
|  |  |  |  | - Organize District wide Health Screening | District Wide |  |  |  |  |  | 12,000 | 33,000 |  |  | GHS | NGOs |
|  |  |  |  | - Embark on quarterly regenerative health and nutrition outreach programmes | District Wide |  |  |  |  | 12,125 | 5,000 |  |  |  | GHS | CENTRAL ADMIN. |
| HEALTH AND HEALTH SERVICE DELIVERY |  | HIV, AIDS/STIs and other infections |  | - Intensify comprehensive education on HIV/AIDS and STIs, including reduction of stigmatisation | District wide |  |  |  |  | 6,625 |  | 6,250 |  |  | GHS | NGOs |
|  |  |  |  | - Organize quarterly HIV/AIDS Committee Meetings and world AIDS day. | Nkroful |  |  |  |  | 11,000.00 |  |  |  |  | DAC | GHS |
|  |  |  |  | - Counsel and test for HIV in all pregnant women | District wide |  |  |  |  | 7,575 |  | 1,020 |  |  | GHS | CENTRAL ADMIN. |
|  |  |  |  | - Organize HIV/AIDS and TB campaigns in schools | District wide |  |  |  |  | 7,500 |  |  |  |  | GHS | GES |
|  |  | Population Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | - Ensure registration of all birth and death in the district | District wide |  |  |  |  |  | 1,000 |  |  |  | Birth & death Dept. | CENTRAL ADMIN. |
|  |  |  |  | - Organize quarterly sensitization programmes on teenage pregnancy and child marriage | District wide |  |  |  |  |  | 19,100 |  |  |  | SWCD | CENTRAL ADMIN./NCCE |
|  |  |  |  | - Provide support for family planning activities | District wide |  |  |  |  | 5,000 |  | 2,000 |  |  | GHS | CENTRAL ADMIN. |
| HEALTH AND HEALTH SERVICE DELIVERY |  | Food and Nutrition |  | - Organize food and nutrition campaign in schools and health centres and on radio | District wide |  |  |  |  |  | 13,000 | 2,000 |  |  | GHS/EHSU | CENTRAL ADMIN. |
|  |  |  |  | - Monitor the school feeding programme to ensure quality and well balanced diet is served | District wide |  |  |  |  | 10000 | 3000 |  |  |  | Central Admin | CENTRAL ADMIN. |
| WATER AND ENVIRONMENTAL SANITATION |  | Water Supply, Waste Management and Environmental Sanitation |  | - Drilling of 10No. Disability friendly Mechanized boreholes | Selected communities and health facilities |  |  |  |  | 250,000 |  | 10,000 |  |  | CENTRAL ADMIN. | DWST |
|  |  |  |  | - Completion, Construction/ Extension of water supply for selected communities | Nkroful, Kamgbuli,Asomase, Teleku Bokazo new and old Bakanta, Asanta, Kwesikrom, Sanzule |  |  |  |  | 200,000 | 100,000 |  |  |  | CENTRAL ADMIN. | DWST |
| WATER AND ENVIRONMENTAL SANITATION |  | Water Supply, Waste Management and Environmental Sanitation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | - Prepare, and implement the District Water and Sanitation Plan | District Assembly |  |  |  |  |  | 8,500 |  |  |  | DWST | CENTRAL ADMIN. |
|  |  |  |  | - Form and train 10No. WATSan Committees | Selected Communities |  |  |  |  | 15,000 |  |  |  |  | DWST | CENTRAL ADMIN. |
|  |  |  |  | - Implement the CLTS programme and intensify environmental health education campaigns | District wide |  |  |  |  | 25,000 |  |  |  |  | EHSU | CENTRAL ADMIN. |
|  |  |  |  | - Completion/ Construction of slaughter slabs at market places | Aiyinasi, Esiama, Assasetre |  |  |  |  | 2500,000 |  |  |  |  | CENTRAL ADMIN. | EHSU |
|  |  |  |  | - Conduct screening of food vendors | District wide |  |  |  |  | 7,500 | 5,000 |  |  |  | EHSU | GHS, CENTRAL ADMIN. |
|  |  |  |  | - Support the Conveyance/ waste management activities | District wide |  |  |  |  | 320000 |  |  |  |  | EHSU | CENTRAL ADMIN. |
|  |  |  |  | - Monitor waste collection by zoomlion | Market Places |  |  |  |  |  | 10,000 |  |  |  | EHSU | CENTRAL ADMIN. |
|  |  |  |  | - Procure a cespit emptier | District Assembly |  |  |  |  |  |  |  |  |  |  |  |
| GENDER, CHILDREN AND SOCIAL PROTECTION |  | Child Protection and Youth Development |  | - Mobilize and sensitize 10 communities on parental responsibilities | District Wide |  |  |  |  |  | 25,000 |  |  |  | CENTRAL ADMIN. | GES, SWCD, NCCE |
|  |  |  |  | - Monitor Day Care Centres and orphanages within the district | District Wide |  |  |  |  | 5,000 | 2,000 |  |  |  | SWCD | CENTRAL ADMIN. |
|  |  |  |  | - Enforce child right and Gender related Bye laws | District Wide |  |  |  |  |  | 25,000 |  |  |  | SWCD | GES, NCCE,DA, Police etc. |
|  |  |  |  | - organize sensitization programmes on child protection issues | District Wide |  |  |  |  |  | 13,000 UNICEF |  |  |  | SWCD | CENTRAL ADMIN., NCCE, LABOUR DEP'T, NCCE |
|  |  |  |  | - Institute Child Protection Committees in 20 Communities | District wide |  |  |  |  |  | 5,000 UNICEF |  |  |  | SWCD | CENTRAL ADMIN. |
|  |  |  |  | - Settle child maintenance cases Organize community engagements and behavioural change campaigns to promote positive parenting | District wide |  |  |  |  |  | 5,000 UNICEF |  |  |  | SWCD | UNICEF |
|  |  |  |  | - Organize girls empowerment summits in Senior High Schools and create a pool of potential female leaders | District wide |  |  |  |  |  | 17,000.00 |  |  |  | SWCD | GES |
|  |  |  |  | - Establish adolescent clubs in schools and communities | District wide |  |  |  |  |  | 3,500 | 3,000 |  |  | SWCD | Gender Desk |
|  |  | Support for the Aged |  | - Create a database on the aged and support the Ellembelle Elderly Care Centre with Food Items | Ampain |  |  |  |  | 8,000 |  | 2,400 |  |  | DPU | CENTRAL ADMIN. |
|  |  | Women empowerment |  | - Organize quarterly sensitization Campaigns on gender-based violence and other harmful cultural practices | District Wide |  |  |  |  | 10,000 |  | 3,500 |  |  | SWCD/DPCU | CENTRAL ADMIN. |
|  |  |  |  | - Organize skills training for 1000 women | District Wide |  |  |  |  |  | 20,000 | 5,000 |  |  | SWCD | DA, GEA |
|  |  | Social Protection |  | - Mobilize indigenes and vulnerable people for NHIS registration | District Wide |  |  |  |  | 10,000 |  |  |  |  | SWCD | NHIS, DA |
|  |  |  |  | - Construct 5No. Disability friendly Community parks | District wide |  |  |  |  | 300,000 |  |  |  |  | Works Dept. | Sport Committee |
|  |  |  |  | - Support People With Disabilities (PWDs) with training skills, items, cash, school fees medical bills and start-up capital. | District Wide |  |  |  |  | 200,000.00 |  |  |  |  | SWCD | GEA, DA |
|  |  |  |  | - Monitor and support the Livelihood Empowerment Against Poverty (LEAP) programme | District wide |  |  |  |  | 10,000 |  |  |  |  | SWCD | CENTRAL ADMIN. |
|  |  |  | Goal 3: Safeguard the Natural Environment and Ensure A Resiliant Built Environment |  |  |  |  |  |  |  |  |  |  |  |  |  |
| NATURAL RESOURCE MANAGEMENT |  | Mineral Extraction |  | - Arrest and prosecute illegal, sand winners, miners, lumbers | District Wide |  |  |  |  | 30,000 | 30,000.00 |  |  |  | Security Agencies | EHSU,CENTRAL ADMIN. |
|  |  |  |  | - Establish a community mining scheme in 3 communities. | Salma, Teleku Bokazo, Nkroful |  |  |  |  |  | 6,000 | 3,000 |  |  | Works Dept. | CENTRAL ADMIN. |
|  |  |  |  | - Ensure the reclamation of degraded land after mining | Mining communities |  |  |  |  |  | 100,000 | 100,000 |  |  | PPD | CENTRAL ADMIN. |
|  |  | Coastal and Marine Erosion |  | - Revive conservation committee groups and build women capacity in conservation | District Assembly |  |  |  |  | 5,000 |  |  |  |  | DPU | CENTRAL ADMIN. |
|  |  | Deforestation, Desertification and Soil Erosion |  | - Develop landfill site into a modern engineered site | Ala Bokazo |  |  |  |  | 300,000 |  |  |  |  | EHSU | PPD, EPA |
|  |  |  |  | - Protect natural reserves (mangroves and forest) and recreation areas from encroachment | District Wide |  |  |  |  | 26,500 | 15,000.00 |  |  |  | Forestry | Works/NADMO/PPD |
| CLIMATE CHANGE AND DISASTER RISK REDUCTION |  | Climate Variability and Change |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | - Organize Capacity Building Training in Climate Change for DPCU/HODS Members | District Assembly |  |  |  |  |  |  | 6,500 |  |  | Agri Dept. | CENTRAL ADMIN. |
|  |  |  |  | - Train farmers on climate smart agriculture technologies | District wide |  |  |  |  | 5,000 |  |  |  |  | Agric .Dept. | MOFA |
|  |  |  |  | - Complete the construction of town roads | Esiama- Nkrofu- Bokazo Eikwe, Sanzule, Baku, Ngalekyi, Bobrama, Aiyinase South, Aiyinase North, and others |  |  |  |  | 2,000,000 |  |  |  |  | GHA, Dep't of Feeder Roads | CENTRAL ADMIN. |
|  |  |  |  | - Develop of Modern lorry parks and stores at Aiyinase and Esiama | Aiyinase, Esiama |  |  |  |  |  | 100,000 |  |  |  | GHA | CENTRAL ADMIN. |
|  |  |  |  | - Support road safety activities in the District | District Wide |  |  |  |  | 120,000.00 |  |  |  |  | GHA | CENTRAL ADMIN. |
| CLIMATE CHANGE AND DISASTER RISK REDUCTION |  | Information Communication Technology |  | - Rehabilitate existing post offices | Aiyinase, Nkroful Esiama |  |  |  |  |  | 200,000 |  |  |  | Works dept | CENTRAL ADMIN. |
|  |  |  |  | - Renovation of ICT Centre at Aiyinase and Install Wi-Fi at the District Assembly Office | Aiyinase Nkroful |  |  |  |  | 64,500 | 54,200 |  |  |  | ICT Dept. | GIFEC |
|  |  | Human Settlements Development and Housing |  | - Organize technical and statutory planning committee meetings | District Assembly |  |  |  |  |  | 12,000 |  |  |  | PPD | HODs |
|  |  |  |  | - Preparation of local plans | Bomoakpole |  |  |  |  |  | 20,000 |  |  |  | PPD | CENTRAL ADMIN. |
|  |  |  |  | - Sensitization of the public on Land use planning and permitting | District Wide |  |  |  |  |  | 3,000 |  |  |  | PPD | Works Dep't, CENTRAL ADMIN. |
|  |  |  |  | - Organize joint inspections to check unauthorised developments | District Wide |  |  |  |  |  | 20,000.00 |  |  |  | PPD | Works Dep't, CENTRAL ADMIN. |
|  |  |  |  | - Construction of 5No. Community Centres | New Bakanta, Adurim, Aiyinasi North and others |  |  |  |  | 780,000 |  |  |  |  | DA | COCOBOD |
|  |  | Drainage and Flood Control |  | - Prepare and implement drainage plans for flood prone areas | District Assembly |  |  |  |  |  | 5,000 |  |  |  | PPD | Works Dep't, CENTRAL ADMIN. |
|  |  |  |  | - Construct and frequently desilt chocked drains | District Assembly |  |  |  |  | 200,000.00 | 20,000 |  |  |  | EHSU | PPD,WORKS,NADMO |
| CLIMATE CHANGE AND DISASTER RISK REDUCTION |  | Infrastructure Maintenance |  | - Organize capacity building training in inventory and asset management for selected staff | District Assembly |  |  |  |  |  | 7,000 |  |  |  | HR | CENTRAL ADMIN. |
|  |  |  |  | - Prepare operation and maintenance (O&M) Plan | District Assembly |  |  |  |  | 5,000 |  |  |  |  | Works Dep't | Dev't Planning Unit |
|  |  |  |  | - Undertake building inspections and ensure that all public buildings are disability friendly | District wide |  |  |  |  |  | 10,000 |  |  |  | Works Dep't | CENTRAL ADMIN. |
|  |  |  | Goal 4: Maintain a Stable, United and Safe Society |  |  |  |  |  |  |  |  |  |  |  |  |  |
| DEMOCRACY, GOVERNANCE AND PUBLIC ACCOUNTABILITY |  | Resource Mobilization and Expenditure Management |  | - Update economic/ Tourism data to improve revenue | District wide |  |  |  |  | 100,000.00 |  |  |  |  | Statistical Dept. | Revenue Unit,DPO, PPD, Budget |
|  |  |  |  | - Provide revenue collection and management logistics | District Assembly |  |  |  |  | 12,000 |  |  |  |  | Revenue Unit | GIZ, CENTRAL ADMIN. |
|  |  |  |  | - Organize public sensitization on revenue mobilization in market places and lorry stations | Aiyinase, Asasetre, Esiama, Teleku Bokazo |  |  |  |  |  | 7,500 |  |  |  | Revenue Unit | Budget/Finance, Works, PPA, NCCE |
|  |  |  |  | - Mount and update revenue performance and Accountability Bill Boards at the Various Area Councils | Esiama, Asasetre, Awiebo Basake, Aiyinase, Kikam, Nkroful, Atoabo |  |  |  |  | 22,000 |  |  |  |  | Fin. Dep't | CENTRAL ADMIN. |
|  |  |  |  | - Prepare and Implement a Revenue Improvement Action Plan and Concept Note | District Assembly |  |  |  |  | 5,000.00 | 7,000 |  |  |  | DBU/ | DPO, Fin Dept |
| Democracy, Governance and Public Accountability |  | Local Government and Decentralization |  | - Completion/furnishing /Construction of Area Council Office | Asasetre, Nkroful. Atuabo |  |  |  |  | 500,000.00 | 500,000 .00 |  |  |  | CENTRAL ADMIN. | WORKS/DPO |
|  |  |  |  | - Organize sensitization programme on Elections | District Wide |  |  |  |  |  |  |  |  |  | NCCE | EC |
|  |  |  |  | - Support and build the capacity of women to contest for political positions | District Wide |  |  |  |  |  |  |  |  |  | NCCE | CENTRAL ADMIN. |
|  |  |  |  | - Organize all statutory meetings and celebration of National Days | District Assembly |  |  |  |  | 90,000.00 | 20,000.00 | 40,000,00 |  |  | Central Admin | CENTRAL ADMIN. |
|  |  |  |  | - Secure/furnish office accommodation for area councils | District Assembly |  |  |  |  | 100,000.00 |  |  |  |  | Planning | Finance, CENTRAL ADMIN. |
|  |  |  |  | - Coordinate the preparation of Community Action Plans | District Assembly |  |  |  |  | 10,000.00 |  |  |  |  | Dev't Planning/PP | HODs |
|  |  |  |  | - Review and prepare Annual Action Plans, Composite Budgets, Procurement plans | District Assembly |  |  |  |  | 50,000.00 |  |  |  |  | Planning, Budget Unit, Procurement | HODs |
|  |  |  |  | - Undertake Town Hall Meetings on AAPs, fee-fixing and composite annual budget | All Area Council Offices |  |  |  |  | 50,000 | 10,000.00 | 5,000 |  |  | Dev't Planning/Budget | HODs, CENTRAL ADMIN. |
| Democracy, Governance and Public Accountability |  | Local Government and Decentralization |  | - Administer comprehensive HRMIS and submit monthly returns to RCC | District Assembly |  |  |  |  |  | 4,000 |  |  |  | HR | HODs |
|  |  |  |  | - Organize capacity building training for revenue collectors and Area Council members on effective revenue mobilization | District Assembly |  |  |  |  |  | 40,000.00 |  |  |  | HR/DPU | NGO |
|  |  |  |  | - Organize capacity building training for all staff and Assembly members | District Assembly |  |  |  |  | 35,000 |  |  |  |  | HR | Fin. Dep't, HODs |
|  |  |  |  | - Procure office stationery, logistics, Vehicles and others | District Assembly |  |  |  |  | 600,000.00 |  |  |  |  | Procurement | CENTRAL ADMIN. |
|  |  |  |  | - Maintenance of Assembly accommodation vehicles, computers and other logistics | District Assembly |  |  |  |  | 100,000.00 |  |  |  |  | Procurement | CENTRAL ADMIN. |
| Democracy, Governance and Public Accountability |  | Human Security and Public Safety |  | - Construction of Police Station | Dadwen |  |  |  |  |  | 350,000 |  |  |  | CENTRAL ADMIN. | GPS |
|  |  |  |  | - Form 4No. Neighbourhood watchdog committees | Selected Communities |  |  |  |  |  | 5,000 |  |  |  | GPS | CENTRAL ADMIN. |
|  |  |  |  | - Conduct fire safety inspections at all public places | Selected premises |  |  |  |  | 20,000 |  |  |  |  | GNFS | CENTRAL ADMIN., NADMO |
|  |  | Corruption and Economic Crimes |  | - Support all activities of the Audit unit including audit committees | District Assembly |  |  |  |  | 40,000 |  |  |  |  | Internal Audit | External Audit |
|  |  |  |  | - Ensure that all HODs complete the Assets Declaration Form | District Assembly |  |  |  |  |  | 5,000 |  |  |  | DA |  |
|  |  | Law and Order |  | - Lobby for the posting of more Police Personnel into the district | District Assembly |  |  |  |  |  | 20,000 |  |  |  | DISEC | GPS |
|  |  |  |  | - Support the Police Service, fire service, ambulance service, immigration, BNI | District Assembly |  |  |  |  | 30,000 | 5,000 |  |  |  | DISEC | All security agencies |
|  |  |  |  | - Organize DISEC Meetings | District Wide |  |  |  |  |  | 60,000.00 |  |  |  | Central Admin | CENTRAL ADMIN. |
| Democracy, Governance and Public Accountability |  | Civil Society and Civic Engagement |  | - Collaborate with NGO to implement the Youth inclusive development programme | District Assembly |  |  |  |  |  | 4,000 | 2,500 |  |  | DPU | NGO |
|  |  |  |  | - Attend Nzema Maanle TC Meetings to engage TAs on the works of the Assembly | Ampain |  |  |  |  |  | 5,500 |  |  |  | DPU | CENTRAL ADMIN. |
|  |  |  |  | - Support Religious activities | District Wide |  |  |  |  | 21,800 |  |  |  |  | CENTRAL ADMIN. |  |
|  |  |  |  | - Collaborate with Youth Bridge to implement youth involvement programme | District Wide |  |  |  |  |  | 10,200 |  |  |  | DPU | CENTRAL ADMIN. |
|  |  | Culture |  | - Organize story telling competition in Nzema and Fanti and cultural festivals for basic schools | Selected Schools |  |  |  |  | 12,000 |  |  |  |  | GES | CENTRAL ADMIN. |
|  |  |  | Goal 5: Mainstream Emergency Planning and Preparedness Into Ghana’s Development Planning Agenda At All Levels To Respond To Potential Internal And External Threats (Including Covid-19 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| EMERGENCY PLANNING AND RESPONSE (INCLUDING COVID-19 RECOVERY PLAN) |  | Hydrometeological Threats |  | - Organize community sensitizations on disaster prevention | District Wide |  |  |  |  | 12,500 |  |  |  |  | NADMO | CENTRAL ADMIN., NCCE |
|  |  |  |  | - Organize pests and insect infection sensitization campaign in communities | District Wide |  |  |  |  |  | 6,000 | 4,500 |  |  | NADMO | MOFA, NCCE |
|  |  |  |  | - Formation of Disaster Risk Reduction clubs in schools and communities | Selected Schools |  |  |  |  |  | 8,000 |  |  |  | NADMO | GES, CENTRAL ADMIN. |
|  |  |  |  | - Organize DRR training programmes at zonal levels | District Wide |  |  |  |  |  | 2,000 | 3,000 |  |  | NADMO | GNFS, CENTRAL ADMIN. |
|  |  |  |  | - Supply stationery and logistics to NADMO | District Assembly |  |  |  |  | 8,000 |  |  |  |  | CENTRAL ADMIN. | REG/NAT NADMO |
|  |  |  |  | - Train Area Council Members and Traditional Authorities on impact of sand winning and galamsey on the environment | District Wide |  |  |  |  |  | 16,000 |  |  |  | NADMO | CENTRAL ADMIN., NCCE |
| EMERGENCY PLANNING AND RESPONSE (INCLUDING COVID-19 RECOVERY PLAN) |  | Biological Threats |  | - Undertake surveillance, monitoring and evaluation of Health threats and epidemics and pandemics | District Wide |  |  |  |  |  | 10,000 |  |  |  | DHD | NCCE |
|  |  | Anthropogenic Threats |  | - Support National Ambulance Service | District Wide |  |  |  |  |  | 15,000 |  |  |  | GHS | CENTRAL ADMIN. |
|  |  |  |  | - Intensify monitoring at Filling Stations to ensure adherence to Standard Operating Procedures. | District Wide |  |  |  |  |  | 6,000 |  |  |  | GNFS | Security agencies |
|  |  |  |  | - Establish a well-resourced Emergency Centre | District Wide |  |  |  |  |  | 50,000 | 70,000 |  |  | CENTRAL ADMIN. | Private Sector/GHS |
|  |  | Security |  | - Organize Annual ADR week Celebration | District Wide |  |  |  |  |  | 6,000 |  |  |  | CENTRAL ADMIN. |  |
|  |  |  |  | - Create awareness on the consequences of ethnic and chieftaincy conflicts | District Wide |  |  |  |  |  |  | 8,500 |  |  | NCCE | CENTRAL ADMIN., ETC |
| EMERGENCY PLANNING AND RESPONSE (INCLUDING COVID-19 RECOVERY PLAN) |  | Covid-19 Response |  | - Conduct sensitization on pandemics and implement a recovery Plan | District Wide |  |  |  |  |  | 6,000 |  |  |  | DHD | NCCE |
|  |  |  |  | - Support Public Health Emergency Management Committee | District Wide |  |  |  |  | 10,000 | 4,800 |  |  |  | CENTRAL ADMIN. | DHD |
|  |  |  |  | - Vaccinate 50,000 people against covid-19 and other pandemics. | District Wide |  |  |  |  |  | 35,000 |  |  |  | DHD | CENTRAL ADMIN. |
|  |  |  | Goal 6: Improve Delivery of Development Outcomes at all Levels |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Implementation, Coordination, Monitoring And Evaluation |  | Implementation and Coordination |  | - Review of MTDP (2022-2025) | District Assembly |  |  |  |  | 15,000 | 5,000 |  |  |  | Dev't Planning | HODs |
|  |  |  |  | - Organize Capacity Building programme for DPCU members and HODs | District Assembly |  |  |  |  | 6,000 | 2,500 |  |  |  | Dev't Planning | HODs |
|  |  | Monitoring and Evaluation |  | - Organize quarterly Participatory Project Monitoring | District Assembly |  |  |  |  | 120,000 |  |  |  |  | Dev't Planning | HODs, CENTRAL ADMIN. |
|  |  |  |  | - Organize Quarterly M&E/ AAP Review Meetings | District Assembly |  |  |  |  | 12,000 | 5,000 |  |  |  | Dev't Planning | HODs |
| Production And Utilisation Of Statistics |  | Data-Based Planning and Budgeting |  | - Establish District Statistical Working Group and train Field Officers | District Assembly |  |  |  |  | 2,000 | 2,000 |  |  |  | Statistical Dept. | HODs |
|  |  |  |  | - Establish and update Central Database for Planning and Budgeting | District Assembly |  |  |  |  | 10,000 |  |  |  |  | Statistical Dept. | HODs |
|  |  |  |  | - Support the GSS to collect population data | District wide |  |  |  |  | 30,000 |  |  |  |  | Statistical Dept. | CENTRAL ADMIN. |
|  |  |  |  | - Conduct Monthly Market Survey | District Assembly |  |  |  |  | 5,000 | 2,500 |  |  |  | Statistical Dept. | HODs |
|  |  |  |  | - Disseminate statistical Data and projections with Relevant Units, Departments and Agencies in the District. | District Assembly |  |  |  |  | 10,000 |  | 5,000 |  |  | Statistical Dept. | HODs |

Table 5. 3: 2025 Annual Action Plan

| Programmes | Sub-programmes |  | Projects/activities | Location | Time Frame |  |  |  | Cost |  |  | Prog Status |  | Implementing Dep'ts |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | 1 | 2 | 3 | 4 | GoG | IGF | Others | New | Old | Lead | Coll. |
|  |  |  | Goal 1: Build a Prosperous Society |  |  |  |  |  |  |  |  |  |  |  |  |
| ECONOMIC DEVELOPMENT | Local and Economic Development |  | - Support 1000 local businesses with training and funding | District Wide |  |  |  |  |  | 30,000 |  |  |  | GEA | CENTRAL ADMIN. |
|  |  |  | - Completion of 4No market and construction of 2No market. | Basake, Sanzule, Atuabo, Eikwe, Akropong |  |  |  |  | 2,000,000.00 |  |  |  |  | Works Dep't | CENTRAL ADMIN. |
|  |  |  | - Create industrial village | Ampain |  |  |  |  | 450,000 |  | 150,000 |  |  | CENTRAL ADMIN. | GEA/NBSSI |
|  |  |  | - Establish a ceramics factory | Teleku Bokazo |  |  |  |  | 500,000 | 50,00 | 1,500.000 |  |  | CENTRAL ADMIN. | GFZB |
|  |  |  | - Registration and training of local businesses. | District Wide |  |  |  |  |  | 5,000 |  |  |  | GEA | RGD |
|  |  |  | - Create a marketing platform for sellers and buyers of agro produce | District Wide |  |  |  |  |  | 10,000 |  |  |  | ENI/ GEA | Agri Dept/ENI |
|  |  |  | - Establish agro-processing Centres in rural communities | District wide |  |  |  |  | 5,000 | 9,000 |  |  |  | Agri Dept. | CENTRAL ADMIN. |
|  |  |  | - Train 50 forest fringe community members in bee keeping, snail and grass cutter rearing | District wide |  |  |  |  |  | 5,000.00 | 10,000.00 |  |  | GEA | MOFA, CENTRAL ADMIN. |
|  |  |  | - Prepare and implement Local Economic Development (LED) Plan | District wide |  |  |  |  |  | 7,500.00 | 7,500 |  |  | GEA | CENTRAL ADMIN. |
|  |  |  | - Organize annual Business Expo | District wide |  |  |  |  |  | 30,000 | 45,000 |  |  | GEA | Agri Dept., Private Sector,HODs |
|  | Agricultural and Rural Development |  | - Collaborate with private sector to establish a commercial rice farm | Nkroful |  |  |  |  |  | 25,000 | 50,000 |  |  | Agri Dept. | Private Sector |
|  |  |  | - Establish youth training centre | Nkroful |  |  |  |  |  | 100,000 |  |  |  | YEA | GEA, WORKS |
|  |  |  | - Support the Implementation of the EDGE Project | Menzezor |  |  |  |  |  |  | 1,900,000.00 |  |  | ENI | MOFA/CENTRAL ADMIN. |
|  |  |  | - Establish and update database on all farmers in the district | District Wide |  |  |  |  | 4,100 |  |  |  |  | Agri Dept | CENTRAL ADMIN./Statistics |
|  |  |  | - Advanced E-Extension and sensitization activities (study tour, malaria, COVID 19, child labour, HIV, pest and infections) | Menzezor, District Wide |  |  |  |  | 4.800 | 2,000 |  |  |  | Agri Dept | Works Dep't, CENTRAL ADMIN./ NCCE/GHS |
|  |  |  | - Train 500 and equip 200 youth in modern agriculture and agro-business | District Wide |  |  |  |  |  | 5,000 | 10,000 |  |  | Agri Dept | Agri Dept. |
|  |  |  | - Organize District Level Farmers Day Celebration | Selected Community |  |  |  |  | 50,000 |  | 100,000 |  |  | Agri Dept | DPO, CENTRAL ADMIN. |
|  |  |  | - Conduct yield studies on selected crops (rice, maize, cassava and plantain) | District Wide |  |  |  |  |  | 5,375 | 5,200 |  |  | Agri Dept. | MOFA |
| ECONOMIC DEVELOPMENT | Agricultural and Rural Development |  | - Collaborate with forestry commission to plant and nature 5,000 trees | District wide |  |  |  |  | 5000.00 |  |  |  |  | Forestry | Agric Dept |
|  |  |  | - Early warning systems and emergency preparedness for livestock and crop production. (small ruminant, COVID,PPE and FAW) | District wide |  |  |  |  | 5,810.00 |  |  |  |  | Agric Dept | CENTRAL ADMIN./NADMO |
|  |  |  | - Support the distribution of 10,000 (PERD) rubber seedling and 50,000 oil palm seedling by CSIR and MDF. | District wide |  |  |  |  |  | 21,500 |  |  |  | Agric Dept | CENTRAL ADMIN. |
|  |  |  | - Organise capacity building training for staffs ( AEAs, DDOs) | District wide |  |  |  |  |  | 15,000 | 3,000 |  |  | Agric Dept | CENTRAL ADMIN. |
|  |  |  | - Undertake M&E of implemented activities | District wide |  |  |  |  |  | 10,000 | 15,180 |  |  | Agric Dept | CENTRAL ADMIN. |
|  |  |  | - Train 20 women farmers and 5 AEAs on local food utilization | District wide |  |  |  |  | 3,950.00 |  |  |  |  | Agric Dept | CENTRAL ADMIN. |
|  |  |  | - Showcase to 20 women farmers the establishment of home gardens | District wide |  |  |  |  | 3,230 |  |  |  |  | Agric Dept | CENTRAL ADMIN. |
| ECONOMIC DEVELOPMENT | Agricultural and Rural Development |  | - Train 10 farmers (5 males and 5 females) on safe use and handling of Agro-Chemicals by the end of October 2022. | District wide |  |  |  |  | 2,790 |  |  |  |  | Agric Dept | CENTRAL ADMIN. |
|  |  |  | - Support the District Chamber of Agriculture, Commerce and Technology (Training for DCAT officers) | District Assembly |  |  |  |  |  | 5,000 | 5,000 |  |  | Agri Dept | CENTRAL ADMIN. |
|  |  |  | - Organize /Participate in meeting (RELC and Others) | District Assembly |  |  |  |  |  | 1,500 | 3,364 |  |  | Agri Dept | CENTRAL ADMIN. |
|  | Tourism and creative Arts development |  | - Promotion of drama, poetry festive and cultural activities (kundum festival) | District wide |  |  |  |  |  | 25,000 | 10,000 |  |  | Culture Unit | CENTRAL ADMIN. |
|  |  |  | - Development of the Baku crocodile pond | Baku |  |  |  |  |  | 100,000.00 | 200,000.00 |  |  | CENTRAL ADMIN. | GTDA |
|  |  |  | - Form 10 tourism clubs in basic and Senior High Schools | Selected Schools |  |  |  |  |  | 2,500 | 1,500 |  |  | GES | Culture/ CENTRAL ADMIN. |
|  |  |  | - Rehabilitation of Kwame Nkrumah Motel/Mausoleum | Nkroful |  |  |  |  |  | 330,000 |  |  |  | Works | CENTRAL ADMIN. |
|  |  |  | Goal 2: Create Opportunities for All |  |  |  |  |  |  |  |  |  |  |  |  |
| EDUCATION AND TRAINING | Pre-Tertiary Education |  | - Support STMIE programme | District wide |  |  |  |  | 3,625 | 3,000 |  |  |  | GES | CENTRAL ADMIN. |
|  |  |  | - Completion of 2No. and Construction of 1No. 6-unit classroom block | Domeabra Obengkrom, Kamgbanli |  |  |  |  | 1,110,000.00 | 169,500 |  |  |  | CENTRAL ADMIN. | GES |
|  |  |  | - Renovate 2No. Basic/primary school buildings | Asemko, Mezzizor |  |  |  |  | 50,000.00 | 100,000.00 |  |  |  | CENTRAL ADMIN. | GES |
|  |  |  | - Construction of 50 meters walkway for Kikam SDA basic school | Kikam |  |  |  |  | 30,000.00 |  |  |  |  | CENTRAL ADMIN. | GES |
|  |  |  | - Completion of 7No. 3-unit classroom blocks and construction of 1No 3-unit classroom block | Asomase (O) Aluku, Azulenloanu, selected community |  |  |  |  | 616,223.9 |  | 465,196.79 |  |  | CENTRAL ADMIN. | GES |
|  |  |  | - Construction of assembly hall at UBAISH | Kamgbunli |  |  |  |  | 3,000,000 |  | 50,000 |  |  | CENTRAL ADMIN. | GES |
|  |  |  | - Completion 2No. KG and construction of 1No KG block | Kikam, Awiaso |  |  |  |  | 500,000 | 315,368.34 |  |  |  | CENTRAL ADMIN. | GES |
|  |  |  | - Completion of 3No. and construction of 1No. 4-unit teachers quarters | Adubrim, Awiebo Kotokuom, Kwesikrom |  |  |  |  | 40,000 | 20,000 | 50,000 |  |  | CENTRAL ADMIN. | GES |
|  |  |  | - Completion of 5 gender-friendly and disability friendly institutional latrines | Basake (O), Asanta(O) Nvenlosolo (O), Bomaokpole (O), Salman (0) |  |  |  |  | 480,000.00 |  |  |  |  | Works Dept. | EHSU |
|  |  |  | - Completion of Assembly Hall for Esiama Sec-Tec | Esiama |  |  |  |  | 412,000 | 47,500 |  |  |  | CENTRAL ADMIN. | GES |
|  |  |  | - Support to organize inter-school sports Competitions | District Wide |  |  |  |  |  | 10,000.00 |  |  |  | CENTRAL ADMIN. | GES |
| EDUCATION AND TRAINING | Pre-Tertiary Education |  | - Provide items for "my first day at school" celebrations and institute Best Teacher Award especially in deprived schools | District Wide |  |  |  |  | 20,000 | 18,500 | 15,000.00 |  |  | CENTRAL ADMIN. | GES/Private Schools |
|  |  |  | - Supply of classroom furniture/Uniforms to schools | Some Selected Schools |  |  |  |  | 90,000 | 50,000 |  |  |  | Works /Procurement | GES |
|  |  |  | - facilitate the completion of GETFUND,MSDI, GNPC project | NASS, Esiama Sec Tech, KIMTECH. Charlotte Dolphine training institute |  |  |  |  | 200,000 |  | 700,000 |  |  | CENTRAL ADMIN. | GES |
|  |  |  | - Support needy but brilliant students and Award scholarship to PWDs in higher education | District wide |  |  |  |  |  | 15,000 | 7,000 |  |  | SWCD | GES |
|  |  |  | - Facilitate the provision of resource persons such as sign language interpreters and braille transcribers at all levels | District wide |  |  |  |  |  | 4,000 |  |  |  | SWCD | PWD |
|  |  |  | - Promote the re-entry of dropouts and adolescent mothers back to school after childbirth | Predominant Communities |  |  |  |  |  | 5,000 |  |  |  | SWCD | GES |
| EDUCATION AND TRAINING | Pre-Tertiary Education |  | - Construct 4No. ICT Centres | AB Bokazo Anwia. |  |  |  |  | 200,000.00 | 100,000.00 |  |  |  | Works Dep't | GES |
|  |  |  | - Procure and supply 100 computers and accessories to basic schools and senior high schools | All SHS and basic schools in the District |  |  |  |  |  | 100,000 | 30,000 |  |  | CENTRAL ADMIN. | GES/Pivate Sector |
|  |  |  | - Conduct induction workshop for newly trained teachers | District wide |  |  |  |  | 15,000 |  |  |  |  | GES | CENTRAL ADMIN./HRM |
|  |  |  | - Conduct SPAM in basic schools and Organize yearly mock exams for JHS students | District wide |  |  |  |  | 6,500 | 10,000.00 |  |  |  | GES | CENTRAL ADMIN. |
|  |  |  | - Support regular inspection and monitoring of schools, SMCs and PTAs | District wide |  |  |  |  | 2,000 | 4,500 |  |  |  | GES | CENTRAL ADMIN. |
|  |  |  | - Strengthen non-formal education, form clubs in 4 communities to establish a rice farm, piggery, poultry and fishponds | Asanta Kotokro, Sanzule Aiyinase North, |  |  |  |  |  | 17,100 | 4,125 |  |  | GES | Agric Dept, Private Sector |
| HEALTH AND HEALTH SERVICE DELIVERY | Primary Healthcare Delivery |  | - Construct a District Hospital at Nkroful | Nkroful |  |  |  |  | 14,000,000 |  |  |  |  | GHS | CENTRAL ADMIN. |
|  |  |  | - Provision of medical supplies to CHPS Compounds (BP apparatus, weighing scale and motor bikes) | All facilities |  |  |  |  |  | 6,000 | 7,500 |  |  | CENTRAL ADMIN. | GHS |
|  |  |  | - Completion of 4No. and construction of 1No. CHPS Compounds | Ayawora, Mpeasem Boamoakpole, Ngabawie |  |  |  |  | 600,000.00 |  |  |  |  | CENTRAL ADMIN. | GHS |
|  |  |  | - Complete the upgrading and expansion works at St. Martin De Porres Hospital, Eikwe | Eikwe |  |  |  |  |  |  | 9,000,000 |  |  | CENTRAL ADMIN. | GNPC |
|  |  |  | - Complete the construction of NHIS Office at Nkroful | Nkroful |  |  |  |  | 500,000 |  |  |  |  | CENTRAL ADMIN. | NHIS |
|  |  |  | - Conduct public health education and organize campaigns on mental health | District Wide |  |  |  |  | 1,500 | 8,000 |  |  |  | GHS | SWCD,Religious groups |
|  |  |  | - Support to organize capacity building programmes for Health Staff for effective monitoring and evaluation | District Wide |  |  |  |  | 15,500 |  | 22,000 |  |  | GHS | NGO |
| HEALTH AND HEALTH SERVICE DELIVERY | Primary Healthcare Delivery |  | - Distribute 2500 insecticide treated mosquito nets | District Wide |  |  |  |  | 2,250 | 8,500 |  |  |  | GHS | CENTRAL ADMIN. |
|  |  |  | - Promote ante/post natal services and organize district health wide health screening activities. | District Wide |  |  |  |  | 7,500 |  | 4,000 |  |  | GHS | CENTRAL ADMIN. |
|  |  |  | - Continue the administration of vaccines under the NID programme | District Wide |  |  |  |  | 3,000 | 6,000 | 2,000 |  |  | GHS | CENTRAL ADMIN. |
|  |  |  | - Organize District wide Health Screening | District Wide |  |  |  |  |  | 12,000 | 33,000 |  |  | GHS | NGOs |
|  |  |  | - Embark on quarterly regenerative health and nutrition outreach programmes | District Wide |  |  |  |  | 12,125 | 5,000 |  |  |  | GHS | CENTRAL ADMIN. |
| HEALTH AND HEALTH SERVICE DELIVERY | HIV, AIDS/STIs and other infections |  | - Intensify comprehensive education on HIV/AIDS and STIs, including reduction of stigmatisation | District wide |  |  |  |  | 6,625 |  | 6,250 |  |  | GHS | NGOs |
|  |  |  | - Organize quarterly HIV/AIDS Committee Meetings and world AIDS day. | Nkroful |  |  |  |  | 11,000.00 |  |  |  |  | DAC | GHS |
|  |  |  | - Counsel and test for HIV in all pregnant women | District wide |  |  |  |  | 7,575 |  | 1,020 |  |  | GHS | CENTRAL ADMIN. |
|  |  |  | - Organize HIV/AIDS and TB campaigns in schools | District wide |  |  |  |  | 7,500 |  |  |  |  | GHS | GES |
|  | Population Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | - Ensure registration of all birth and death in the district | District wide |  |  |  |  |  | 1,000 |  |  |  | Birth & death Dept. | CENTRAL ADMIN. |
|  |  |  | - Organize quarterly sensitization programmes on teenage pregnancy and child marriage | District wide |  |  |  |  |  | 19,100 |  |  |  | SWCD | CENTRAL ADMIN./NCCE |
|  |  |  | - Provide support for family planning activities | District wide |  |  |  |  | 5,000 |  | 2,000 |  |  | GHS | CENTRAL ADMIN. |
| HEALTH AND HEALTH SERVICE DELIVERY | Food and Nutrition |  | - Organize food and nutrition campaign in schools and health centres and on radio | District wide |  |  |  |  |  | 13,000 | 2,000 |  |  | GHS/EHSU | CENTRAL ADMIN. |
|  |  |  | - Monitor the school feeding programme to ensure quality and well-balanced diet is served | District wide |  |  |  |  | 10000 | 3000 |  |  |  | Central Admin | CENTRAL ADMIN. |
| WATER AND ENVIRONMENTAL SANITATION | Water Supply, Waste Management and Environmental Sanitation |  | - Drilling of 10No. Disability friendly Mechanized boreholes | Selected communities and health facilities |  |  |  |  | 250,000 |  | 10,000 |  |  | CENTRAL ADMIN. | DWST |
|  |  |  | - Completion, Construction/ Extension of water supply for selected communities | Nkroful, Kamgbuli,Asomase, Teleku Bokazo new and old Bakanta, Asanta, Kwesikrom, Sanzule |  |  |  |  | 200,000 | 100,000 |  |  |  | CENTRAL ADMIN. | DWST |
| WATER AND ENVIRONMENTAL SANITATION | Water Supply, Waste Management and Environmental Sanitation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | - Prepare, and implement the District Water and Sanitation Plan | District Assembly |  |  |  |  |  | 8,500 |  |  |  | DWST | CENTRAL ADMIN. |
|  |  |  | - Form and train 10No. WATSan Committees | Selected Communities |  |  |  |  | 15,000 |  |  |  |  | DWST | CENTRAL ADMIN. |
|  |  |  | - Implement the CLTS programme and intensify environmental health education campaigns | District wide |  |  |  |  | 25,000 |  |  |  |  | EHSU | CENTRAL ADMIN. |
|  |  |  | - Completion/ Construction of slaughter slabs at market places | Aiyinasi, Esiama, Assasetre |  |  |  |  | 2,500,000 |  |  |  |  | CENTRAL ADMIN. | EHSU |
|  |  |  | - Conduct screening of food vendors | District wide |  |  |  |  | 7,500 | 5,000 |  |  |  | EHSU | GHS, CENTRAL ADMIN. |
|  |  |  | - Support the Conveyance/ waste management activities | District wide |  |  |  |  | 320000 |  |  |  |  | EHSU | CENTRAL ADMIN. |
|  |  |  | - Monitor waste collection by zoomlion | Market Places |  |  |  |  |  | 10,000 |  |  |  | EHSU | CENTRAL ADMIN. |
|  |  |  | - Procure a cespit emptier | District Assembly |  |  |  |  |  |  |  |  |  |  |  |
| GENDER, CHILDREN AND SOCIAL PROTECTION | Child Protection and Youth Development |  | - Mobilize and sensitize 10 communities on parental responsibilities | District Wide |  |  |  |  |  | 25,000 |  |  |  | CENTRAL ADMIN. | GES, SWCD, NCCE |
|  |  |  | - Enforce child right and Gender related Bye laws | District Wide |  |  |  |  |  | 25,000 |  |  |  | SWCD | GES, NCCE,DA, Police etc. |
|  |  |  | - Monitor Day Care Centres and orphanages within the district | District Wide |  |  |  |  | 5,000 | 2,000 |  |  |  | SWCD | CENTRAL ADMIN. |
|  |  |  | - organize sensitization programmes on child protection issues | District Wide |  |  |  |  |  | 13,000 UNICEF |  |  |  | SWCD | CENTRAL ADMIN., NCCE, LABOUR DEP'T, NCCE |
|  |  |  | - Institute Child Protection Committees in 20 Communities | District wide |  |  |  |  |  | 5,000 UNICEF |  |  |  | SWCD | CENTRAL ADMIN. |
|  |  |  | - Settle child maintenance cases Organize community engagements and behavioural change campaigns to promote positive parenting | District wide |  |  |  |  |  | 5,000 UNICEF |  |  |  | SWCD | UNICEF |
|  |  |  | - Organize girls empowerment summits in Senior High Schools and create a pool of potential female leaders | District wide |  |  |  |  |  | 17,000.00 |  |  |  | SWCD | GES |
|  |  |  | - Establish adolescent clubs in schools and communities | District wide |  |  |  |  |  | 3,500 | 3,000 |  |  | SWCD | Gender Desk |
|  | Support for the Aged |  | - Create a database on the aged and support the Ellembelle Elderly Care Centre with Food Items | Ampain |  |  |  |  | 8,000 |  | 2,400 |  |  | DPU | CENTRAL ADMIN. |
|  | Women empowerment |  | - Organize quarterly sensitization Campaigns on gender-based violence and other harmful cultural practices | District Wide |  |  |  |  | 10,000 |  | 3,500 |  |  | SWCD/DPCU | CENTRAL ADMIN. |
|  |  |  | - Organize skills training for 1000 women | District Wide |  |  |  |  |  | 20,000 | 5,000 |  |  | SWCD | CENTRAL ADMIN., GEA |
|  | Social Protection |  | - Mobilize indigenes and vulnerable people for NHIS registration | District Wide |  |  |  |  | 10,000 |  |  |  |  | SWCD | NHIS, CENTRAL ADMIN. |
|  |  |  | - Construct 5No. Disability friendly Community parks | District wide |  |  |  |  | 300,000 |  |  |  |  | Works Dept. | Sport Committee |
|  |  |  | - Support People with Disabilities (PWDs) with training skills, items, cash, school fees medical bills and start-up capital. | District Wide |  |  |  |  | 200,000.00 |  |  |  |  | SWCD | GEA, CENTRAL ADMIN. |
|  |  |  | - Monitor and support the Livelihood Empowerment Against Poverty (LEAP) programme | District wide |  |  |  |  | 10,000 |  |  |  |  | SWCD | CENTRAL ADMIN. |
|  |  |  | Goal 3: Safeguard the Natural Environment and Ensure A Resilient Built Environment |  |  |  |  |  |  |  |  |  |  |  |  |
| NATURAL RESOURCE MANAGEMENT | Mineral Extraction |  | - Arrest and prosecute illegal, sand winners, miners, lumbers | District Wide |  |  |  |  | 30,000 | 30,000.00 |  |  |  | Security Agencies | EHSU,CENTRAL ADMIN. |
|  |  |  | - Establish a community mining scheme in 3 communities. | Salma, Teleku Bokazo, Nkroful |  |  |  |  |  | 6,000 | 3,000 |  |  | Works Dept. | DA |
|  |  |  | - Ensure the reclamation of degraded land after mining | Mining communities |  |  |  |  |  | 100,000 | 100,000 |  |  | PPD | CENTRAL ADMIN. |
|  | Coastal and Marine Erosion |  | - Revive conservation committee groups and build women capacity in conservation | District Assembly |  |  |  |  | 5,000 |  |  |  |  | DPU | CENTRAL ADMIN. |
|  | Deforestation, Desertification and Soil Erosion |  | - Develop landfill site into a modern engineered site | Ala Bokazo |  |  |  |  | 300,000 |  |  |  |  | EHSU | PPD, EPA |
|  |  |  | - Protect natural reserves (mangroves and forest) and recreation areas from encroachment | District Wide |  |  |  |  | 26,500 | 15,000.00 |  |  |  | Forestry | Works/NADMO/PPD |
| CLIMATE CHANGE AND DISASTER RISK REDUCTION | Climate Variability and Change |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | - Organize Capacity Building Training in Climate Change for DPCU/HODS Members | District Assembly |  |  |  |  |  |  | 6,500 |  |  | Agri Dept. | CENTRAL ADMIN. |
|  |  |  | - Train farmers on climate smart agriculture technologies | District wide |  |  |  |  | 5,000 |  |  |  |  | Agric .Dept. | MOFA |
|  |  |  | - Complete the construction of town roads | Esiama- Nkrofu- Bokazo Eikwe, Sanzule, Baku, Ngalekyi, Bobrama, Aiyinase South, Aiyinase North, and others |  |  |  |  | 2,000,000 |  |  |  |  | GHA, Dep't of Feeder Roads | CENTRAL ADMIN. |
|  |  |  | - Develop of Modern lorry parks and stores at Aiyinase and Esiama | Aiyinase, Esiama |  |  |  |  |  | 100,000 |  |  |  | GHA | CENTRAL ADMIN. |
|  |  |  | - Support road safety activities in the District | District Wide |  |  |  |  | 120,000.00 |  |  |  |  | GHA | CENTRAL ADMIN. |
| CLIMATE CHANGE AND DISASTER RISK REDUCTION | Information Communication Technology |  | - Rehabilitate existing post offices | Aiyinase, Nkroful Esiama |  |  |  |  |  | 200,000 |  |  |  | Works dept | CENTRAL ADMIN. |
|  |  |  | - Renovation of ICT Centre at Aiyinase and Install Wi-Fi at the District Assembly Office | Aiyinase Nkroful |  |  |  |  | 64,500 | 54,200 |  |  |  | ICT Dept. | GIFEC |
|  | Human Settlements Development and Housing |  | - Organize technical and statutory planning committee meetings | District Assembly |  |  |  |  |  | 12,000 |  |  |  | PPD | HODs |
|  |  |  | - Preparation of local plans | Bomoakpole |  |  |  |  |  | 20,000 |  |  |  | PPD | CENTRAL ADMIN. |
|  |  |  | - Sensitization of the public on Land use planning and permitting | District Wide |  |  |  |  |  | 3,000 |  |  |  | PPD | Works Dep't, CENTRAL ADMIN. |
|  |  |  | - Organize joint inspections to check unauthorised developments | District Wide |  |  |  |  |  | 20,000.00 |  |  |  | PPD | Works Dep't, CENTRAL ADMIN. |
|  |  |  | - Construction of 5No. Community Centres | New Bakanta, Adurim, Aiyinasi North and others |  |  |  |  | 780,000 |  |  |  |  | CENTRAL ADMIN. | COCOBOD |
|  | Drainage and Flood Control |  | - Prepare and implement drainage plans for flood prone areas | District Assembly |  |  |  |  |  | 5,000 |  |  |  | PPD | Works Dep't, CENTRAL ADMIN. |
|  |  |  | - Construct and frequently desilt chocked drains | District Assembly |  |  |  |  | 200,000.00 | 20,000 |  |  |  | EHSU | PPD,WORKS,NADMO |
| CLIMATE CHANGE AND DISASTER RISK REDUCTION | Infrastructure Maintenance |  | - Organize capacity building training in inventory and asset management for selected staff | District Assembly |  |  |  |  |  | 7,000 |  |  |  | HR | CENTRAL ADMIN. |
|  |  |  | - Prepare operation and maintenance (O&M) Plan | District Assembly |  |  |  |  | 5,000 |  |  |  |  | Works Dep't | Dev't Planning Unit |
|  |  |  | - Undertake building inspections and ensure that all public buildings are disability friendly | District wide |  |  |  |  |  | 10,000 |  |  |  | Works Dep't | CENTRAL ADMIN. |
|  |  |  | Goal 4: Maintain a Stable, United and Safe Society |  |  |  |  |  |  |  |  |  |  |  |  |
| DEMOCRACY, GOVERNANCE AND PUBLIC ACCOUNTABILITY | Resource Mobilization and Expenditure Management |  | - Update economic/ Tourism data to improve revenue | District wide |  |  |  |  | 100,000.00 |  |  |  |  | Statistical Dept. | Revenue Unit,DPO, PPD, Budget |
|  |  |  | - Provide revenue collection and management logistics | District Assembly |  |  |  |  | 12,000 |  |  |  |  | Revenue Unit | GIZ, CENTRAL ADMIN. |
|  |  |  | - Organize public sensitization on revenue mobilization in market places and lorry stations | Aiyinase, Asasetre, Esiama, Teleku Bokazo |  |  |  |  |  | 7,500 |  |  |  | Revenue Unit | Budget/Finance, Works, PPA, NCCE |
|  |  |  | - Mount and update revenue performance and Accountability Bill Boards at the Various Area Councils | Esiama, Asasetre, Awiebo Basake, Aiyinase, Kikam, Nkroful, Atoabo |  |  |  |  | 22,000 |  |  |  |  | Fin. Dep't | CENTRAL ADMIN. |
|  |  |  | - Prepare and Implement a Revenue Improvement Action Plan and Concept note | District Assembly |  |  |  |  | 5,000.00 | 7,000 |  |  |  | DBU | DPO, Fin Dept |
| Democracy, Governance and Public Accountability | Local Government and Decentralization |  | - Completion/furnishing /Construction of Area Council Office | Asasetre, Nkroful. Atuabo, Kikam |  |  |  |  | 500,000.00 | 500,000 .00 |  |  |  | CENTRAL ADMIN. | WORKS/DPO |
|  |  |  | - Support and build the capacity of women to contest for political positions | District Wide |  |  |  |  | 4,500 |  | 6,000 |  |  | NCCE | CENTRAL ADMIN. |
|  |  |  | - Secure/furnish office accommodation for area councils | District Assembly |  |  |  |  | 100,000.00 |  |  |  |  | Planning | Finance, CENTRAL ADMIN. |
|  |  |  | - Coordinate the preparation of Community Action Plans | District Assembly |  |  |  |  | 10,000.00 |  |  |  |  | Dev't Planning/PP | HODs |
|  |  |  | - Review and prepare Annual Action Plans, Composite Budgets, Procurement plans | District Assembly |  |  |  |  | 50,000.00 |  |  |  |  | Planning, Budget Unit, Procurement | HODs |
|  |  |  | - Undertake Town Hall Meetings on AAPs, fee-fixing and composite annual budget | All Area Council Offices |  |  |  |  | 50,000 | 10,000.00 | 5,000 |  |  | Dev't Planning/Budget | HODs, CENTRAL ADMIN. |
|  |  |  | - Organize all statutory meetings and celebration of days | District Assembly |  |  |  |  | 90,000.00 | 20,000.00 | 80,000.00 |  |  | Central Admin | Adamus, Ghana Gas, ENI, etc |
| Democracy, Governance and Public Accountability | Local Government and Decentralization |  | - Administer comprehensive HRMIS and submit monthly returns to RCC | District Assembly |  |  |  |  |  | 4,000 |  |  |  | HR | HODs |
|  |  |  | - Organize capacity building training for revenue collectors and Area Council members on effective revenue mobilization | District Assembly |  |  |  |  |  | 40,000.00 |  |  |  | HR/DPU | NGO |
|  |  |  | - Organize capacity building training for all staff and Assembly members | District Assembly |  |  |  |  | 35,000 |  |  |  |  | HR | Fin. Dep't, HODs |
|  |  |  | - Procure office stationery, logistics, Vehicles and others | District Assembly |  |  |  |  | 600,000.00 |  |  |  |  | Procurement | CENTRAL ADMIN. |
|  |  |  | - Maintenance of Assembly Accommodation, vehicles, computers and other logistics | District Assembly |  |  |  |  | 100,000.00 | 100,000.00 |  |  |  | Procurement | CENTRAL ADMIN. |
| Democracy, Governance and Public Accountability | Human Security and Public Safety |  | - Construction of Police Station | Dadwen |  |  |  |  |  | 350,000 |  |  |  | CENTRAL ADMIN. | GPS |
|  |  |  | - Form 4No. Neighbourhood watchdog committees | Selected Communities |  |  |  |  |  | 5,000 |  |  |  | GPS | CENTRAL ADMIN. |
|  |  |  | - Conduct fire safety inspections at all public places | Selected premises |  |  |  |  | 20,000 |  |  |  |  | GNFS | CENTRAL ADMIN., NADMO |
|  | Corruption and Economic Crimes |  | - Support all activities of the Audit unit including audit committees | District Assembly |  |  |  |  | 40,000 |  |  |  |  | Internal Audit | External Audit |
|  |  |  | - Ensure that all HODs complete the Assets Declaration Form | District Assembly |  |  |  |  |  | 5,000 |  |  |  | CENTRAL ADMIN. |  |
|  | Law and Order |  | - Lobby for the posting of more Police Personnel into the district | District Assembly |  |  |  |  |  | 20,000 |  |  |  | DISEC | GPS |
|  |  |  | - Support the Police Service, fire service, ambulance service, immigration, BNI | District Assembly |  |  |  |  | 30,000 | 5,000 |  |  |  | DISEC | All security agencies |
|  |  |  | - Organize DISEC Meetings | District Wide |  |  |  |  |  | 60,000.00 |  |  |  | Central Admin | CENTRAL ADMIN. |
| Democracy, Governance and Public Accountability | Civil Society and Civic Engagement |  | - Collaborate with NGO to implement the Youth inclusive development programme | District Assembly |  |  |  |  |  | 4,000 | 2,500 |  |  | DPU | NGO |
|  |  |  | - Attend Nzema Maanle TC Meetings to engage TAs on the works of the Assembly | Ampain |  |  |  |  |  | 5,500 |  |  |  | DPU | CENTRAL ADMIN. |
|  |  |  | - Support Religious activities | District Wide |  |  |  |  | 21,800 |  |  |  |  | CENTRAL ADMIN. |  |
|  |  |  | - Collaborate with Youth Bridge to implement youth involvement programme | District Wide |  |  |  |  |  | 10,200 |  |  |  | DPU | CENTRAL ADMIN. |
|  | Culture |  | - Organize story telling competition in Nzema and Fanti and cultural festivals for basic schools | Selected Schools |  |  |  |  | 12,000 |  |  |  |  | GES | CENTRAL ADMIN. |
|  |  |  | Goal 5: Mainstream Emergency Planning and Preparedness Into Ghana’s Development Planning Agenda At All Levels To Respond To Potential Internal And External Threats (Including Covid-19 |  |  |  |  |  |  |  |  |  |  |  |  |
| EMERGENCY PLANNING AND RESPONSE (INCLUDING COVID-19 RECOVERY PLAN) | Hydrometeological Threats |  | - Organize community sensitizations on disaster prevention | District Wide |  |  |  |  | 12,500 |  |  |  |  | NADMO | CENTRAL ADMIN., NCCE |
|  |  |  | - Organize pests and insect infection sensitization campaign in communities | District Wide |  |  |  |  |  | 6,000 | 4,500 |  |  | NADMO | MOFA, NCCE |
|  |  |  | - Formation of Disaster Risk Reduction clubs in schools and communities | Selected Schools |  |  |  |  |  | 8,000 |  |  |  | NADMO | GES, CENTRAL ADMIN. |
|  |  |  | - Organize DRR training programmes at zonal levels | District Wide |  |  |  |  |  | 2,000 | 3,000 |  |  | NADMO | GNFS, CENTRAL ADMIN. |
|  |  |  | - Supply stationery and logistics to NADMO | District Assembly |  |  |  |  | 8,000 |  |  |  |  | CENTRAL ADMIN. | REG/NAT NADMO |
|  |  |  | - Train Area Council Members and Traditional Authorities on impact of sand winning and galamsey on the environment | District Wide |  |  |  |  |  | 16,000 |  |  |  | NADMO | CENTRAL ADMIN., NCCE |
| EMERGENCY PLANNING AND RESPONSE (INCLUDING COVID-19 RECOVERY PLAN) | Biological Threats |  | - Undertake surveillance, monitoring and evaluation of Health threats and epidemics and pandemics | District Wide |  |  |  |  |  | 10,000 |  |  |  | DHD | NCCE |
|  | Anthropogenic Threats |  | - Support National Ambulance Service | District Wide |  |  |  |  |  | 15,000 |  |  |  | GHS | CENTRAL ADMIN. |
|  |  |  | - Intensify monitoring at Filling Stations to ensure adherence to Standard Operating Procedures. | District Wide |  |  |  |  |  | 6,000 |  |  |  | GNFS | Security agencies |
|  |  |  | - Establish a well-resourced Emergency Centre | District Wide |  |  |  |  |  | 50,000 | 70,000 |  |  | CENTRAL ADMIN. | Private Sector/GHS |
|  | Security |  | - Organize Annual ADR week Celebration | District Wide |  |  |  |  |  | 6,000 |  |  |  | CENTRAL ADMIN. |  |
|  |  |  | - Create awareness on the consequences of ethnic and chieftaincy conflicts | District Wide |  |  |  |  |  |  | 4,500 |  |  | NCCE | CENTRAL ADMIN., ETC |
| EMERGENCY PLANNING AND RESPONSE (INCLUDING COVID-19 RECOVERY PLAN) | Covid-19 Response |  | - Conduct sensitization on pandemics and implement a recovery Plan | District Wide |  |  |  |  |  | 6,000 |  |  |  | DHD | NCCE |
|  |  |  | - Support Public Health Emergency Management Committee | District Wide |  |  |  |  | 10,000 | 4,800 |  |  |  | CENTRAL ADMIN. | DHD |
|  |  |  | - Vaccinate 50,000 people against covid-19 and other pandemics. | District Wide |  |  |  |  |  | 35,000 |  |  |  | DHD | CENTRAL ADMIN. |
|  |  |  | Goal 6: Improve Delivery of Development Outcomes at all Levels |  |  |  |  |  |  |  |  |  |  |  |  |
| Implementation, Coordination, Monitoring and Evaluation | Implementation and Coordination |  | - Preparation New MTDP (2026-2030) | District Assembly |  |  |  |  | 80,000 | 45,000 |  |  |  | Dev't Planning | HODs |
|  |  |  | - Organize Capacity Building programme for DPCU members and HODs | District Assembly |  |  |  |  | 6,000 | 2,500 |  |  |  | Dev't Planning | HODs |
|  | Monitoring and Evaluation |  | - Organize quarterly Participatory Project Monitoring | District Assembly |  |  |  |  | 120,000 |  |  |  |  | Dev't Planning | HODs, CENTRAL ADMIN. |
|  |  |  | - Organize Quarterly M&E/ AAP Review Meetings | District Assembly |  |  |  |  | 12,000 | 5,000 |  |  |  | Dev't Planning | HODs |
| Production And Utilisation of Statistics | Data-Based Planning and Budgeting |  | - Establish District Statistical Working Group and train Field Officers | District Assembly |  |  |  |  | 2,000 | 2,000 |  |  |  | Statistical Dept. | HODs |
|  |  |  | - Establish and update Central Database for Planning and Budgeting | District Assembly |  |  |  |  | 10,000 |  |  |  |  | Statistical Dept. | HODs |
|  |  |  | - Support the GSS to collect population data | District wide |  |  |  |  | 30,000 |  |  |  |  | Statistical Dept. | CENTRAL ADMIN. |
|  |  |  | - Conduct Monthly Market Survey | District Assembly |  |  |  |  | 5,000 | 2,500 |  |  |  | Statistical Dept. | HODs |
|  |  |  | - Disseminate statistical Data and projections with Relevant Units, Departments and Agencies in the District. | District Assembly |  |  |  |  | 10,000 |  | 5,000 |  |  | Statistical Dept. | HODs |

# CHAPTER SIX

# MONITORING AND EVALUATION PLAN

## Introduction

The recognition that resources are limited and the ever-rising expectations from citizens for better services are enough reasons for the district to find most cost-effective options to meeting these demands with the available resources.

This chapter focuses on the processes involved in conducting Monitoring and Evaluation and disseminating and communication strategy during the implementation of the DMTDP 2018-2021.

## Purpose of the M&E Plan

The Monitoring and Evaluation (M&E) arrangement is primarily meant to institute an effective and efficient system for tracking the progress of programmes and projects in the District Medium Term Development Plan (2018-2021) by the DPCU and other stakeholders. It provides a clear direction on how specific activities within the MTDP will be measured. Aside providing useful lessons to aid in programme / project implementation, it would also enhance stakeholders’ accountability.

## Monitoring

Monitoring is the systematic process of collecting, analyzing and using information to track a programme’s progress toward reaching its objectives and to guide management decisions.  Monitoring usually focuses on processes such as when and where activities occur, who delivers them and how many people or entities they reach.

Monitoring also ensures that, at any given stage of a project, the required inputs are delivered on time, used as intended and is producing the desired results. Since plans are affected by uncontrollable situations such as socio-economic changes, political climate and international relations, it is necessary that they are constantly monitored and adjustments made accordingly. The monitoring scheme is designed for the annual plan. In the scheme, three (3) activities occur:

- Monitoring activities cover the implementation period.

(ii)	On-going evaluation occurs at specific points within the implementation phase.

(iii)	Terminal evaluation occurs at specific end of the project implementation.

    - Monitoring Matrix

The Monitoring and Evaluation Matrix shows the linkage of the Medium Term Development Plan to the Goals of the NMTDPF 2018-2021. The matrix provides a format for presenting the input, output, and outcome and impact indicators of each of the MTDP objective.

The matrix has the Goals of the NMTDPF 2018-2021 as well as the indicators, indicator type and the baseline for 2017. Others are the targets for 2018, 2019, 2020 and 2021, the data disaggregation, monitoring frequency and whose responsibility it is to supply the data. The indicator type, be they input, output, process or outcome ones are all stated. The monitoring matrix for the Ellembelle District Assembly is presented in the table below:

Table 6. 1: monitoring and evaluation indicator

| Indicators | Indicator Definition | Indicator Type | Baseline 2021 | Targets |  |  |  | Disaggregation | Monitoring Frequency | Responsibility |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | 2022 | 2023 | 2024 | 2025 |  |  |  |
| GOAL 1: Build a Prosperous Society |  |  |  |  |  |  |  |  |  |  |
| Programme 1: Economic Development Sub- Programme 1: Resource Mobilization |  |  |  |  |  |  |  |  |  |  |
| Percentage increase in IGF | Percentage increase in IGF collection | Output | 25% | 30% | 30% | 30% | 30% |  | Annually | Budget Unit |
| Programme 1: Economic Development Sub- Programme 2: Expenditure Management |  |  |  |  |  |  |  |  |  |  |
| Percentage of financial irregularities in Audit Report | Amount of financial irregularities as a percentage of total expenditure | Process | 2% | 0% | 0% | 0% | 0% |  | Annually | Finance Dep’t |
| No. of new industries established | No. of industries established | Output | 0 | 0 | 1 | 1 | 1 |  | Annually | Private Sector |
| Programme 1: Economic Development Sub- Programme 3: Private Sector Development |  |  |  |  |  |  |  |  |  |  |
| No. of businesses supported | No. of businesses supported with training and capital | Output | 300 | 250 | 250 | 350 | 150 | Small and medium scale businesses | Yearly | GEA |
| No of new jobs created | Jobs created to reduce unemployment | output | 272 | 300 | 320 | 340 | 360 |  | Yearly | GEA. NABCO, YEA, HR, FORESTRY, AGRIC |
| Percentage of youth/SMEs supported with start-up kits | youth/SMEs supported with start-up kits expressed as percentage | Impact | 30% | 10% | 10% | 10% | 10% | Males and females, Small and micro businesses | quarterly | GEA, SW, AGRIC |
| Number of youths supported to undergo apprenticeship training | Count of youth supported to successfully undergo apprenticeship training | output | 12 | 25 | 25 | 25 | 25 | Sex | Annually | GEA |
| Programme 1: Economic Development Sub- Programme 4: Agriculture and Rural Development |  |  |  |  |  |  |  |  |  |  |
| Percentage increase in yield of selected crops | Total quantity of selected crops, livestock and poultry produced in the district in a given year as a percentage of the previous year’s production Maize Rice Cassava Yam Cocoyam Plantain Cattle Sheep Goat Pig Poultry | Outcome | 3,160.72 1,984.32 87,818.34 194.32 432.57 3,986.24 15.58 28.82 24.5 31.3 78.83 | 30% 30% 30% 30% 30% 30% 30% 30% 30% 30% 30% | 30% 30% 30% 30% 30% 30% 30% 30% 30% 30% 30% | 30% 30% 30% 30% 30% 30% 30% 30% 30% 30% 30% | 30% 30% 30% 30% 30% 30% 30% 30% 30% 30% 30% |  | Annually | Agric. Department |
| Percentage of arable land under cultivation | Agriculture lands in use | Outcome | 60% | 65% | 70% | 75% | 80% |  | Yearly | AGRIC |
| No. of Agro-processing facilities established | No. of agro-processing facilities established and functioning | output | NIL | 1 | 1 |  |  | Rural | Quarterly | Agric, GEA |
| Farmer Extension Agent Ratio | Ratio of farmers reached by Agric-Extension Agents | Outcome |  |  |  |  |  | Male/Female | Annually | Agric. Dep’t |
| Programme 1: Economic Development Sub- Programme 4: Tourism and Creative Arts Development |  |  |  |  |  |  |  |  |  |  |
| No. of tourism clubs formed | No. of tourism clubs formed in schools | Output | 0 | 2 | 3 | 3 | 2 |  | Annually | Culture |
| No. of tourist sites developed | No. of tourist sites developed | output | 0 | 0 | 1 | 0 | 0 |  | Annually | GEA, DA |
| GOAL 2: Create Opportunities for All |  |  |  |  |  |  |  |  |  |  |
| Programme 2: Education and Training Sub- Programme 1: Pre-Tertiary Education |  |  |  |  |  |  |  |  |  |  |
| Gender Parity index KG Primary JHS SHS | Ratio between boys and girls | outcome | 1 1 1 0.93 | 1 1 1 1 | 1 1 1 1 | 1 1 1 1 | 1 1 1 1 | Males and females | Annually | GES |
| Pass rate JHS SHS | Count of final exams takers (girls and boys) who passed a particular exam over a total count of final exam takers in that same exams expressed as a percentage | outcome | 68% 73% | 100% 100% | 100% 100% | 100% 100% | 100% 100% | Males and females | Annually | GES |
| Net enrolment ratio; KG PRIM JHS | Number of appropriately aged pupils/students enrolled in school as a proportion of children in relevant age group | Outcome | 84% 63% 81% | 100% 100% 100% | 100% 100% 100% | 100% 100% 100% | 100% 100% 100% | Males and females | Annually | GES |
| Number of Students awarded scholarships and D/A supports | Count of students benefiting from government scholarship and D/A support | Input | 23 | 50 | 50 | 50 | 50 | Sex | Annually | DA, GES |
| Completion rate; Primary-District Boys Girls JHS –District Boys Girls | Proportion of pupils/students who remain and complete school after enrolment | outcome | 89% 97% 87% 97% | 100% 100% 100% 100% | 100% 100% 100% 100% | 100% 100% 100% 100% | 100% 100% 100% 100% | Males and females | Annually | GES |
| Programme 3: Health and Health Service Delivery Sub-Programme 1: Primary Health Care Delivery |  |  |  |  |  |  |  |  |  |  |
| No. of operational health facilities CHPS Clinic Health Centre Hospital | No. of health facility functioning | output | 28 6 7 1 | 30 6 7 1 | 32 7 8 1 | 34 8 9 2 | 36 9 10 2 | Urban and rural | Quarterly | DA/GHS |
| Proportion of population with valid NHIS card | The population with valid NHIS card, expressed as a percentage of total district population | output | 38% | 40% | 45% | 50% | 60% | Sex, Age, | Yearly | NHIA/GHS |
| Number of registered Births Deaths | Count of births and deaths registered in the district in a particular year | output | 4,947 386 | 100% 100% | 100% 100% | 100% 100% | 100% 100% | Sex, Age | Annually | Birth and Death Department, GHS |
| Under five mortality Rate | number of deaths occurring between birth and exact age five per 1000 live births | Outcome | 0 | 0% | 0% | 0% | 0% | Males and females | Annually | DA/GHS |
| Malaria case fatality | Malaria case fatality in children under five years per 10000 population | Outcome | 0 | 0% | 0% | 0% | 0% | Males and females | Annually | GHS |
| Programme 3: Health and Health Service Delivery Sub-Programme 2: HIV, AIDS/STIs and other infections |  |  |  |  |  |  |  |  |  |  |
| HIV/AIDS Prevalent rate | HIV/AIDS Prevalent rate (% adult population 15-49 years HIV positive) | outcome | 9% | 7% | 5% | 3% | 0% | Males and females | Annually | GHS |
| Programme 4: Population Management and Migration for Development Sub-Programme 1: Population Management |  |  |  |  |  |  |  |  |  |  |
| Percentage of family planning acceptors | Total population | Outcome | 31% | 33% | 35% | 37% | 41% | Males and females | Annually | GHS |
| Programme 4: Population Management and Migration for Development Sub-Programme 2: Maternal and Adolescent Reproductive Health |  |  |  |  |  |  |  |  |  |  |
| Maternal Mortality ratio | Maternal deaths recorded per 100,000 live births in the district | Outcome | 60.6/100,000 | 0% | 0% | 0% | 0% |  | Annually | DA/GHS |
| Percentage of Supervised Deliveries | Proportion of pregnant women assisted by a skilled birth attendant (midwife) and monitored with a pantograph | outcome | 70.70% | 100% | 100% | 100% | 100% |  | Annually | GHS |
| Antenatal Coverage | ANC registrants over expected pregnancy | outcome | 79% | 80% | 81% | 81% | 82% | Males and females | Semi-annually | GHS |
| Programme 6: Water and Environmental Sanitation Sub-Programme 1: Potable Water Supply |  |  |  |  |  |  |  |  |  |  |
| Proportion of Population with sustainable access to safe water sources | Share of the district population with access to basic drinking water services expressed as a percentage of total district population | outcome | 85% | 90% | 92% | 95% | 98% | Urban and rural | Quarterly | DWST/DEH |
| No. of functioning water facilities | Water facilities working all year round | output | 126 | 130 | 136 | 140 | 146 | Urban and rural | Annually | Works/DWST |
| Programme 6: Water and Environmental Sanitation Sub-Programme 2: Waste Management and Environmental Sanitation |  |  |  |  |  |  |  |  |  |  |
| Proportion of population with access to improved sanitation services | Share of population with access to basic sanitation services expressed as a percentage of total district population | outcome | 47% | 49% | 51% | 53% | 55% | Urban and rural | Quarterly | DEH/DWST |
| Programme 7: Gender, Children and Social Protection Sub-Programme 1: Child Protection |  |  |  |  |  |  |  |  |  |  |
| Number of recorded cases of - Child trafficking and abuse | Count of recorded cases of child trafficking and child abuse cases in the district | outcome |  |  |  |  |  | Sex | Annually | SWCD, Security services |
| Number of sensitization programmes on child protection organized | Count of sensitization programmes on child protection organized | process | 4 | 4 | 4 | 4 | 4 | Sex | Annually | SWCD,Security services |
| Number of women groups formed and supported | Count of women groups formed and supported | output | 1 | 1 | 1 | 2 | 1 | Sex | Annually | DSW&CD |
| Percentage increase in coverage of LEAP | Increase in LEAP beneficiary households | Input | 0% | 10% | 10% | 20% | 10% | Male and female | Annually | SWCD |
| Number of PWDs supported | Count of PWDs supported with training, capital etc. | Output | 32 | 50 | 50 | 50 | 50 | Male and female | Quarterly | SWCD |
| Proportion of case workers trained in child protection and family welfare | Percentage of case workers trained in child protection and family welfare | outcome | 4 | 10 | 15 | 20 | 30 | Male and female | Annually | SWCD |
| Number of child violence cases benefitting from social welfare/social services | Count of child violence cases benefitting from social welfare/social services | Output | 8 | 10 | 20 | 30 | 40 | Male and female | Annually | SWCD |
| Number of children reached by social work/social services | count of children reached by social work/social services | Output | 205 | 210 | 230 | 250 | 260 | Male and female | Annually | SWCD |
| Number of people reached with child protection and SGBV information | count of people reached with child protection and SGBV information | Output | 235 | 250 | 260 | 270 | 280 | Male and female | Annually | SWCD |
| Number of LEAP household members on NHIS | Count of LEAP household members on NHIS | Output | 1,400 | 1500 | 1600 | 1700 | 1800 | Male and female | Annually | SWCD |
| Number of children placed in foster care | Count of children placed in foster care | Output | 2 | 5 | 7 | 9 | 12 | Male and female | Annually | SWCD |
| Number of households with adolescent girls benefiting from LEAP Programme | Count of households with adolescent girls benefiting from LEAP Programme | Output | 500 | 520 | 550 | 600 | 650 | females | Annually | SWCD |
| GOAL 3: Safeguard the Natural Environment and Ensure Resilient Built Environment |  |  |  |  |  |  |  |  |  |  |
| Programme 8: Natural Resource Management Sub-Programme 1: Mineral Extension |  |  |  |  |  |  |  |  |  |  |
| Number of Community Mining Schemes established | Count of Community Mining schemes established in the district | Input | 0 | 1 | 1 | 2 | 0 |  | Annually | LMC |
| Hectares of degraded lands reclaimed | Hectares of lands degraded by illegal miners reclaimed in the district | output | 0 | 2 | 3 | 3 | 2 |  | Annually | EPA, LMC |
| Programme 8: Natural Resource Management Sub-Programme 2: Water Resource Management |  |  |  |  |  |  |  |  |  |  |
| Hectares of degraded mangrove vegetation restored | Hectares of mangrove vegetation illegally destroyed that have been restored | output | 6 | 7 | 8 | 10 | 5 |  | Annually | EPA, LMC, Conservation commiittees |
| Programme 9: Climate Change and Disaster Risk Reduction Sub-Programme 1: Climate Change and Variability |  |  |  |  |  |  |  |  |  |  |
| Number of trees planted and nurtured | Count of trees planted and being nurtured in the district | output | 1,500 | 5,000 | 5,000 | 5,000 | 5,000 | Sex | Annually | Security services |
| Programme 10: Resilient Built Environment Sub-Programme 1: Transport Infrastructure |  |  |  |  |  |  |  |  |  |  |
| Percentage of road network in good condition | The total km of classified road network in good condition expressed as percentage of total road network | Output | 57.40% | 60.5% | 68.0% | 78.5% | 82% | Urban and rural | Annually | DA/WORKS |
| Proportion or length of feeder roads (km) maintained/rehabilitated | Feeder roads maintained expressed as percentage of total feeder roads | Output | 24.7 | 30.0KM | 35KM | 50KM | 20KM | Rural | Annually | Works |
| Programme 10: Resilient Built Environment Sub-Programme 3: Human Settlement Development |  |  |  |  |  |  |  |  |  |  |
| No of new buildings with permits | No of new buildings with permits | Output | 36% | 45% | 55% | 65% | 75% | Urban and rural | Annually | PPD/Works |
| Percentage of communities with street names (NDPAS) | Communities with street lights expressed as percentage of total communities | Outcome | 7.3% | 10% | 15% | 20% | 25% | Urban and rural | Annually | PPD/ NABCO/ Works |
| Percentage of communities sensitized on permit compliance | Communities sensitized expressed as percentage of total communities | outcome | 65% | 70% | 75% | 80% | 85% | Urban and rural | Quarterly | PPD/WORKS |
| Programme 10: Resilient Built Environment Sub-Programme 4: Rural Development |  |  |  |  |  |  |  |  |  |  |
| Percentage of Communities with electricity | The number of communities in the district connected to the national grid divided by total number of communities in the district expressed as percentage | output | 76% | 80% | 88% | 95% | 100% | Urban and rural | Annually | DA/WORKS |
| GOAL 4: Maintain a Stable, United and Safe Society |  |  |  |  |  |  |  |  |  |  |
| Programme 11: Democracy, Governance and Public Accountability Sub-Programme 1: Democratic Governance |  |  |  |  |  |  |  |  |  |  |
| District Assembly Performance in District League Table | Score of D/A in the District League Table Rankings | output | 88% | 100% | 100% | 100% | 100% |  | Annually | Security |
| Programme 11: Democracy, Governance and Public Accountability Sub-Programme 2: Local Government and Decentralization |  |  |  |  |  |  |  |  |  |  |
| District Assembly Performance in DPAT Assessments | Score of D/A in the annual DPAT Assessment | output | 99% | 100% | 100% | 100% | 100% |  | Annually | Security |
| District Assembly Score in Performance Contract | Score of D/A in the Performance Contract Assessment | output | 92% | 100% | 100% | 100% | 100% |  | Annually | Security |
| Programme 11: Democracy, Governance and Public Accountability Sub-Programme 3: Human Security and Public Safety |  |  |  |  |  |  |  |  |  |  |
| Police Citizen Ratio | Police citizens ratio | output | 1:10,625 | 1:8,000 | 1:7000 | 1:4000 | 1:2500 | Male and female | Annually | Security |
| Reported cases of crime Total Children Women Men | Count of reported cases of major crimes including rape, armed robbery, defilement and murder recorder by Ghana Police in a given year | Output | 607 | 597 | 590 | 580 | 570 | Sex, Age | Annually | Security |
| GOAL 5: Mainstream emergency planning and preparedness into Ghana’s development planning agenda at all levels to respond to potential internal and external threats (including COVID-19) |  |  |  |  |  |  |  |  |  |  |
| Programme 12: Emergency Planning and Response Sub-Programme 1: Anthropogenic Threats |  |  |  |  |  |  |  |  |  |  |
| Number of communities affected by disaster | Count of communities affected by disaster | output | 23 | 5 | 5 | 5 | 5 | Urban/ Rural, Type | quarterly | NADMO/Forestry |
| Programme 12: Emergency Planning and Response Sub-Programme 2: Anthropogenic Threats |  |  |  |  |  |  |  |  |  |  |
| No. of people vaccinated against covid-19 | Total number of persons fully vaccinated against covid-19 | output | 3,500 | 50,000 |  |  |  | Urban and rural | quarterly | NADMO/Forestry |
| Goal 6: Improve delivery of development outcomes at all levels |  |  |  |  |  |  |  |  |  |  |
| Programme 12: Emergency Planning and Response Sub-Programme 1: Implementation and Coordination |  |  |  |  |  |  |  |  |  |  |
| Percentage of Annual Action Plan Implemented | Count of activities implemented divided by the total number of planned activities in a given year expressed as a percentage | Outcome | 72% | 80% | 82% | 84% | 85% | Development Dimensions | Quarterly | DPCU |
| Programme 12: Emergency Planning and Response Sub-Programme 2: Participatory Monitoring and Evaluation |  |  |  |  |  |  |  |  |  |  |
| No. of PM&E conducted | No of PM & E Conducted in a given year | output | 0 | 1 | 1 | 1 | 1 | Development Dimensions | Quarterly | DPCU |
| Programme 12: Emergency Planning and Response Sub-Programme 3: Evidence-based decision making |  |  |  |  |  |  |  |  |  |  |
| No of Monthly Market Surveys Conducted | No of monthly market surveys conducted in a given year | Process | 12 | 12 | 12 | 12 | 12 |  | Quarterly | DPCU |

## Stakeholders Analysis

Stakeholders are people with great influence and interest in the success of an organization. They are mainly classified into two (2) types; thus Primary and Secondary stakeholders. The Primary stakeholders of the District Assembly are those who are directly affected by the decisions made. They include; the District Chief Executive, the Member of Parliament the Assembly members, Unit Committee Members, the Community Members, Traditional Authority, the District Coordinating Director, Heads of Departments (HODs).

With regards to the secondary stakeholders, they are indirectly affected by the decisions of the District Assembly. Examples include; the National Development Planning Commission (NDPC), the Regional Co-ordinating Council, (RCC), Civil Society Organization (CSOs), Community Based Organization (CBOs), Media, Development Partners, Non-Governmental Organization (NGOs), Ministry of Local Government and Rural Development, Head of Local Government Service (OHLGS), DACF Secretariat, RCC, Private Sector, Consultants. Other stakeholders especially NGO’s, CBO’s all contribute in the development process of the District through their interventions.

At the District Assembly level, stakeholder participation is at both the plan and budget preparation stages. After the plans and budget are prepared, public hearings are organized at least once in a year in every area council to brief the stakeholders on the future plans of the Assembly and solicit for the citizenry contributions to enrich the process. The medium of communication is the Nzema language in order to enable almost everyone present understand and participate in the processes. Afterwards, other channels are employed for dissemination of the information. Some of the channels used are Community Radios and Public education by NCCE. These participatory decision making process helps in project ownership, judicious use of resources and project sustainability.

Below is Table 6.2 showing the major primary and secondary stakeholders of the District Assembly and their roles in the attainment of the development interventions in the Medium Term Development Plan (MTDP 2022-2025) and Table 6.3 showing the workplan for monitoring and evaluation for the plan period (2022-2025)

Table 6. 2: Stakeholder Analysis for the Conduct of Monitoring and Evaluation

| No. | Type of Stakeholder- (Primary) | Roles | Roles In M& E |
| --- | --- | --- | --- |
| 1 | District Assembly/ Assembly Members | Decision making, by-laws, deliberation and adoption of plans, approval of budget for programmes and projects. | M&E Plan preparation, M&E seminars & meetings, supervision, project inspection, evaluations, M&E results reporting and dissemination, etc. |
| 2. | Traditional Authorities | Advisory services, transparency and accountability, etc. | M&E seminars & meetings, supervision, project inspection, M&E results reporting and dissemination, etc. |
| 3 | The Community/Beneficiaries | Demand for information, and also give information on all developmental issues. They also monitor implementation of plans and use resources at all levels | Dissemination and Communication of M&E results, participatory monitoring, transparency, accountability, decision making |
| 4 | Member of Parliament | Decision making, common fund for programmes and projects, etc. | M&E seminars & meetings, supervision, project inspection, evaluations, M&E results reporting and dissemination, etc. |
|  | Secondary | Roles | Roles in M& E |
| 5 | NDPC | Policy direction, guidelines, capacity building, performance targets, advisory services etc. | M&E Plan preparation, indicator guidelines, PM &E, examiners of M&E results dissemination, and reports etc. |
| 6 | Office of Head of Local Government Service | Technical assistance, job analysis, management of services, etc. | M&E seminars & meetings, supervision, project inspection, evaluations, M&E results reporting and dissemination, etc. |
| 7 | RCC | Advisory services, capacity building, etc. | M&E plan preparation, evaluations, PM&E, data collection, M&E seminars & meetings, supervision, project inspection, M&E results reporting and dissemination, etc |
| 8 | CSOs / NGOs | Advocacy, financial and material resources, transparency and accountability, etc. | M&E seminars & meetings, supervision, project inspection, PM&E, data collection, M&E results reporting, etc. |
| 9 | Media | Transparency and accountability, etc. | Dissemination and Communication of M&E results |
| 10 | DACF Secretariat | Transparency and accountability, Financial and material resources, technical assistance, etc. | M&E seminars & meetings, supervision, project inspection, evaluations, M&E results reporting and dissemination, etc |
| 11 | Development Partners | Business development, transparency, accountability, financial and material resources | M&E seminars & meetings, supervision, project inspection, data collection, M&E results reporting, etc. |
| 12 | Consultants | Technical assistance, Advisory services | Facilitator of PM and E, M&E Plan preparation and evaluations, |

Source: DPCU, 2021

Table 6. 3: Monitoring and Evaluation Work Plan

| Activities | Time frame |  |  |  | Actors |
| --- | --- | --- | --- | --- | --- |
|  | 2022 | 2023 | 2024 | 2025 |  |
| MTDP Evaluations |  |  |  |  |  |
| DMTDP Mid-term Evaluation | Start end of year, 2023 |  |  |  | DPCU, Stakeholders |
| Terminal Evaluation | Start end of 2025 |  |  |  | DPCU, Stakeholders |
| Participatory M&E | Every year |  |  |  | DPCU, Stakeholders |
| Implementation monitoring |  |  |  |  |  |
| Inspection of projects | Every monthly |  |  |  | Works/Physical planning/ other Departments |
| Quarterly Field Visit | Third week of every quarter |  |  |  | DPCU, Stakeholders |
| Quarterly Review Meetings | 1st week of every quarter |  |  |  | DPCU, Stakeholders |
| Preparation of Quarterly reports | 12th Jan, April, July and October |  |  |  | DPCU |
| APR preparation and dissemination |  |  |  |  |  |
| Data collection and Collation | From 2nd week of January |  |  |  | DPCU |
| Data analysis and validation | From 14th January |  |  |  | DPCU, Stakeholders |
| Prepare Draft MDA APR | Mid - January |  |  |  | DPCU, Stakeholders |
| Organise Draft APR review workshop | Third week of January |  |  |  | DPCU, Stakeholders |
| Final APR submitted to NDPC | 20th February |  |  |  | DPCU, Stakeholders |
| Dissemination of District APR | First week of February. |  |  |  | DPCU, Stakeholders |

Source: DPCU, 2021

## Evaluation Arrangement

Evaluation is a key component in plan preparation. Its main purpose is to ascertain the expected impacts of implemented programmes and projects. The main types of evaluation include ex-ante evaluation; which is before project implementation, mid-term evaluation meaning in the middle of implementation, terminal which is at the end of implementation and ex-post; that is after implementation.

The DPCU which is the body in charge of preparation of quarterly and annual plans of the Assembly would undertake some forms of evaluation to enrich its reports.  In addition, the District Assembly would seek the assistance of Development Partners to engage consultants to assist in the evaluation of its projects and programmes in the DMTDP.

## Participatory Monitoring and Evaluation

The main reasons of conducting participatory Monitoring and Evaluating of the programmes and projects is to ensure transparency and accountability, efficient use of resources, project ownership and sustainability.

Some of the tools employed to undertake such activity include; Citizens Report Card, Community Score Cards, Participatory Rural Approach (transect walk, Mapping).  These tools enable citizens assess the duty bearers on the goods and services provided them. Through the use of these tools, service delivery is improved, efficiency and accountability are also measured.

Citizen Report Card (CRC) -The Citizen Report Card is a participatory evaluation tool to be used to obtain information from citizens on the performance of the government, service providers, programmes or projects.

Community Score Card (CSC) -With this, focus group discussions to collect data from community members for analysis, with the main objective being to influence the quality, efficiency and accountability with which services are provided at local level.

Transect Walk - It is a systematic walk with key informants through the area of interest, while observing, asking, listening, and seeking out problems and solutions.

Table 6.4 shows the PM and E template for the assessment of the outcome and impacts of the projects and programme in the DMTDP

| Name of the PM & E Tool | Policy/Prog/Project Involved | Consultant/resource persons Involved | Methodology used | Findings | Recommendations |
| --- | --- | --- | --- | --- | --- |
| Community Score Card/ Citizen Score Card | -Physical project 1. Construction of classroom block with ancillary facility 2.Construction of slaughter house | DPO, Works Engineer. | Focus Group Discussion Interviews, Field visit, Questionnaires | Would be after actual M & E | Would be after actual M & E |
|  | Programmes; - FSHP - MAG - LEAP | DPO, | Focus Group Discussion Interviews, Field visit, Questionnaires | Would be after actual M & E | Would be after actual M & E |
|  |  | Agric Director | Focus Group Discussion Interviews, Field visit, Questionnaires | Would be after actual M & E | Would be after actual M & E |
|  |  | SW/CD | Focus Group Discussion Interviews, Field visit, Questionnaires | Would be after actual M & E | Would be after actual M & E |

Table 6. 4 Participatory Monitoring and Evaluation Template

# CHAPTER SEVEN

# COMMUNICATION STRATEGY

## Introduction

The preparation of the District Medium Term Development Plan was a collaborative effort of stakeholders within and outside the district. Therefore, to ensure successful implementation of the plan, the same level of co-operation and collaboration from all stakeholders is required. In view of this, the DMTDP will need to be disseminated to all stakeholders so as to ensure effective implementation of the programmes and projects in the plan.

It specifies the dissemination of the plan and Annual Progress Reports (APR) during implementation. It would also outline ways to create awareness, promote access to information and management of public expectations.

One of the approaches to gain the support of all stakeholders in the implementation process is the efficient and effective communication of the provisions in the medium term development plan. Many agencies and institutions including the private sectors are prepared to fund and provide some financial support for some proposed projects and programmes in the plan.  However, this can only be possible if these agencies/stakeholders really understand the rational and the potential benefits of the proposed interventions.  Communication strategy is prepared to ensure public ownership of the programmes and projects and also to mobilize collective efforts from all stakeholders towards a sustainable development.

In this approach, attempts will be made to encourage greater collaboration and coordination with all stakeholders in the achievement of set targets and goals.  In order for maximum benefits to be derived from the implementation of planed interventions, much emphasis would be laid on transparency and accountability.

## Communication Objectives

The purpose of communication includes the following:

- Create awareness, eliminate any misunderstanding and distortions, and promote greater understandings, appreciation and acceptance of the Service and bridge the bureaucracy towards decentralization;

- Promote donor orientation, support, involvement and co-ordination;

- Advance a process to promote and sustain stakeholder involvement –participation, consultation, support, and collaboration.

- Ensure timely communication to relevant groups or individuals

- Ensure timely notices for requirements/meetings

- Ensure optimum results for all communications and project expectations

## Dissemination of the Medium-Term Development Plan

At a public hearing, the first final draft of the DMTDP (2022-2025) will be disseminated to stakeholders. At the Public hearings, the proposed interventions to address the various development issues will be presented to them to seek their final inputs and recommendation for the finalization of the plan. The communication strategy classified the following as major target groups based on their involvement in legislation, policy, funding, implementation, monitoring and evaluation and reporting arrangements. The major stakeholders/institutions identified include:

Member of Parliament and relevant Parliamentary Sub-Committees, especially the Committees on Local Government and Rural Development, Finance and Manpower, Youth and Employment;

- Ministers and Deputy Regional Ministers, Chief Directors and Directors

- Regional Coordinating Councils, Regional Ministers and Heads of Departments

- District Assemblies, Heads of Departments and Sub-District Councils

- Academia/ Research (including KNUST Department of Planning, GIMPA, ILGS etc)

- Sub-District Councils

- Development Partners

- Private Sector

- NALAG and Local Government Workers Union

- NGOS/ CSOs (including Religious Bodies)

The communication strategy could not have identified the stakeholders by chance. These are illustrated in the matrix (Table 7.1) below:

Table 7. 1: Matrix Showing Target Stakeholders and Purpose of Communication

| Target Institutions | Target Stakeholders | Basic Objective/Purpose of Communication |
| --- | --- | --- |
| Ministries, Departments and Agencies | Ministers Deputy Ministers Chief Directors | Create politically enabling environment and ensure top management support Develop co-operative atmosphere for a breakdown of barriers for successful implementation |
| Parliament | -Members of Parliament -Members of Select Committees on Local Government Members of other Select committees especially on Finance | Create political goodwill and legislative support and resource allocation |
| Regional Coordinating Councils (RCC) | -Regional Minister -Deputy Regional Minister -Regional Co-ord. Directors -Heads of Department of RCC | Ensure preparedness, capacity availability and ownership of project |
| District Assembly | Chief Executives Presiding Member Heads of Departments Assembly Members | Impart knowledge, abilities and skills necessary for successful implementation and sustainability |
| Sub-District Councils | Traditional Authorities Area and Urban council reps Sub-District Officers People | Ensure preparedness and ownership of projects |
| Development Partners | Multi-lateral Agencies Bi-Lateral Agencies CSOs/NGOs | Inform on developments and progress towards agreed objectives Financing support |
| Universities and Institute | Academics Researchers | Provide general knowledge and database |
| Private Sector | Businessmen | Provide general knowledge and create awareness on area of private sector participation ion service delivery |

Source: DPCU, 2021

## Approaches/Channels for Communication

The methodologies outlined below will focus on group and individual approaches or organizational through interaction, information dissemination, training, management development programmes, team building and survey feedback techniques.

The approaches to be used to achieve the above-objectives are:

- Newspapers/ Newsletter Publications

- Local Dailies

- Local Government Information Digest

- Broadcast media, TV and radio, public service announcements and call-ins;

- Workshops/Seminars

- Focus Group Discussions

- Consultative Meetings

- Briefing of RCCs and General Assembly during meetings

- District Website Updating (www.eda.gov.gh)

The Communication channels envisaged are:

Using Discussion Programmes

- Electronic Media: Radio (selected FM stations and other stations close to the Districts)

- Social Media: facebook (www.facebook.com/ellembelledistrictassembly), twitter, Instagram etc

- Print Media: Selected Newspaper for publication of Articles

- Using Information Services Division

Table 7. 2: Communication Strategies

| Activity | Purpose | Audience | Method/Tool | Timeframe | Responsibility |
| --- | --- | --- | --- | --- | --- |
| Public Forum | To create awareness on the DMTDP and gather feedback | Community members, Traditional authorities, NGOs etc | Community durbars | Quarterly | DPCU |
| Update DA website and Social Media Pages | To get the public to stay abreast with the activities of the DA | General Public | Uploading interventions on the platform | Jan – Dec each year | DPO |
| Radio Programmes | To update the populace on the status of implementa tion of development interventions | General Public | Technical officers of the Assembly engaged in radio discussions | Monthly | HoDs |
| Briefing of RCCs and General Assembly during meetings | To update them on the status of implementa tion of development interventions | DA Members and RCC | Technical officers of the Assembly engaged to brief GA and RCC on progress made through Progress Reports | Quarterly | DPCU |
| Consultative Meetings/ Town Hall Meetings | To get them to appreciate the DMTDP | Chiefs, Opinion leaders, NGOs | Technical officers of the Assembly engaged to brief them on progress made | Mid-Year | DPCU |
| Workshops/Seminars | To answer questions relating to the DA to enhance accountability | Selected Participants | DA staff partaking in workshops to clear erroneous impressions | Quarterly | HoDs |
| Newspapers/ Newsletter Publications | To Publish major accomplishments and challenges of the DA | General Public | Publish major accomplishments and challenges of the DA | Quarterly | DPCU |
| Using Information Services Division | To create awareness about DA projects and programmes | General Populace | Information van moving form community to community creating awareness | Quarterly | Information Department |
| Public Notice boards | To create awareness about DA projects and programmes | General Populace | Critical information pasted on notices to inform the populace | Monthly | DPCU |

# CONCLUSION

In pursuance of the mandate given to MMDAs by the Local Governance Act 2016, Act 936, the Ellembelle District Assembly has prepared its Medium Term Development Plan to guide the development aspiration of the people in the next four years (2022-2025). The Plan has been prepared in line with the Medium-Term National Development Policy Framework 2018-2021 provided by the NDPC.

The preparation of the Plan adopted a comprehensive bottom approach where stakeholders at all levels of society were consulted in the forms of Community Needs Assessment exercises, Public Hearing and Town Hall meetings to inform them and also to seek for their views as inputs into the Plan. Following from the above, the proposed projects/activities in the Plan reflect the development aspiration of the people and hence serve as the path to achieving the district’s development goals and objectives.

The total activities planned for the DMTDP, 2022-2025 have been estimated with the cost of Seventy-Five million, Seven Hundred and Seven Thousand, Four Hundred and Fifty-Two Ghana Cedis (GH¢ 75,707,452).

A monitoring framework has been developed to track the level of progress of the implementation of activities as against set indicators. This is to help institute an effective and efficient system for tracking the progress of programmes, and projects of the Assembly to foster greater collaboration with all stakeholders in the achievement of set targets.

Recognizing the important contributions of all stakeholders in the development of the district, a communication strategy has been formulated to create awareness about the Medium-Term Development Plan and to gain their support for effective implementation of the Plan. This is geared towards enhancing sustainability and ownership of the Plan and consequently, to achieve the mission and vision of the Assembly.

# References

Ghana Statistical Service (2014): 2010 Population and Housing Census – Ellembelle District, Accra, Ghana.

National Development Planning Commission (2021): Medium-Term National Policy Framework (2018-2021), Accra, Ghana.

National Development Planning Commission (2020): Guidelines for Preparation Sector and District Medium-Term Development Plans 2022-2025

National Development Planning Commission (2017): Draft Guidelines for the Preparation of District Medium-Term Development Plan under the Medium-Term National Development Policy Framework (2018-2021), Accra, Ghana.

Ellembelle District Assembly (2013): District Medium-Term Development Plan (2018-2021), Ellembelle, Ghana

National Monitoring and Evaluation Manual, 2017