| Programmes | Sub-programmes | Projects/activities | Location | Time Frame |  |  |  | Cost |  |  | Prog. Status |  | Implementing Dep'ts |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | 1 | 2 | 3 | 4 | GoG | IGF | Others | New | Ongoing | Lead | Coll. |
| Goal 1: Build a Prosperous Society |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ECONOMIC DEVELOPMENT | Local and economic development | - Support 1000 local businesses with training and start-kids | District Wide |  |  |  |  |  | 30,000 |  |  |  | BAC | DA |
|  |  | - Completion/ Construction of 4No market and renovate 1No market. | Esiama, Adubrim Nkroful, Aiyinase |  |  |  |  | 1,980,000.00 |  |  |  |  | Works Dep't | DA |
|  |  | - support the Registration of 50 local businesses. | District Wide |  |  |  |  |  | 3,000 |  |  |  | BAC | RGD |
|  |  | - Create a marketing platform for sellers and buyers of agric produce | District Wide |  |  |  |  |  | 10,000 |  |  |  | ENI/ BAC | Agri Dept/ENI |
|  |  | - Establish agro-processing Centres in selected communities | Allakpokpe, shoe factory |  |  |  |  | 5,000 |  |  |  |  | BAC | Agric/ DA |
|  |  | - Prepare and implement Local Economic Development (LED) Plan | District wide |  |  |  |  |  | 10,000.00 | 7,500 |  |  | BAC | DA |
|  |  | - Organize stakeholder forum with business community | District wide |  |  |  |  |  | 30,000 | 45,000 |  |  | BAC | Agri Dept., Private Sector,HODs |
|  |  | - Support the Implementation of the EDGE Project | Menzezor |  |  |  |  |  |  | 1,900,000.00 |  |  | ENI | MOFA/DA |
|  |  | - Establish and update database on all farmers in the district | District Wide |  |  |  |  | 4,100 |  |  |  |  | Agri Dept | DA/Statistics |
|  |  | - Advanced E-Extension and sensitization activities (study tour, malaria, COVID 19, child labour, HIV, pest and infections) | Menzezor, District Wide |  |  |  |  | 4.800 |  |  |  |  | Agri Dept | Works Dep't, DA/ NCCE |
|  |  | - Conduct yield studies on selected crops (rice, maize, cassava and plantain) | District Wide |  |  |  |  |  | 5,375 |  |  |  | Agri Dept. | MOFA |
|  |  | - Train farmers on climate smart agriculture technologies | District wide |  |  |  |  | 12,000 |  |  |  |  | Agric .Dept. | MOFA |
|  |  | - Early warning systems and emergency preparedness for livestock and crop production. (small ruminant, COVID,PPE and FAW) | District wide |  |  |  |  | 2,810.00 |  |  |  |  | Agric Dept | DA/NADMO |
|  |  | - Support the distribution of 10,000 (PERD) rubber seedling and 50,000 oil palm seedling by CSIR and MDF. | District wide |  |  |  |  | 21,500 |  |  |  |  | Agric Dept | DA |
|  |  | - Train 10 farmers (5 males and 5 females) on safe use and handling of Agro-Chemicals by the end of October 2022. |  |  |  |  |  | 950.00 |  |  |  |  | Agric Dept | DA |
|  |  | - Facilitate the implementation of Gov’t programmes (PERD, PFJ, DCACT etc) | District Assembly |  |  |  |  | 100,000.00 |  |  |  |  | Agri Dept | DA |
| Sub-Total |  |  |  |  |  |  |  | 413,600 | 175,575 | 58,500 |  |  |  |  |

| Program mes | Sub-programmes | Projects/activities | Location | Time Frame |  |  |  | Cost |  |  | Prog. Status |  | Implementing Dep'ts |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | 1 | 2 | 3 | 4 | GoG | IGF | Others | New | Ongoing | Lead | Coll. |
| Goal 2: Create Opportunities for all |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| EDUCATION AND TRAINI NG | Pre-Tertiary Education | - Support STMIE programme | Nkroful |  |  |  |  | 3,625 | 3,000 |  |  |  | GES | DA |
|  |  | - Completion of 2No. 6-unit classroom block | Esiama SDA, Kimtech. |  |  |  |  | 1,110,000.00 | 169,500 |  |  |  | DA | GES |
|  |  | - Completion of 5No. 3-unit classroom blocks and construction of 1No 3-unit classroom block | Nyamebekyere, Basake, Akropong, Awiebo, Awiaso, |  |  |  |  | 616,223.9 |  | 465,196.79 |  |  | DA | GES |
|  |  | - Completion 2No. KG and construction of 1No KG block | Anlobra, Teleku Bokazu, |  |  |  |  | 500,000 | 315,368.34 |  |  |  | DA | GES |
|  |  | - Construction of 1No. 4-unit teachers quarters | Adubrim |  |  |  |  | 40,000 | 20,000 | 50,000 |  |  | DA | GES |
|  |  | - Completion of Assembly Hall for Esiama Sec-Tec | Esiama |  |  |  |  | 412,000 | 47,500 |  |  |  | DA | GES |
|  |  | - Support to organize inter-school sports Competitions | District Wide |  |  |  |  |  | 10,000.00 |  |  |  | DA | GES |
|  |  | - Provide items for "my first day at school" celebrations and institute Best Teacher Award especially in deprived schools | Some Selected Schools especially in Aiyinase North |  |  |  |  | 20,000 | 18,500 | 15,000.00 |  |  | DA | GES/Private Schools |
|  |  | - Supply of classroom furniture to schools at all levels | Some Selected Schools |  |  |  |  | 90,000.00 | 20,000.00 |  |  |  | DA | GES |
|  |  | - Complete the overall upgrading and modernization of Charlotte Dolphine Training Institute | Sanzule |  |  |  |  | 700,000 |  |  |  |  | DA | GES |
|  |  | - Conduct induction workshop for newly trained teachers | District wide |  |  |  |  | 15,000 |  |  |  |  | GES | DA/HRM |
|  |  | - Support the conduct of SPAM in basic schools and Organize yearly mock exams for JHS students | District wide |  |  |  |  | 6,500 | 10,000.00 |  |  |  | GES | DA |
|  |  | - Support regular inspection and monitoring of schools.SMCs and PTAs | District wide |  |  |  |  |  | 4,500 |  |  |  | GES | DA |
|  |  | - Strenthen non-formal education, form clubs in 8 communities to establish a rice farm, piggery, poultry and fishponds | Asanta Kotokro, Sanzule |  |  |  |  |  | 7,100 | 4,125 |  |  | GES | Agric Dept, Private Sector |
|  |  | - Provision of medical supplies to CHPS Compounds | Ngalekyi |  |  |  |  |  | 6,000 | 7,500 |  |  | DA | GHS |
|  |  | - Construction / Completion of 2 No. CHPS Compounds | New Adiembra, Aluku, Azulenuonu |  |  |  |  | 600,000.00 |  |  |  |  | DA | GHS |
|  |  | - Complete the upgrading and expansion works at St. Martin De Porres Hospital, Eikwe | Eikwe |  |  |  |  |  |  | 9,000,000 |  |  | DA | GNPC |
|  |  | - Complete the construction of NHIS Office at Nkroful | Nkroful |  |  |  |  | 500,000 |  |  |  |  | DA | NHIS |
| HEALTH AND HEALTH SERVICE DELIVERY |  | - Conduct public health education and organize campaigns on mental health | District Wide |  |  |  |  |  | 8,000 |  |  |  |  |  |
|  |  | - Distribute 2500 insecticide treated mosquito nets | District Wide |  |  |  |  |  | 8,500 |  |  |  | GHS | DA |
|  |  | - Promote ante/post natal services and organize district health wide health screening activities. | District Wide |  |  |  |  | 7,500 |  | 4,000 |  |  | GHS | DA |
|  |  | - Continue the administration of vaccines under the NID programme | District Wide |  |  |  |  |  | 6,000 | 2,000 |  |  | GHS | DA |
|  |  | - Organize District wide Health Screening | District Wide |  |  |  |  |  |  | 33,000 |  |  | GHS | NGOs |
|  |  | - Embark on quarterly regenerative health and nutrition outreach programmes | District Wide |  |  |  |  | 12,125 |  |  |  |  | GHS | DA |
|  | HIV, AIDS/STIs and other infections | - Intensify comprehensive education on HIV/AIDS and STIs, including reduction of stigmatisation | District wide |  |  |  |  | 4,625 |  | 6,250 |  |  | GHS | NGOs |
|  |  | - Organize quarterly HIV/AIDS Committee Meetings and world AIDS day. | Nkroful |  |  |  |  | 11,000.00 |  |  |  |  | DAC | GHS |
|  | Population Management | - Support the GSS to collect population data | District wide |  |  |  |  | 12,700 |  |  |  |  | Statistical Dept. | DA |
|  |  | - Ensure registration of all birth and death in the district | District wide |  |  |  |  |  | 1,000 |  |  |  | Birth & death Dept. | DA |
|  |  | - Provide support for family planning activities | District wide |  |  |  |  |  |  |  |  |  | GHS | DA |
|  | Food and Nutrition | - Organize food and nutrition campaign in schools and health centres and on radio | District wide |  |  |  |  |  | 13,000 |  |  |  | GHS/EHSU | DA |
|  |  | - Monitor the school feeding programme to ensure quality and well balanced diet is served | District wide |  |  |  |  | 1,500 |  |  |  |  | Central Admin | DA |
| WATER AND ENVIRONMENTAL SANITATION | Water Supply, Waste Management and Environmental Sanitation | - Drilling of 10No. Disability friendly Mechanized boreholes | Anokye, Baku, Asanta. Ngalakyi Baku, Asomase, Aluku, Ankobra, Ewe community and others. |  |  |  |  | 250,000 |  | 10,000 |  |  | DWST | CWSA/WSMT |
|  |  | - Construction/ Extension of water supply for selected communities | Selected communities |  |  |  |  |  |  |  |  |  | DWST | CWSA/WSMT |
|  |  | - Prepare, and implement the District Water and Sanitation Plan | District Assembly |  |  |  |  |  | 4,500 |  |  |  | DWST | DA |
|  |  | - Support the activities of water and sanitation management teams and ECG |  |  |  |  |  | 15,000.00 |  |  |  |  | DWST | DA |
|  |  | - Construction / Completion of 3No. gender-disability friendly institutional latrines | Basake, Asanda, Aweibo Tandan |  |  |  |  | 35,000 |  |  |  |  | Works Dept. | EHSU |
|  |  | - Monitor waste collection by zoomlion | Market Places |  |  |  |  |  | 2,000 |  |  |  | EHSU | DA |
|  |  | - Monitor Day Care Centres and orphanages within the district | District Wide |  |  |  |  | 5,000 | 2,000 |  |  |  | SWCD | DA |
|  |  | - Organize sensitization programmes on child protection issues | District Wide |  |  |  |  |  | 13,000 |  |  |  | SWCD | DA, NCCE, LABOUR DEP'T, NCCE |
|  |  | - Institute Child Protection Committees in 10 Communities | District wide |  |  |  |  |  | 5,000 |  |  |  | SWCD | DA |
|  |  | - Settle child maintenance cases and follow-ups | District wide |  |  |  |  |  | 5,000 |  |  |  | SWCD | UNICEF |
|  |  | - Organise and support community mobilization activities in 10 communities | District wide |  |  |  |  |  | 1,500 | 625 |  |  | SWCD | Gender Desk |
|  | Women empowerment | - Organize sensitization Campaigns on gender-based violence and other harmful cultural practices in 10 Community | District Wide |  |  |  |  | 7,100 |  | 2,500 |  |  | SWCD | DA/UNICEF |
|  |  | - Organize skill training for women on VSLA and other income generating activities | District Wide |  |  |  |  |  | 2,000 | 3,000 |  |  | SWCD | DA, BAC |
|  |  | - Support People With Disabilities (PWDs) | District Wide |  |  |  |  | 200,000.00 |  |  |  |  | SWCD | NHIS,BAC, DA |
|  |  | - Monitor and support the Livelihood Empowerment Against Poverty (LEAP) programme including NHIS registration | District wide |  |  |  |  |  | 2,000.00 |  |  |  | SWCD | DA |
|  |  | - Celebration of Women’s Day | Krisan Camp |  |  |  |  | 2,000.00 |  |  |  |  | SWCD | DA |
| Sub-Total |  |  |  |  |  |  |  | 17,251,500 | 641,900 | 10,311,289 |  |  |  |  |

| Programmes | Sub-programmes | Projects/activities | Location | Time Frame |  |  |  | Cost |  |  | Prog. Status |  | Implementing Dep'ts |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | 1 | 2 | 3 | 4 | GoG | IGF | Others | New | Ongoing | Lead | Coll. |
| Goal 3: Safeguard the Natural Environment and ensure a resilient Built Environment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| NATURAL RESOURCE MANAGEMENT | Deforestation, Desertification and Soil Erosion | - sensitize 10 communities on improved sanitation | District Wide |  |  |  |  |  | 10,000.00 |  |  |  | EHSU | DA |
|  |  | - Noise pollution control | Districtwide |  |  |  |  |  | 8,000 |  |  |  | EHSU | DA |
|  |  | - Educate and inspect galamsey sites to reclaim degraded lands and plant trees. | District wide |  |  |  |  |  | 30,000.00 |  |  |  | EHSU | DA, NADMO, FORESTRY |
|  |  | - Management of communal landfill site | Ampain |  |  |  |  | 40,000 |  | + |  |  | EHSU | PPD, DA |
|  |  | - Sensitization, Screening and monitoring of food vendors | District Wide |  |  |  |  | 10,000 |  |  |  |  | EHSU | DA |
|  |  | - Organization of National sanitation day | District Wide |  |  |  |  | 15,000.00 |  |  |  |  | EHSU | DA |
|  |  | - support the activities of forestry Commission | District wide |  |  |  |  |  | 10,000.00 |  |  |  | Forestry Comm | DA |
|  |  | - Support the activities of EPA | District wide |  |  |  |  | 15,000.00 |  |  |  |  | EPA | DA |
|  |  | - Monitoring of roads in the District | Selected communities |  |  |  |  | 20,000.00 |  |  |  |  | Feeder Roads | DA |
|  |  | - Support road safety activities in the District | District Wide |  |  |  |  | 120,000.00 |  |  |  |  | Road Safty | DA |
|  | Human Settlements Development and Housing | - Organize technical and statutory planning committee meetings | District Assembly |  |  |  |  |  | 6,000 |  |  |  | PPD | HODs |
|  |  | - Preparation of local plans | Bomoakpole |  |  |  |  |  | 1,000 |  |  |  | PPD | DA |
|  |  | - Sensitization of the public on LUPMP and permitting | District Wide |  |  |  |  |  | 2,000 |  |  |  | PPD | Works Dep't, DA |
|  |  | - Organize joint inspections to check unauthorised developemts | District Wide |  |  |  |  |  | 20,000.00 |  |  |  | PPD | Works Dep't, DA |
|  | Infrastructure Maintenance | - Organize capacity building training in inventory and asset management for selected staff | District Assembly |  |  |  |  |  | 6,000 |  |  |  | HR | DA |
|  |  | - Prepare and implement operation and maintenance (O&M) Plan | District Assembly |  |  |  |  | 3,000 |  |  |  |  | Works Dep't | Dev't Planning Unit |
|  |  | - Undertake building inspections and ensure that all public buildings disable friendly | District wide |  |  |  |  |  | 8,250 |  |  |  | Works Dep't | DA |
| Sub-Total |  |  |  |  |  |  |  | 23,685,650 | 229,620 | 13,000 |  |  |  |  |

| Programmes | Sub-programmes |  | Projects/activities |  | Location |  | Time Frame |  |  |  |  |  |  |  | Cost |  |  |  |  |  | Prog. Status |  |  | Implementing Dep'ts |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  | 1 |  | 2 |  | 3 |  | 4 |  | GoG |  | IGF |  | Others |  | New |  | Ongoing | Lead |  | Coll. |  |
| Goal 4: Maintain a Stable, United and Safe Society |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Resource Mobilization and Expenditure Management |  | - Update economic/ Tourism data to improve revenue |  | District wide |  |  |  |  |  |  |  |  |  | 100,000.00 |  |  |  |  |  |  |  |  | Statistical Dept. |  | Revenue Unit |  |
|  |  |  | - Provide revenue collection and management logistics |  | District Assembly |  |  |  |  |  |  |  |  |  | 12,000 |  |  |  |  |  |  |  |  | Revenue Unit |  | GIZ, DA |  |
|  |  |  | - Organize public sensitization on revenue mobilization at market places and lorry stations |  | Aiyinase, Asasetre, Esiama, Teleku Bokazo |  |  |  |  |  |  |  |  |  |  |  | 7,500 |  |  |  |  |  |  | Revenue Unit |  | Budget/Finance, Works, PPA |  |
|  |  |  | - Mount and update revenue performance and Accountability Bill Boards at the Various Area Councils |  | Esiama, Asasetre, Awiebo Basake, Aiyinase, Kikam, Nkroful, Atoabo |  |  |  |  |  |  |  |  |  | 22,000 |  |  |  |  |  |  |  |  | Fin. Dep't |  | DA |  |
|  |  |  | - Prepare and Implement a Revenue Improvement Action Plan (RIAP) and all budgetary and procurement documents |  | District Assembly |  |  |  |  |  |  |  |  |  |  |  | 7,000 |  |  |  |  |  |  | DBU/Fin Dept |  | DA |  |
|  |  |  | - process personnel inputs and submit timely |  | Administration |  |  |  |  |  |  |  |  |  |  |  | 5,000.00 |  |  |  |  |  |  | HRM. |  | DA |  |
| DEMOCRACY, GOVERNANCE AND PUBLIC ACCOUNTABILITY | Local Government and Decentralization |  | - strengthen the operations of Area councils |  | Selected communities |  |  |  |  |  |  |  |  |  | 500,000.00 |  | 500,000 .00 |  |  |  |  |  |  | DA |  | WORKS/DPO |  |
|  |  |  | - Organize all statutory planning meetings |  | District Assembly |  |  |  |  |  |  |  |  |  | 100,000.00 |  | 50,000.00 |  |  |  |  |  |  | Central Admin |  | DA |  |
|  |  |  | - Review and prepare Annual Action Plans, procurement plans and Composite Budgets |  | District Assembly |  |  |  |  |  |  |  |  |  | 50,000.00 |  |  |  |  |  |  |  |  | Dev't Planning, Budget Unit |  | HODs |  |
|  |  |  | - Undertake Town Hall Meetings on AAPs, fee-fixing and composite annual budget |  | Esiama, Nkroful |  |  |  |  |  |  |  |  |  | 50,000 |  | 10,000.00 |  | 5,000 |  |  |  |  | Dev't Planning/Budget |  | HODs, DA |  |
|  |  |  | - Organize Public Hearings of the MTDP (2022-2025). |  | District Assembly |  |  |  |  |  |  |  |  |  | 5,000 |  | 4,000 |  | 5,000 |  |  |  |  | DPO |  | HODs, other stakeholders |  |
|  |  |  | - Administer comprehensive HRMIS and submit monthly returns to RCC |  | District Assembly |  |  |  |  |  |  |  |  |  |  |  | 1,800 |  |  |  |  |  |  | HR |  | HODs |  |
|  |  |  | - Organize training for Revenue collectors and Area council members for effective revenue collection |  | District Assembly |  |  |  |  |  |  |  |  |  |  |  | 40,000.00 |  |  |  |  |  |  | HR |  | DA |  |
|  |  |  | - Enforce the implementation of PFM, PPA and GIFMIS |  | District Assembly |  |  |  |  |  |  |  |  |  |  |  | 10,000.00 |  |  |  |  |  |  | FINANCE |  | BUDGET/DA |  |
|  |  |  | - Organize capacity building training for all staff and Assemblymembers |  | District Assembly |  |  |  |  |  |  |  |  |  | 5,000 |  |  |  |  |  |  |  |  | HR |  | Fin. Dep't, HODs |  |
|  |  |  | - Procure office stationery logistics and others |  | District Assembly |  |  |  |  |  |  |  |  |  | 100,000.00 |  |  |  |  |  |  |  |  | Procurement |  | DA |  |
|  |  |  | - Support all renovation/ Maintenance of office equipment and logistics |  | District Assembly |  |  |  |  |  |  |  |  |  | 50,000.00 |  |  |  |  |  |  |  |  | Procurement |  | DA |  |
|  | Human Security and Public Safety |  | - Construction of Police Station |  | Asomase |  |  |  |  |  |  |  |  |  |  |  | 50,000 |  |  |  |  |  |  | DA |  | GPS |  |
|  |  |  | - support the activities of GNFS |  | Selected Communities |  |  |  |  |  |  |  |  |  | 8,300 |  |  |  |  |  |  |  |  | GNFS |  | DA, NADMO |  |
|  |  |  | - Support the activities of NCCE |  |  |  |  |  |  |  |  |  |  |  |  |  | 12,000 |  |  |  |  |  |  | NCCE |  | DA |  |
|  | Corruption and Economic Crimes |  | - Support all activities of the Audit unit including audit committes |  | District Assembly |  |  |  |  |  |  |  |  |  | 10,000 |  |  |  |  |  |  |  |  | Internal Audit |  | External Audit |  |
|  |  |  | - Support the Police Service and other Security Agencies with Logistics |  | District Assembly |  |  |  |  |  |  |  |  |  | 60,500 |  |  |  | 50,000 |  |  |  |  | DISEC |  | GPS |  |
|  |  |  | - support the celebration of all National Events |  | District Wide |  |  |  |  |  |  |  |  |  |  |  | 100,000.00 |  |  |  |  |  |  | Central Admin |  | DA |  |
|  |  |  | - Support the activities of NHIA |  | District wide |  |  |  |  |  |  |  |  |  | 10,000.00 |  |  |  |  |  |  |  |  | NHIA |  | DA |  |
|  |  |  | - Support Religious activities |  | District Wide |  |  |  |  |  |  |  |  |  | 21,800 |  |  |  |  |  |  |  |  | DA |  |  |  |
|  | Culture |  | - Organize story telling competition in Nzema and Fanti and cultural festivals for basic schools |  | Selected Schools |  |  |  |  |  |  |  |  |  | 2,000 |  |  |  |  |  |  |  |  | GES |  | DA |  |
| TOTAL |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 104,700 |  | 170,350 |  | 18,500 |  |  |  |  |  |  |  |  |
| Programmes | Sub-programmes | Projects/activities |  | Location |  | Time Frame |  |  |  |  |  |  |  | Cost |  |  |  |  |  | Prog. Status |  |  |  |  | Implementing Dep'ts |  |  |  |
|  |  |  |  |  |  | 1 |  | 2 |  | 3 |  | 4 |  | GoG |  | IGF |  | Others |  | New |  | Ongoing |  |  | Lead |  | Coll. |  |
| Goal 5: Mainstream emergency planning and preparedness into Ghana’s development planning agenda at all levels to respond to potential internal and external threats (including COVID-19) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| EMERGENCY PLANNING AND RESPONSE (INCLUDING COVID-19 RECOVERY PLAN) | Hydrometeological Threats | - Organize community sensitizations on disaster prevention |  | District Wide |  |  |  |  |  |  |  |  |  | 90,500 |  |  |  |  |  |  |  |  |  |  | NADMO |  | DA, NCCE |  |
|  |  | - Organize pests and insect infection sensitization campaign in communities |  | District Wide |  |  |  |  |  |  |  |  |  |  |  | 16,000 |  | 4,500 |  |  |  |  |  |  | NADMO |  | MOFA, NCCE |  |
|  |  | - Formation of Disaster Risk Reduction clubs in schools and communities |  | Selected Schools |  |  |  |  |  |  |  |  |  |  |  | 8,000 |  |  |  |  |  |  |  |  | NADMO |  | GES, DA |  |
|  |  | - Provide support for disaster victims |  | District Wide |  |  |  |  |  |  |  |  |  |  |  | 50,000 |  | 50,000 |  |  |  |  |  |  | NADMO |  | GNFS, DA |  |
|  |  | - Collaborate with forestry to undertake tree-planting exercise |  | Selected communities |  |  |  |  |  |  |  |  |  | 20,000 |  |  |  | 10,000 |  |  |  |  |  |  | Forestry |  | Agri Dept.NADMO DA |  |
|  | Biological Threats | - Undertake surveillance, monitoring and evaluation of Health threats and epidemics and pandemics |  | District Wide |  |  |  |  |  |  |  |  |  |  |  | 6,000 |  |  |  |  |  |  |  |  | DHD |  | NCCE |  |
|  | Anthropogenic Threats | - Support National Ambulance Service |  | District Wide |  |  |  |  |  |  |  |  |  |  |  | 6,000 |  |  |  |  |  |  |  |  | GHS |  | DA |  |
|  |  | - Intensify monitoring at Filling Stations to ensure adherence to Standard Operating Procedures. |  | District Wide |  |  |  |  |  |  |  |  |  |  |  | 6,000 |  |  |  |  |  |  |  |  | GNFS |  | Security agencies |  |
|  |  | - Establish a well-resourced Emergency Centre |  | District Wide |  |  |  |  |  |  |  |  |  |  |  | 6,000 |  |  |  |  |  |  |  |  | DA |  | Private Sector |  |
|  | Security | - Organize Annual ADR week Celebration |  | District Wide |  |  |  |  |  |  |  |  |  |  |  | 6,000 |  |  |  |  |  |  |  |  | DA |  |  |  |
|  |  | - Support Police and other Security Forces |  | District Wide |  |  |  |  |  |  |  |  |  |  |  | 6,000 |  |  |  |  |  |  |  |  | DA |  | NGO |  |
|  |  | - Support Public Health Emergency Management Committee |  | District Wide |  |  |  |  |  |  |  |  |  |  |  | 4,800 |  |  |  |  |  |  |  |  | DA |  | DHD |  |
|  |  | - Vaccinate 50,000 people against covid-19 |  | District Wide |  |  |  |  |  |  |  |  |  |  |  | 35,000 |  |  |  |  |  |  |  |  | DHD |  | DA |  |
| Sub-Total |  |  |  |  |  |  |  |  |  |  |  |  |  | 17,500 |  | 118,300 |  | 12,000 |  |  |  |  |  |  |  |  |  |  |

| Programmes | Sub-programmes | Projects/activities |  | Location | Time Frame |  |  |  | Cost |  |  | Prog. Status |  | Implementing Dep'ts |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | 1 | 2 | 3 | 4 | GoG | IGF | Others | New | Ongoing | Lead | Coll. |
| Goal: 6 Improve delivery of development outcomes at all levels |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| IMPLEMENTATION, COORDINATION, MONITORING AND EVALUATION | Implementation and Coordination | - Organize quarterly DPCU Meetings |  | District Assembly |  |  |  |  | 15,000 | 5,000 |  |  |  | Dev't Planning | HODs |
|  |  | - Prepare quarterly and Annual Progress Reports |  | District Assembly |  |  |  |  | 10,000 |  | 3,000 |  |  | Dev't Planning | HODs |
|  |  | - Organize Capacity Building programme for DPCU members |  | District Assembly |  |  |  |  | 6,000 | 2,500 |  |  |  | Dev't Planning | HODs |
|  | Monitoring and Evaluation | - Organize quarterly Participatory Project/programme Monitoring |  | District Assembly |  |  |  |  | 62,000 .00 | 50,000.00 |  |  |  | Dev't Planning | HODs, DA |
|  |  | - Conduct mid-term review of 2018-2021 DMTDP |  | District Assembly |  |  |  |  | 25,000 |  | 2,500 |  |  | Dev't Planning | HODs, DA |
|  |  | - Organize Quarterly M&E Review Meetings |  | District Assembly |  |  |  |  | 5,000 |  |  |  |  | Dev't Planning | HODs |
|  | Data-Based Planning and Budgeting | - Establish District Statistical Working Group and train Field Officers |  | District Assembly |  |  |  |  | 1,000 |  |  |  |  | Statistical Dept. | HODs |
|  |  | - Establish and update Central Database for Planning and Budgeting |  | District Assembly |  |  |  |  | 10,000 |  |  |  |  | Statistical Dept. | HODs |
|  |  | - Disseminate statistical Data and projections with Relevant Units, Departments and Agencies in the District. |  | District Assembly |  |  |  |  | 10,000 |  |  |  |  | Statistical Dept. | HODs |
| Sub-Total |  |  |  |  |  |  |  |  | 69,000 | 10,000 | 5,500 |  |  |  |  |
| GRAND TOTAL |  |  |  |  |  |  |  |  | 41,541,950 | 1,345,745 | 10,418,789 |  |  |  |  |